## Features
ID | Feature | Where | Status | Local tests | Test (staging) | Prod | Flag | Evidence / notes
F1 | Audit of existing bank / wallet / payout code | Docs | Done | n/a | n/a | n/a | — | docs/gig-bank-payouts-2026-10/FINDINGS.md: bank accounts, ₹1 + bank check, refunds to bank, payout providers, weekly rider batches all existed and were reused
F2 | Bank account for customers (refunds) | Web + Android + iOS | Done (existing) | Pass | Live already | Live already | — | Unchanged; covered again by the new test (add + verify)
F3 | Bank account for delivery partners (same personal account) | Web + Android + iOS | Done | Pass | Not deployed | Not deployed | rider_bank_account_enabled | /gig/wallet; add, verify (₹1 / bank check), change, remove
F4 | Emailed code before changing / removing a rider's verified account | Web + Android + iOS | Done | Pass | Not deployed | Not deployed | rider_bank_account_enabled | 10-minute single-use grant; customers never asked
F5 | Masking and encryption of account numbers | All | Done (existing) | Pass | Live already | Live already | — | AES-256-GCM at rest, last 4 only in screens, notifications and logs
F6 | Wallet → bank withdrawal (riders' earnings) | Web + Android + iOS | Done | Pass | Not deployed | Not deployed | rider_withdrawal_enabled | ₹100–₹10,000, ₹10,000/day, no fee; quote with fee, TDS, settlement; emailed code; debit released on failure
F7 | Customer wallet → bank withdrawal | — | Not started (owner: No) | n/a | n/a | n/a | — | Owner 31 Oct: customer wallet stays closed (RBI closed PPI, wallet terms). Refund-to-bank path unchanged
F8 | Bank transactions in a ledger with status | Web | Done | Pass | Not deployed | Not deployed | — | rider_bank_transfers: PENDING / PROCESSING / SUCCESS / FAILED / REVERSED / RELEASED + rider_transfer_events + finance ledger RIDER_PAYOUT / REVERSAL
F9 | Failure handling (reverse, notify) | Web + push + email | Done | Pass | Not deployed | Not deployed | — | Refused withdrawal → back to balance; unknown outcome → finance; reversed after success → back to balance
F10 | Monthly payout on the 5th, 09:00 IST | Server (hourly cron) | Done | Pass | Not deployed | Not deployed | rider_monthly_payout_enabled | Pays previous month's unpaid earnings; eligibility approved + verified account + ≥ ₹100; carry-forward
F11 | Idempotent run, resume after interruption | Server | Done | Pass | Not deployed | Not deployed | — | rider_payout_runs one row per month; unique run + rider; provider idempotency key per attempt
F12 | Retries then manual review | Server + Admin | Done | Pass | Not deployed | Not deployed | — | 3 retries (60/120/180 min), then Admin → Rider payouts: Retry / Return to balance
F13 | TDS s.194C on rider payouts | Server | Done | Pass | Not deployed | Not deployed | — | 1% / 20% without PAN above ₹30,000 single or ₹1,00,000 a year; CA to confirm section and filing
F14 | Notifications and payout summary | In-app + email + push (apps) | Done | Pass | Not deployed | Not deployed | — | 4 new templates; statement page per payment
F15 | Admin view of runs, failures, totals | Web | Done | Pass (UI checked locally) | Not deployed | Not deployed | rider_bank_account_enabled | /admin/rider-payouts and /admin/rider-payouts/[id]
M1 | Android app: wallet, withdrawal, payouts, notifications | Android | Done (no app change needed) | Not run on device | Not run | Not run | — | The app is a WebView of the site (mobile/README.md): new pages and push arrive without a store build. Phone layout checked at 375 px in a browser
M2 | iPhone app: wallet, withdrawal, payouts, notifications | iOS | Done (no app change needed) | Not run on device | Not run | Not run | — | As M1
T1 | Full suite, single database | CI / local | Running in CI (PR #309) | Running in CI (PR #309) | Pending | n/a | — | See TEST_RESULTS_rider_bank_payouts_2026-10-31.md
T2 | Full suite, two-database split | CI / local | Running in CI (PR #309) | Running in CI (PR #309) | Pending | n/a | — | As T1
T3 | Prod smoke test with small real amounts | gokesari.com | Blocked | n/a | n/a | Blocked | — | Needs Cashfree Payouts keys on production and the owner to run it: Claude does not move real money

## Decisions
Item | Decision / status | Who | Date
Customer wallet cash-out | No — riders only | Owner | 31 Oct 2026
Weekly vs monthly | Keep both | Owner | 31 Oct 2026
Withdrawal limits / fee | ₹100–₹10,000 each, ₹10,000/day, no fee; monthly minimum ₹100; 3 retries | Owner | 31 Oct 2026
TDS | s.194C 1% / 20% without PAN, thresholds ₹30,000 / ₹1,00,000 | Owner | 31 Oct 2026
Payout provider keys on production | OPEN — Cashfree Payouts (or RazorpayX) keys and rule riderPayouts.provider | Owner
TDS filing (26Q, Form 16A), 194C vs 194-O | OPEN — CA to confirm | Owner / CA
Social Security Code aggregator contribution | OPEN — not in this change | Owner / CA
KYC level for payouts | Today: partner APPROVED. Tighten when PAN/Aadhaar rider KYC lands | Owner

## Summary
Item | Value
Date | 31 Oct 2026
Branch | feat/gig-bank-payouts — PR #309 into staging (https://github.com/sanjaymorankar-debug/GoKesari/pull/309)
Migration | 0123_rider_bank_payouts (additive; rollback scripts/rollback-0123.sql)
Flags | rider_bank_account_enabled, rider_withdrawal_enabled, rider_monthly_payout_enabled — all OFF
Docs | docs/gig-bank-payouts-2026-10/README.md, FINDINGS.md