## Summary
Inventory & Accounting for shop owners — feature tracker (2026-10-15)
Status: Done / In progress / Not started / Blocked (dropdown in 'Features' column F). Counts below are formulas.
Status | Features
Done
In progress
Not started
Blocked
Total
Part | Done | In progress | Not started | Blocked
1 Inventory
2 Accounting
3 GST portal
4 Soft copy
5 Hard copy
6 Review
7 Data & security
UI
Mobile
QA

## Features
ID | Part | Feature / sub-feature | What it does | Where it runs | Status | Notes / blocked on
IA-001 | 1 Inventory | Product master per shop | Listings linked to the gokesari.com master product (MRP, HSN, GST rate, unit, barcode/GTIN); shop-level HSN/GST/price stay per shop |  | Done
IA-002 | 1 Inventory | Stock ledger | inv_stock_ledger: every movement (opening, purchase, sale, sale return, damage/expiry write-off, adjustment, reversal) with date, source document, qty, cost/rate, user; current stock = sum of the ledger |  | Done
IA-003 | 1 Inventory | Online orders reduce stock in real time | DB triggers on shop_products / inventory_movements write the ledger row in the checkout / cancellation / subscription / catalogue transaction (event-driven, no cron, existing code unchanged) |  | Done | Verified on test.gokesari.com with a real customer order (stock 199 → 198, SALE row with the order id) and its cancellation; a cancellation is labelled SALE_RETURN since migration 0078 (found in staging testing)
IA-004 | 1 Inventory | Opening balance backfill | Migration 0076 writes today's stock of every listing as OPENING so ledger = stock from day one; drift check on the stock page |  | Done
IA-005 | 1 Inventory | Batch & expiry tracking | Per listing (auto-on when a bill has batch numbers); FEFO batch balances; expiring-soon list with alert window setting |  | Done
IA-006 | 1 Inventory | Low stock / reorder level | Existing per-shop thresholds and stock alerts reused; purchases and write-offs re-evaluate alerts |  | Done
IA-007 | 1 Inventory | Stock valuation FIFO / weighted average | Selectable per shop; reversals take back exactly the reversed cost; uncosted opening stock valued at last purchase rate and reported |  | Done
IA-008 | 1 Inventory | Loose goods & unit conversions | kg/g/L/ml/piece/dozen, UQC codes, Hindi/Marathi unit words; owner-saved conversions (1 case = 24); fractional quantities exact in the ledger |  | Done
IA-009 | 1 Inventory | Write-off and physical count | Damage / expiry write-off at cost (P&L line); physical count posts the difference as an adjustment |  | Done
IA-010 | 2 Accounting | Purchase register | Confirmed bills, versions, cancellations; month filter |  | Done
IA-011 | 2 Accounting | Sales register | Own GST invoices plus GoKesari order tax invoices |  | Done
IA-012 | 2 Accounting | Supplier & customer ledgers | Parties with GSTIN, credit days, opening balance; running-balance ledger from the books |  | Done
IA-013 | 2 Accounting | Cash / bank book | Opening, in, out, closing, running balance |  | Done
IA-014 | 2 Accounting | Expenses | Categories, claimable GST, cash/bank/credit, cancel with reason |  | Done
IA-015 | 2 Accounting | Payables / receivables with ageing | 0-30 / 31-60 / 61-90 / 90+ by due date; payments applied to the named bill, then oldest first |  | Done
IA-016 | 2 Accounting | Double-entry books | Balanced vouchers, append-only, reversing vouchers for corrections and cancellations; trial balance |  | Done
IA-017 | 2 Accounting | GST sales invoice (CGST/SGST/IGST by place of supply) | Rule-46 fields, numbering per FY, GST-inclusive pricing option, PDF, cancel |  | Done
IA-018 | 2 Accounting | Reports: P&L, stock summary, day book, GST summary, registers | Perpetual COGS, write-offs, expenses net of GST |  | Done
IA-019 | 2 Accounting | Export Excel / PDF / Tally XML | Every report as xlsx and PDF; Tally import XML with party masters (GSTIN) and vouchers |  | Done | Tally import to be confirmed on the shop's own TallyPrime
IA-020 | 3 GST portal | Link GSTIN once (consent + OTP) | Consent text recorded, portal username, OTP, token stored encrypted, unlink |  | Done | Consent + username + OTP through the GSP adapter; refused on production (no licensed GSP, IA-022). On test.gokesari.com blocked by the encryption key format (IA-056) — tokens are never stored unencrypted. Passes in the integration tests (mock GSP)
IA-021 | 3 GST portal | Pluggable GSP adapter | GST_RETURNS_PROVIDER: none / mock / GSP slots (masters_india, cleartax, iris, tally_gsp, vayana) |  | Done
IA-022 | 3 GST portal | Licensed GSP live connection | Real GSTR-2B/2A/1 pull from the GST system | Code on undefined; not switched on | Blocked | Needs a GSP contract and API credentials chosen by the owner; until then the manual upload works on gokesari.com
IA-023 | 3 GST portal | Pull GSTR-2B / 2A / GSTR-1 (API) | Through the configured adapter; mock on test.gokesari.com |  | Done | Live only with a GSP (IA-022); on test blocked by IA-056. Passes in the integration tests (mock GSP, OTP 575757)
IA-024 | 3 GST portal | Manual fallback: upload GSTR-2B JSON / Excel | GSTR-2B JSON (both shapes), GSTR-2A, GSTR-1 JSON, GSTR-2B Excel with merged headers |  | Done
IA-025 | 3 GST portal | Reconciliation | Supplier GSTIN + invoice no. + date + amount; matched, amount mismatch, missing in books, missing on portal; ITC status updated |  | Done
IA-026 | 3 GST portal | GST liability dashboard (month / quarter) | Output - reconciled ITC = net payable per CGST/SGST/IGST/cess with the legal set-off order and carry forward; pending ITC shown separately |  | Done
IA-027 | 3 GST portal | Due dates and reminders | Monthly / QRMP due dates (GSTR-1, GSTR-3B, PMT-06); daily reminder cron, one reminder per return and period |  | Done | Owner to schedule /api/cron/gst-reminders on the server (see README)
IA-028 | 3 GST portal | Estimates only, no filing | 'Verify with your CA before filing' on every GST figure; nothing is filed |  | Done
IA-029 | 4 Soft copy | Upload PDF / photo / Excel / e-invoice JSON | Up to 10 files, sniffed types, progress bar for slow networks |  | Done
IA-030 | 4 Soft copy | Share to app (WhatsApp / email / Files) | PWA share target: installed site on Android receives shared bills |  | Done
IA-031 | 4 Soft copy | Share straight into the native Android/iOS app | Native share-intent module + new store build | Code on undefined; not switched on | Blocked | Needs a native share-intent module and an EAS store build tested on a device; share to the installed website or forward by email meanwhile
IA-032 | 4 Soft copy | Forward by email | Private per-shop address bills+<id>-<sig>@domain; inbound webhook /api/inbound/bill-email | Code on undefined; not switched on | Blocked | Code done and tested; needs an inbound mail provider + INBOUND_EMAIL_SECRET / INBOUND_EMAIL_DOMAIN on the server
IA-033 | 4 Soft copy | E-invoice JSON / signed QR as trusted source | IRP JSON (plain or signed), signed QR decoded from photos and PDFs; RS256 check when NIC key configured |  | Done | Signature check needs EINVOICE_QR_PUBLIC_KEY (NIC public key)
IA-034 | 4 Soft copy | AI document parsing | Claude reads supplier, GSTIN, number, date, lines, totals with per-field confidence | Code on undefined; not switched on | Blocked | Code done; needs ANTHROPIC_API_KEY + INVOICE_EXTRACTION_PROVIDER=claude on the servers (owner decision: bills are sent to Anthropic for reading)
IA-035 | 4 Soft copy | Local extraction fallback | Excel item tables, PDF text layer, OCR text with rules |  | Done | OCR worker does not start on Hostinger (same as the document reader, NEW-062): photos fall back to typing
IA-036 | 4 Soft copy | Match lines to product master | Remembered supplier mapping, barcode/GTIN, HSN + name, name; suggestions; create new product (reuses the master by barcode) |  | Done
IA-037 | 4 Soft copy | Validation | Line maths, GST maths, totals = invoice total, GSTIN format + check digit, duplicate (supplier + number), e-invoice QR agreement, place of supply |  | Done
IA-038 | 5 Hard copy | Camera scan (web + app) | Edge detection, crop, de-skew, enhance (colour / grey / B&W), corner adjust, multi-page, blur warning, small JPEGs |  | Done
IA-039 | 5 Hard copy | OCR + AI for printed and handwritten bills (English, Hindi, Marathi) | AI reader handles handwriting and Hindi/Marathi; local OCR English only | Code on undefined; not switched on | Blocked | Hindi/Marathi and handwriting need the AI reader (IA-034)
IA-040 | 5 Hard copy | Per-field confidence, low confidence highlighted | Amber = not sure, red = must fix; confidence % next to the field |  | Done
IA-041 | 6 Review | Side-by-side review & correction screen | Original bill + editable table (phone: switch); edit any field, add/remove lines, change mapping, auto-save |  | Done
IA-042 | 6 Review | Nothing touches stock until Confirm | Captures hold drafts only |  | Done
IA-043 | 6 Review | Confirm in one DB transaction | Stock + cost + batches, purchase, supplier ledger, ITC record, mappings, files |  | Done
IA-044 | 6 Review | Post-confirmation correction | Reopen -> reversing + corrected entries in stock, books and ITC; never an overwrite |  | Done
IA-045 | 6 Review | Audit trail | acc_change_log: who, when, old value, new value, reason; shown on the bill |  | Done
IA-046 | 6 Review | Corrections feed back into extraction | Supplier-specific product + unit mappings used first on the next bill |  | Done
IA-047 | 7 Data & security | Seller DB tables scoped by shop_id | 24 tables, ownership map; every API checks the shop; isolation tested |  | Done
IA-048 | 7 Data & security | Encryption at rest | GST tokens (AES-256-GCM); uploaded bills encrypted when INTEGRATION_ENCRYPTION_KEY is set |  | Done | GST portal tokens: always encrypted (refused without a valid key). Stored bills: encrypted when INTEGRATION_ENCRYPTION_KEY is valid (IA-056); always served only through the access-checked route
IA-049 | 7 Data & security | Object storage with per-shop access control | S3-compatible bucket (ACCOUNTS_STORAGE=s3) or MEDIA_DIR / DB; served only via the access-checked route |  | In progress | Code done; bucket credentials not configured yet, so files are in the database / MEDIA_DIR
IA-050 | 7 Data & security | Background job queue + progress | inv_bill_captures queue with progress %, SKIP LOCKED, retry; cron safety net |  | Done | Owner to schedule /api/cron/bill-captures (optional safety net)
IA-051 | 7 Data & security | Real-time notification when ready | In-app (+ email) notification and live progress polling on the screen |  | Done
IA-052 | 7 Data & security | Slow networks / one screen | Compressed scans, upload progress, Tile Board one-screen hub, phone layouts |  | Done | Board and GST page were ~40 s on test.gokesari.com (database far from the web server); fixed in #172 — every module page ~4 s on test (Seller Central /shop ~8 s there)
IA-053 | UI | Theme 1 Tile Board hub (web + app) | /shop/accounts with 12 tiles, live counts, 4 headline figures, EN/HI/MR; Inventory tile 'Bills & GST' and Finance hub links |  | Done
IA-054 | Mobile | Android and iOS apps | WebView apps show the module on deploy (no store update); camera via photo picker; downloads via bridge |  | Done | Native share-intent is IA-031
IA-055 | QA | Testing on test.gokesari.com and gokesari.com | Unit, integration, E2E; staging functional run; production read-only checks |  | Done | Local: 149 module unit/integration + E2E 11/11; CI full suite 1,915 tests green on the release. test.gokesari.com: smoke 11/11, functional 26/27 + live order/cancel PASS (GST link blocked by IA-056). gokesari.com: read-only smoke 11/11 after release #179. See TESTING_REPORT.md
IA-056 | 7 Data & security | Encryption key on the servers | INTEGRATION_ENCRYPTION_KEY (base64, 32 bytes) set on test.gokesari.com and gokesari.com — needed for GST portal linking and for encrypting stored bills | Code on undefined; not switched on | Blocked | Owner added the variable on test and production (15 Oct), but the value is not base64 of 32 bytes: test.gokesari.com reports encryption not configured (/api/shops/{id}/integration → ready.encryption=false) and GST linking answers 500. Fix: set the value from `openssl rand -base64 32` (44 characters ending in '='), a different one per site, and redeploy. Nothing has been encrypted with the old values

## Blocked & owner actions
Feature | What is needed | Who
IA-022 | Licensed GSP live connection: Needs a GSP contract and API credentials chosen by the owner; until then the manual upload works on gokesari.com | Owner
IA-031 | Share straight into the native Android/iOS app: Needs a native share-intent module and an EAS store build tested on a device; share to the installed website or forward by email meanwhile | Owner
IA-032 | Forward by email: Code done and tested; needs an inbound mail provider + INBOUND_EMAIL_SECRET / INBOUND_EMAIL_DOMAIN on the server | Owner
IA-034 | AI document parsing: Code done; needs ANTHROPIC_API_KEY + INVOICE_EXTRACTION_PROVIDER=claude on the servers (owner decision: bills are sent to Anthropic for reading) | Owner
IA-039 | OCR + AI for printed and handwritten bills (English, Hindi, Marathi): Hindi/Marathi and handwriting need the AI reader (IA-034) | Owner
IA-049 | Object storage with per-shop access control: Code done; bucket credentials not configured yet, so files are in the database / MEDIA_DIR | Owner
IA-056 | Encryption key on the servers: Owner added the variable on test and production (15 Oct), but the value is not base64 of 32 bytes: test.gokesari.com reports encryption not configured (/api/shops/{id}/integration → ready.encryption=false) and GST linking answers 500. Fix: set the value from `openssl rand -base64 32` (44 characters ending in '='), a different one per site, and redeploy. Nothing has been encrypted with the old values | Owner