## Status 2026-10-13
Task | Feature | Built | Tests | Staging | Production | Blocker / next step
1 | Seller DB / Customer DB split | Tooling done: ownership map, migration + checksum report, cross-DB integrity, postgres_fdw, workflow | db-split 5/5, ownership 3/3; local run PASS (190 tables) | Not run — needs seller DB | Not run | BLOCKED: seller (gokesari_seller) test DB details + secrets TEST_SELLER_DATABASE_URL / TEST_CUSTOMER_DATABASE_URL
2 | Document upload + auto-read (file/camera, OCR, review, Verify & Approve) | Done | extract 21/21, uploads 16/16, browser flow PASS | Deployed; page OK; photo read hit 504 on Hostinger | Not released | PR #147 (25 s limit + type-the-details fallback + health check) → re-test
3 | FSSAI mandatory for food shops | Done (rule on) | integration: approval + profile gates PASS | Deployed (FSSAI card on food shop only) | Not released | —
4 | Compact footer | Done | E2E 16/16 | 16/16 PASS | Not released | —
5 | Logo / tagline styling | Done (web, Seller Central, sign-in, emails) | E2E + email-brand PASS | PASS (incl. sign-in email) | Not released | —
6 | Mobile apps | No native change needed (WebView) | — | Reaches apps with the site | — | No store release needed
Reg | Regression | — | 1,743 unit/integration; lifecycle E2E 21/21 local | Branding E2E only so far | — | Order lifecycle on staging next