## Defects & checks
ID | Area | Defect / check | Root cause (plain words) | Fix / action | Status | Test | Prod | PR / evidence | Decision needed
D1 | Udyam / FSSAI / Shop Act | Status message says the document can't be checked online "for your state" | Our verification vendor (Sandbox.co.in) never checks Udyam, FSSAI or Shop Act in any state; they always go to manual review. The text blamed the seller's state, which was wrong. | New text: "This document can't be checked online. Our team will review it." Wizard Shop Act notice drops "in your state". Upload path unchanged. | Verified on Test | Verified 06:56 UTC: wizard step 2 shows the new text for Udyam, FSSAI, Shop Act; MANUAL_REVIEW vendor_unsupported | Waits for release #302 (owner window) | #304
D2 | PAN (Sandbox) | Sandbox test PAN XXXPX1234A comes back "Under review" instead of a result | Sandbox's test server answers only a request whose body exactly matches its saved example. It returns HTTP 404 "Test environment: Request does not match any saved example" for our PAN request, although our body equals the example in Sandbox's published API spec. The saved example itself is only in the KYC Postman collection in the owner's Sandbox account. This is a test-environment limit, not a live-API defect. | #304 now logs Sandbox's answer (masked), which is how the cause was found. No change to the PAN request without seeing the saved example (a guess could break the live check). | Blocked | Run 2 06:54 UTC: MANUAL_REVIEW config_unexpected_response; log shows HTTP 404 "does not match any saved example" | Not tested (needs owner's real PAN) | #304 | Owner: open Sandbox's KYC Postman collection (or ask Sandbox support) for the exact saved "Search PAN Lite" request; or accept that PAN is proven on production with the owner's own PAN.
D3 | GSTIN (Sandbox) | Sandbox test GSTIN 33ABKCS2033B1ZW comes back "Under review" | Sandbox's test server answers 33ABKCS2033B1ZW with its "Provisional" sample record (log 06:55 UTC: status "Provisional"). Our rule sends a Provisional GSTIN to a person, so the result is "Under review" by design. Sandbox's other sample GSTINs fail the GST check character, so our form refuses them before any call. | The status word is now logged so the cause is visible. No rule change without a decision. | Blocked | Run 2 06:55 UTC: MANUAL_REVIEW source_status_unknown; status word Provisional | Not tested (needs owner's real GSTIN) | #304 | Should a Provisional GSTIN count as verified, or stay in manual review (current)?
D4 | Bank check (Cashfree Verification Suite) | Bank account check never runs on test | Keys are now set (CASHFREE_VERIFICATION_CLIENT_ID / _CLIENT_SECRET / _ENV, sandbox; 2FA mode IP whitelist). Cashfree answers HTTP 401 "authentication_failed: Invalid clientId and clientSecret combination": it does not accept the ID and secret as a pair on sandbox.cashfree.com/verification. That is a credentials refusal, not an IP-whitelist or signature refusal. | No code change. The bank check runs and records ERROR with Cashfree's reason; the account stays PENDING and the ₹1 check is offered. | Blocked | 06:56 UTC: Keys found; connection test 401 Invalid clientId and clientSecret combination; saved sample account → ERROR, ₹1 check offered | Not tested | — | Owner: re-copy the Verification Suite (Secure ID) sandbox Client ID and Secret as one pair from the Cashfree dashboard (not the payment-gateway App ID/Secret, not production keys). After that, if Cashfree refuses the IP, whitelist 93.127.208.167 or set CASHFREE_VERIFICATION_PUBLIC_KEY.
C1 | Logs | No full PAN/GSTIN/Udyam/FSSAI/Shop Act/bank number in logs or error messages | Audit of console calls and error messages in KYC, bank check, seller verification and wizard code: none print a full number. Cashfree's error message was stored as written. | Cashfree error message: digit runs of 5+ masked. Sandbox diagnostics: digit words masked. | Fixed | Code audit + unit tests | Same code | #304
C2 | Timeouts and retries | Retry only transient errors; timeout keeps document PENDING with a reason | Checked src/server/kyc/http.ts: retries timeout, network, 408, 429, 5xx only; 401/403/406 not retried (config error). A timeout returns PENDING with vendor_timeout ("The government service is slow right now…"). | No change needed. | Verified on Test | Code review + unit tests | Same code | —
C3 | Consent | Consent checkbox gates every verification call | Server refuses PAN/GSTIN/step-2 checks without consent (shop-registration-draft.ts 357/482, wizard 592); seller panel records the consent version. | No change needed. | Verified on Test | Integration tests + live: step-2 call without consent → 422 | Same code | —
C4 | Encryption and masking | Numbers encrypted at rest; only masked values in the UI | PAN encrypted (PAN_ENCRYPTION_KEY), last four kept; wizard API returns numberMasked only (seen on test: XXXXXX234A, 33XXXXXXXXXX1ZW). | No change needed. No key rotated. | Verified on Test | API response on test shows masked values only | Same code | —
C5 | Mobile apps | Android and iOS apps carry the changed messages | Both apps show the website in a WebView (mobile/README.md); no message is built into the app. | No app build needed; text ships with the web deploy. | Fixed | Not run in the app | Not run in the app | —

## Summary
Item | Value
Date | 31 Oct 2026
PR | #304 merged into staging 06:47 UTC (05b2e447); test.gokesari.com built 06:51 UTC
Verified on Test | D1 message; logs, retries, consent, encryption
Blocked: PAN | Sandbox test server: "Request does not match any saved example" (404)
Blocked: GSTIN | Sandbox test GSTIN is Provisional → manual review by design; decision needed
Blocked: bank | Cashfree 401 Invalid clientId and clientSecret combination; re-copy the Verification Suite sandbox key pair
Prod | Copy fix rides release #302 (owner window); real-document tests need the owner's documents
Test data left on staging | gk-shop: PAN_ONLY draft with Udyam/FSSAI/Shop Act checks; gk-admin: GSTIN draft; gk-lc14 customer: bank account ••••1191 (Cashfree sample, PENDING)