## Test runs
ID | Environment | Check | Input type | Expected | Actual | Result | Response time | Remaining gap
T1 | Test | Bank check status card (Admin → Bank accounts) | Admin session, GET /api/admin/bank-account-check | "Keys found" once the owner's Verification Suite keys are set | Run 1 05:43: Keys not found. Run 2 06:56: Keys found (CASHFREE_VERIFICATION_CLIENT_ID/_CLIENT_SECRET), env sandbox, 2FA IP whitelist | PASS | 0.33 s
T2 | Test | Bank check connection test (finance) | Admin session, POST /api/admin/bank-account-check/test; Cashfree sample account 026291800001191 / YESB0000262 | Cashfree answers VALID for its sample account | Run 2 06:56: Cashfree HTTP 401 "authentication_failed: Invalid clientId and clientSecret combination"; outbound IP 93.127.208.167 | FAIL | 2.98 s | Owner to re-copy the Verification Suite sandbox key pair
T3 | Test | Save a test bank account: verified/failed with a reason; ₹1 check offered when the check can't run | Customer test account, PUT /api/bank-account with Cashfree sample 026291800001191 / YESB0000262, John Doe | VERIFIED or FAILED with Cashfree's reason; ₹1 check offered on NOT_CONFIGURED/ERROR | Saved; bank check ERROR (401 reason recorded for finance); account PENDING, shown ••••1191; ₹1 check still offered | PASS | 3.42 s | Verified/failed outcomes need working keys
T4 | Test | Auth failure diagnosis (IP whitelist vs public key) | — | Report which 2FA setting is missing | 401 "Invalid clientId and clientSecret combination" = key pair refused. Not an IP-whitelist or public-key refusal; that can only be judged once the pair is accepted | PASS | — | Re-run after the key pair is fixed
T5 | Test | PAN check, Sandbox test PAN (before fix) | Wizard step 1, no GSTIN: POST /api/shops/registration-draft/pan, PAN XXXPX1234A, consent + declaration | VERIFIED with name from the record | MANUAL_REVIEW config_unexpected_response; log 05:43:17 UTC "Sandbox PAN response had no data." Request body equals Sandbox's example; UI shows XXXXXX234A only | FAIL | 3.53 s | Re-run after #304 deploy to capture Sandbox's actual answer
T6 | Test | GSTIN check, Sandbox test GSTIN (before fix) | Wizard step 1: POST /api/shops/registration-draft/gstin, GSTIN 33ABKCS2033B1ZW, consent | VERIFIED with legal name and address filled in | MANUAL_REVIEW source_status_unknown; prefill empty; UI shows 33XXXXXXXXXX1ZW only | FAIL | 3.85 s | Re-run after #304 deploy; status word decides whether this is the Provisional rule
T5b | Test | PAN check, Sandbox test PAN (after #304) | Same as T5, 06:54 UTC | VERIFIED, or Sandbox's reason recorded | MANUAL_REVIEW config_unexpected_response; log: HTTP 404 "Test environment: Request does not match any saved example" | FAIL | 4.44 s | Sandbox test-environment limit: needs the saved example from the owner's Sandbox Postman collection
T6b | Test | GSTIN check, Sandbox test GSTIN (after #304) | Same as T6, 06:55 UTC; also 29AFSPB9500E1ZY, 36AEOFS9999J1ZI, 07CQZCD1111I4Z7 | A real verified / not-verified result | 33ABKCS2033B1ZW → MANUAL_REVIEW, status word "Provisional" (Sandbox's sample). The other three are refused by our form (422, wrong GST check character) before any call | PARTIAL | 2.89 s | Decision on Provisional; no Active sample GSTIN with a valid check character
T7 | Test | Udyam / FSSAI / Shop Act message | Wizard step 2, POST /api/shops/registration-draft/documents: Udyam, FSSAI, Shop Act numbers, consent; plus one call without consent | "can't be checked online. Our team will review it", no mention of state; manual review; upload unchanged | All three MANUAL_REVIEW vendor_unsupported; text "This number can't be checked online. You can carry on — our team will review it." / Shop Act: "Shop Act numbers can't be checked online. You can carry on — after registration, upload your Shop Act certificate…"; masked numbers only. Without consent → 422 | PASS | 2.4–2.6 s | Seller panel (existing shops) text checked in code/tests, not opened in the browser
T8 | Test (local + CI) | Both database layouts | Unit + verification integration suites | All pass on one database and on the split | Local 154/154 one DB, 202/202 split; CI test and test-split pass | PASS | CI ~45 min
T9 | Prod | Copy fix on gokesari.com | — | New message live | Not deployed: rides with release #302 (owner window) | NOT RUN | — | Owner's release window
T10 | Prod | PAN and GSTIN with the owner's real documents | — | VERIFIED or not verified from the live record | Not run: no real documents supplied; test numbers never used on prod | NOT RUN | — | Owner's own PAN/GSTIN and bank account
T11 | Android / iOS | Onboarding journey in the apps | — | New text shows in both apps | Apps are a WebView of the site: no build needed. Not run in the apps | NOT RUN | — | Run in the apps after the web deploy