## Summary
GoKesari - Shop-based Product Master & Inventory spec vs. built code (18 Oct 2026)
Spec: "Gokesari Marketplace - Shop-Based Product Master, Inventory, MRP, Barcode & Stock Management" (sections 1-44). Compared against GoKesari main @c96cd04 (live on gokesari.com) by reading the schema, services, API routes, screens and tests. Status: DONE = built and live; PARTIAL = built in part (see "Missing"); NOT BUILT = no code yet. Change a status with the dropdown - counts are formulas.
1. Features & functions by status
Status | Features / functions | % of total
DONE
PARTIAL
NOT BUILT
Total
2. By area
Area | DONE | PARTIAL | NOT BUILT | Total | % done
Marketplace model
Product Master
Admin
Data ownership
Migration
Shop Inventory
Barcode
Alerts
Customer
Bulk import
Inventory history
Orders
External data
Supplier / restock (future)
Permissions
Security
Scalability
AI
Total
3. Workflow steps by status
Status | Steps
DONE
PARTIAL
NOT BUILT
4. Mandatory acceptance tests (§43)
Coverage | Tests
COVERED
PARTLY
NOT COVERED
5. Headlines
The marketplace model is intact: shops stay the seller, every inventory row belongs to one shop, the master is shared, MRP is master-level and shop prices are per shop. Server-side shop isolation is in place on every inventory route.
Built and live: per-shop stock, low-stock / reorder thresholds, de-duplicated stock alerts (dashboard + bell), out-of-stock per shop, inventory dashboard with value, offers, atomic no-oversell checkout, MRP governance with a correction queue, bulk Excel / CSV shop upload (15 Oct).
Not built: barcode scanning (Phase 3), per-GTIN external lookup / live GS1 (Phase 5 - waits on the GS1 agreement), purchase orders, AI product recognition.
Gaps to fix first: controlled Request New Product, restock on customer returns, shop flows writing master MRP, admin edit screens for master fields / brands / subcategories, a Reorder List page, richer Add Product form.
Tests: 6 of the 15 acceptance tests fully covered, 8 partly, 1 not (concurrent last-unit oversell).

## Features & Functions
ID | Spec section | Area | Feature / function | Status | What exists today | Missing / gap | Evidence (code)
MP-01 | §1, §5, §44 | Marketplace model | GoKesari stays a multi-shop marketplace; shop is the seller, GoKesari is not | DONE | Carts split into one order per shop; orders.shop_id; invoice names the shop as supplier ("Sold by"); About page says GoKesari is not the seller of record | - | services/invoices.ts; app/invoices/[id]/page.tsx; tests/integration/checkout.test.ts
MP-02 | §5, §6 | Marketplace model | Every inventory record belongs to one registered shop; shop → shop product → product master | DONE | shop_products(shop_id, product_id) NOT NULL FKs, unique per shop + product; master never owns stock | - | schema.ts:1519-1621
PM-01 | §3, §7 | Product Master | Central Product Master as a shared catalogue that shops reference | DONE | public.products shared by all shops via shop_products.product_id; separate PMD data platform (pmd.*) feeds it through pmd.catalogue_link | - | schema.ts:1314-1443; drizzle/0015
PM-02 | §7 | Product Master | Identity: productId, productName, shortName, internalSKU, GTIN, EAN, UPC, barcode | PARTIAL | id, code (P00001 = internal SKU), name, gtin (EAN/UPC stored in gtin), barcode (non-GTIN) | shortName; separate EAN / UPC columns (pmd.product_master has them) | schema.ts:1317-1356
PM-03 | §8 | Product Master | Brand Master table (brandId, brandName, brandCode, description, logoUrl, status, dates); products reference brand | PARTIAL | brands table (name, slug, description, logo_url, is_active, timestamps); products.brand_id FK; create/update service with audit | brand_code; status is a boolean; NO admin screen or API calls the brand create/update service | schema.ts:1215-1234; services/brands.ts
PM-04 | §9 | Product Master | Category + subcategory tables; product references categoryId and subcategoryId | PARTIAL | product_categories + product_subcategories; products.category_id / subcategory_id; Category Master page /product-categories with CRUD API | No subcategory create / edit service, API or screen; product create still takes the old free-text sub-category | schema.ts:1246-1308; app/product-categories
PM-05 | §7 | Product Master | Packaging: pack size, pack unit, net quantity, quantity unit, variant, flavour, size, colour | PARTIAL | net_quantity, net_quantity_unit, unit, unit_size_milli, variant; extras kept in product_attributes (jsonb) | pack size / pack unit, flavour, size, colour columns | schema.ts:1358, 1390-1396
PM-06 | §7 | Product Master | Manufacturer name, address, country of origin | DONE | manufacturer_name, manufacturer_address, country_of_origin on products | No admin edit screen (see PM-13) | schema.ts:1387-1389
PM-07 | §7 | Product Master | Tax: HSN, GST rate, tax category | PARTIAL | hsn_code, gst_rate_bp (checked); shop-level HSN / GST / cess overrides on shop_products | taxCategory; cess on the master | schema.ts:1376-1377, 1548-1550
PM-08 | §7, §10 | Product Master | MRP at master level: MRP, currency, source, effective date, verification status, last updated; MRP history | PARTIAL | mrp_paise, mrp_source, mrp_effective_from, mrp_verification_status, mrp_updated_at; product_mrp_history table | currency column (INR assumed) | schema.ts:1365-1371, 1450-1468
PM-09 | §11, §36 | Product Master | Migration: unknown MRP = NULL + PENDING; never copy selling price into MRP | PARTIAL | MRP added nullable, no backfill; no migration copies price into MRP | Default verification status is UNVERIFIED, not PENDING | drizzle/0014:70-74
PM-10 | §12, §32 | Product Master | Shop selling price never overwrites master MRP; shop cannot change verified MRP | PARTIAL | Only ADMIN / OPERATOR can set master MRP (history + audit); shops raise MRP corrections; price above MRP refused; bulk import writes MRP to the listing only | Leak: purchase-bill flow writes MRP, barcode and HSN onto a NEW master product created from a shop bill, with no MRP history row | services/product-master.ts:129-187; mrp-governance.ts; accounts/purchases.ts:158-161
PM-11 | §20 | Product Master | Multiple images: product_images (imageId, productId, url, isPrimary, displayOrder, imageType, createdAt) | PARTIAL | product_images with is_primary, sort_order, alt_text, per-listing images, moderation, one-primary index; multi-image API | imageType column | schema.ts:1478-1513; services/product-images.ts
PM-12 | §37 | Product Master | Same GTIN → one Product Master (no duplicates) | PARTIAL | Unique index on gtin; bulk import and PMD promote match / adopt by GTIN | GTIN not stored in one canonical form (EAN-13 vs GTIN-14 can coexist); duplicate-candidate function never called; manual create has no GTIN check | schema.ts:1427-1429; pmd/catalogue-bridge.ts
PM-13 | §33 | Admin | Admin manages products, brands, categories, subcategories, GTIN, barcode, MRP, HSN, GST, manufacturer, images | PARTIAL | Admin MRP, product-master (PMD), image moderation, product import, shop products, product approvals, category master | No admin product edit screen for GTIN / barcode / brand / HSN / GST / manufacturer / pack; no brand or subcategory admin | src/app/admin/*
PM-14 | §33 | Admin | Verification queues: MRP change requests, new product requests, duplicates, external data sync | PARTIAL | MRP correction queue; new-product approval queue; PMD match / duplicate review; image moderation | No duplicate queue for the live catalogue; no screen for PMD runs / sources (scripts only) | app/admin/mrp; admin/console/product-approvals
PM-15 | §35 | Product Master | Product audit log | DONE | audit_logs records product.created / approved / mrp_changed / identity_updated, brand.*, category.*, image.*; plus MRP history and pmd.product_change_log | No dedicated product_audit_log table (generic log used) | services/audit.ts
PM-16 | §34 | Data ownership | Master fields only editable by admin; shop fields only by the shop - enforced in backend | PARTIAL | Published masters protected (category, MRP, identity = staff only); price, stock, thresholds, offers on shop_products / shop_offers | Shops still write master fields when they CREATE a product (manual create, bulk import, purchase bill) - rows are pending approval but the data is shop-written | services/catalogue.ts:419-436; product-import.ts:916-937
PM-17 | §36 | Migration | Existing shop products mapped to shop + master; price and stock kept | DONE | shop_products has referenced products since the first migration; price and stock stay on shop_products; recategorisation script with dry run and restore | - | drizzle/0000; scripts/categorise-products.ts
SI-01 | §13 | Shop Inventory | Shop inventory fields: price, stock, low-stock threshold, reorder level / qty, min / max order qty, discount type / value, final price, availability, offer, delivery available | PARTIAL | shop_products: online / offline price, online / offline stock, low_stock_threshold, reorder_level, reorder_quantity, min / max order qty, is_available | discount, final price, offer are in shop_offers and worked out at runtime (no columns); availability is a boolean, not an OUT_OF_STOCK value; no deliveryAvailable | schema.ts:1519-1621, 6203-6239
SI-02 | §14 | Shop Inventory | Add Product by searching the Product Master, then price, stock, threshold, reorder, discount → Add to my shop | PARTIAL | Shop Products → Add New Product → Add Existing Product: search, enter price, add | Results show only name, category, code, unit (no brand, subcategory, pack, GTIN, MRP, image); search does not match GTIN; no stock / threshold / reorder / discount in the form - stock starts at 0 | components/add-product-panel.tsx; api/shops/[id]/catalogue-search
SI-03 | §15 | Barcode | Scan barcode (camera / scanner) → GTIN → Product Master → select product | NOT BUILT | GTIN lookup function exists (findProductByGtin) but nothing calls it from a shop screen | Camera barcode scanner, scanner input, shop-side GTIN lookup route; mobile app has no barcode package | services/product-master.ts:58; mobile/package.json
SI-04 | §16 | Barcode | Unknown barcode → external lookup → controlled "Request New Product" (no unverified duplicates) | PARTIAL | Shop-created products go to PENDING_APPROVAL with an admin queue; similar-name warning | No on-demand external lookup; no request record - the product is sellable in that shop at once while unverified; "Create anyway" bypasses the duplicate warning | components/add-product-panel.tsx:262-341; product-approval-queue
SI-05 | §21 | Shop Inventory | Low stock calculated per shop inventory against the shop's threshold | DONE | stockStatus(): listing threshold → product default → shop default | - | services/inventory-alerts.ts:41-98
SI-06 | §22 | Shop Inventory | Reorder settings per shop and "Reorder recommended" display | DONE | Thresholds editable per listing and as shop defaults; reorder badge + "order N" hint; reorder alert with suggested qty | Min / max order qty: API only, not enforced in the cart | api/shop-products/[id]/stock-settings; shop-inventory-manager.tsx
SI-07 | §23 | Alerts | Low-stock alerts per shop: dashboard, bell, inventory page (email / SMS / WhatsApp later) | DONE | stock_alerts (OPEN / ACK / RESOLVED, de-duplicated); in-app notification + bell; dashboard Low-stock tile; alerts on inventory page | Email off by default (no STOCK_LOW template); SMS / WhatsApp waiting on provider (D2) | inventory-alerts.ts:109-195; shop-dashboard.tsx
SI-08 | §24 | Shop Inventory | Stock 0 → out of stock for that shop only; other shops stay available | DONE | Zero stock sets that listing unavailable; product page lists every shop with buyable / not; comparison drops out-of-stock shops | Boolean flag rather than an OUT_OF_STOCK value | inventory-alerts.ts:186-194; app/products/[id]/page.tsx
SI-09 | §29 | Shop Inventory | Inventory Dashboard: total, in stock, low, out, reorder required, inventory value | DONE | All six figures on /shop/inventory; cost-based value on /shop/accounts/stock | Dashboard value is at selling price (cost value is on the accounts page) | inventory-alerts.ts:347-393; app/shop/inventory
SI-10 | §30 | Shop Inventory | Reorder List (product, current stock, reorder level, reorder qty) - own shop only | PARTIAL | Reorder flags and columns in the inventory table; "Need reorder" count; Reorder badge on accounts stock page | No dedicated Reorder List page or reorder filter | shop-inventory-manager.tsx:247-329; app/shop/accounts/stock
SI-11 | §31 | Shop Inventory | Inventory table: product, MRP, selling price, stock, threshold, status | PARTIAL | Product, unit, available, price (editable), reserved, on hand, low at, reorder at, status | MRP column | shop-inventory-manager.tsx:238-251
SI-12 | §12, §32 | Shop Inventory | Shop discounts / offers per product | DONE | /shop/offers: % or flat, per product or category, with dates; applied in cart, checkout, comparison | Behind the shopOffers setting | services/shop-offers.ts
CU-01 | §25 | Customer | Customer search shows each shop with its price and availability (Available / Low stock / Out of stock) | PARTIAL | Product page lists every shop with price, cheapest highlighted, "Not available online" badge; compare page | Customers never see "Low stock"; search results are listings, not a shops-per-product view | app/products/[id]/page.tsx; services/price-comparison.ts
CU-02 | §25, §27 | Customer | Customer buys from the individual shop | DONE | Order belongs to the shop; invoice "Sold by" the shop | - | services/invoices.ts
IM-01 | §18 | Bulk import | Admin bulk import of the Product Master from Excel (GTIN, name, brand, category, subcategory, pack, MRP, HSN, GST, manufacturer, origin, image URL) | PARTIAL | Bulk upload (xlsx / csv, 5,000 rows) with those fields - admins use it through a shop picker; PMD JSON import API; CLI feed import | No admin Excel upload straight into the master without a shop; no subcategory column; no separate net qty / unit columns | product-import/fields.ts; api/product-master/products/import
IM-02 | §18 | Bulk import | Validation (duplicates, missing GTIN, invalid MRP / category / brand / tax) + error report | PARTIAL | Duplicate SKU / file detection; bad category → General + warning; bad brand / HSN / GST → warning; price > MRP refused; result report XLSX / CSV; PMD has proper error codes | Rows are never rejected (warnings only, by design); missing GTIN not flagged; GST not checked against slabs | product-import/normalise.ts; pmd/normalize
IM-03 | §19 | Bulk import | Shop inventory import (GTIN, stock, price, threshold, reorder level / qty) for the logged-in shop only | PARTIAL | Matches GTIN → listing; sets stock (Set / Add) and price; server-side check - owner only own shop (403 / 404); tested | Threshold, reorder level and reorder qty cannot be imported; shop staff not covered (owner only) | services/product-import.ts:102-126; tests/integration/product-import.test.ts
IT-01 | §26 | Inventory history | Inventory transactions per shop (type, qty change, previous, new, order / reference, reason, by, at) | PARTIAL | Two ledgers: inventory_movements (previous / new, reason, order, user) and inv_stock_ledger (typed movement, cost) kept in step by DB triggers; drift check | Neither has every field (movements: no shopId / typed type; ledger: no previous / new); link between them is heuristic; previous qty can be stale under concurrent orders | schema.ts:1683-1709, 6993-7029; drizzle/0076, 0078
IT-02 | §26 | Inventory history | Types: opening, customer order, manual adjustment, stock received, return | PARTIAL | OPENING, SALE, ADJUSTMENT, PURCHASE (bill), SALE_RETURN (cancellation), WRITE_OFF, REVERSAL | Manual "stock received" logged as ADJUSTMENT; customer returns not recorded; PURCHASE_RETURN unused | lib/accounts/constants.ts
OR-01 | §27 | Orders | Customer order deducts only that shop's stock | DONE | Stock taken at checkout per order line (shop listing); also substitutes and subscriptions | - | services/orders.ts:565-572
OR-02 | §28 | Orders | Prevent overselling; stock never negative (locking) | DONE | Conditional UPDATE (stock >= qty) inside the checkout transaction; CHECK constraint stock >= 0; row locks on restock / import | No automated test of two orders racing for the last unit | catalogue.ts:1291-1325; schema.ts:1606-1608
OR-03 | §26 | Orders | Returns / cancellations put stock back | PARTIAL | Cancellations (customer, shop decline, timeout) restock with a row lock | Customer returns AFTER delivery do not restock shop_products or the ledger | orders.ts:1015-1068; returns.ts:688-698
OR-04 | §42 Ph 6 | Orders | Stock reservation (hold at cart / checkout / pending payment) | PARTIAL | Atomic take at order placement, released on cancel; "reserved" shown from open orders | No reservation / hold table or time-limited hold | catalogue.ts:1297-1395
EX-01 | §17 | External data | Provider abstraction ProductDataProvider.lookupProductByGTIN(gtin); not hard-coded; credentials server-side | PARTIAL | Batch SourceAdapter + adapter registry; engine source-agnostic; credentials named by env var | No per-GTIN on-demand lookup interface; credential env vars not read by any code | pmd/sources/adapter.ts, registry.ts
EX-02 | §16, §38 | External data | GS1 India DataKart / Verified by GS1 integration, sync, MRP verification | PARTIAL | gs1_india source defined (BLOCKED_NEEDS_AGREEMENT) with mapping template; CSV feed adapter; PMD external-data tables; MRP from GS1 / brand marked PENDING_VERIFICATION on promote | No live DataKart / GS1 API client; no background sync (CLI only, pmd.job unused); waits on GS1 agreement | pmd/sources/registry.ts; catalogue-bridge.ts
EX-03 | §38 | External data | External data → Product Master → shops (never GoKesari as seller) | DONE | PMD → admin promote (audited) → products → shop_products; same-GTIN product adopted | Promotion is manual, one product at a time | pmd/catalogue-bridge.ts
SU-01 | §39 | Supplier / restock (future) | Reorder → supplier → purchase order → goods received → stock up | PARTIAL | Supplier master (acc_parties); purchase bills add stock at cost with batches; bill photo / QR capture; supplier item maps | No purchase order; no separate goods-received note; reorder list does not create a PO | schema.ts:7077, 7171; accounts/purchases.ts
PE-01 | §32 | Permissions | Shop owner can: search master, add, scan, set price / stock / threshold / reorder, offers, adjust / view own inventory, alerts, reorder list | PARTIAL | All except barcode scan and a dedicated reorder list | Barcode scan; reorder list | api/shops/[id]/*; api/shop-products/[id]/*
PE-02 | §32 | Permissions | Shop owner cannot: change other shops' stock / prices, verified MRP, delete master records | DONE | requireShopAccess on every shop route; listing IDs re-checked; MRP write = admin / operator only; no master delete route | No route-level test that a shop owner gets 403 on /api/mrp | authz/guards.ts:87-106; permissions.ts
SE-01 | §40 | Security | Server-side check on every shop inventory API: user → shop → inventory belongs to shop | DONE | All inventory, listing, price, stock, import, media, offers routes guarded (route or service level); no unguarded route found | - | authz/guards.ts; api/shops/[id]/*
AD-01 | §33 | Admin | Admin manages shops, listings, shop inventory, status, availability | PARTIAL | Approve / reject / suspend shops; admin listing editor; stock / availability edits; product stock defaults | No admin per-shop inventory dashboard or alerts view | app/admin/shops
SC-01 | §41 | Scalability | Indexes, pagination, batch imports, background sync, fast GTIN lookup, transactions | PARTIAL | GTIN indexes; cursor / offset pagination on catalogue and PMD; batched imports with resume; partitioned price history | Shop product list and stock summary not paginated; background work not a durable queue; no GS1 sync job | catalogue.ts; accounts/stock.ts:251-265
AI-01 | §42 Ph 7 | AI | Product image recognition, OCR, matching, AI categorisation, AI duplicate detection | PARTIAL | Keyword categoriser (rule-based); deterministic PMD matcher (GTIN / MPN / trigram); AI + OCR reading of SUPPLIER BILLS and KYC documents | No product-image recognition, product-label OCR, AI categorisation or AI duplicate detection | services/product-categorisation.ts; pmd/match/engine.ts; accounts/capture

## Workflow Trees
Flow / step | Level | Workflow tree | Status | Note
WF-A | 1 | Shop owner adds a product by searching the Product Master
WF-A.1 | 2 | Open My Shop → Inventory → Add Product | DONE | /shop/manage/products → Add New Product → Add Existing Product
WF-A.2 | 2 | Search the Product Master | PARTIAL | Approved products in the shop's categories; name / code / brand only - not GTIN
WF-A.3 | 2 | Show name, brand, category, subcategory, pack, GTIN, MRP, image | PARTIAL | Shows name, category, code, unit only
WF-A.4 | 2 | Enter selling price | DONE | One price used for online and in-shop
WF-A.5 | 2 | Enter stock, threshold, reorder level / qty, discount | NOT BUILT | Set later on other screens; stock starts at 0
WF-A.6 | 2 | Add to My Shop (server checks MRP, category, duplicate) | DONE | POST /api/shops/[id]/products
WF-B | 1 | Shop owner adds a product by barcode scan
WF-B.1 | 2 | Scan barcode with camera / scanner | NOT BUILT | No scanner in web or app
WF-B.2 | 2 | Look up GTIN in the Product Master | NOT BUILT | GTIN lookup is staff-only (PMD_VIEW)
WF-B.3 | 2 | Found → select → add to own shop inventory | NOT BUILT
WF-B.4 | 2 | Not found → external provider lookup (GS1 DataKart) | NOT BUILT | No live provider; GS1 agreement pending
WF-B.5 | 2 | Still not found → controlled Request New Product | PARTIAL | Creates a pending product that the shop can sell at once; duplicate warning can be skipped
WF-C | 1 | Low stock → alert → reorder
WF-C.1 | 2 | Every stock change re-checks alerts in the same transaction | DONE | Orders, restock, bills, imports, edits
WF-C.2 | 2 | Compare with the shop's own threshold | DONE | Listing → product default → shop default
WF-C.3 | 2 | Open / resolve the shop's stock alert (no duplicates) | DONE | stock_alerts
WF-C.4 | 2 | Notify: dashboard, bell, inventory page | DONE | In-app
WF-C.5 | 2 | Notify: email / SMS / WhatsApp | PARTIAL | Email opt-in only; SMS / WhatsApp wait on D2 vendor
WF-C.6 | 2 | Reorder recommended flag + suggested quantity | DONE
WF-C.7 | 2 | Shop Reorder List | PARTIAL | Data in the inventory table; no reorder-only page / filter
WF-D | 1 | Customer buys from a shop → that shop's stock goes down
WF-D.1 | 2 | Customer searches a product | DONE
WF-D.2 | 2 | Sees each shop with price and availability | PARTIAL | No "Low stock" label for customers
WF-D.3 | 2 | Cart split per shop; order belongs to the shop | DONE
WF-D.4 | 2 | Stock taken from that shop only, atomically (no overselling) | DONE | Conditional update + CHECK >= 0
WF-D.5 | 2 | Zero stock → that shop's listing out of stock; others stay available | DONE
WF-D.6 | 2 | Cancellation puts stock back | DONE
WF-D.7 | 2 | Customer return after delivery puts stock back | NOT BUILT | Credit note only; stock not restored
WF-E | 1 | Shop bulk inventory upload (Excel / CSV)
WF-E.1 | 2 | Upload file for the logged-in shop only (server check) | DONE | 403 / 404 for another shop
WF-E.2 | 2 | Match rows by GTIN / SKU / name to the master | DONE
WF-E.3 | 2 | Set / add stock and selling price; ledger rows written | DONE
WF-E.4 | 2 | Import threshold, reorder level, reorder qty | NOT BUILT
WF-E.5 | 2 | Validation, warnings and downloadable result report | PARTIAL | Warnings only - rows never rejected; missing GTIN not flagged
WF-F | 1 | Product Master import and external data
WF-F.1 | 2 | Admin uploads Product Master Excel (no shop involved) | PARTIAL | Only via shop picker, or PMD JSON / CLI
WF-F.2 | 2 | Validate and report errors | PARTIAL | PMD has error codes; shop import warns only
WF-F.3 | 2 | Duplicate detection by GTIN | PARTIAL | Unique GTIN; no canonical GTIN-14 form
WF-F.4 | 2 | External feed (GS1 / brand) → PMD → admin promote → catalogue | PARTIAL | File feeds only; GS1 blocked on agreement; manual promote
WF-F.5 | 2 | Background synchronisation | NOT BUILT | CLI only
WF-G | 1 | MRP governance
WF-G.1 | 2 | MRP held on the master with source, date, status, history | DONE
WF-G.2 | 2 | Shop price may not exceed MRP | DONE
WF-G.3 | 2 | Shop disputes MRP → correction queue → admin decides | DONE | /admin/mrp
WF-G.4 | 2 | Shop cannot write master MRP | PARTIAL | Purchase-bill flow can set MRP on a NEW product
WF-H | 1 | Supplier restocking (future)
WF-H.1 | 2 | Reorder list → purchase order | NOT BUILT
WF-H.2 | 2 | Supplier master | DONE | acc_parties
WF-H.3 | 2 | Goods received / purchase bill → stock up at cost | PARTIAL | Purchase bill doubles as goods receipt; no GRN

## Acceptance Tests
Test | Spec test (§43) | Coverage | Existing automated test (file :: name) | Gap
T1 | Marketplace preservation - two shops stay independent sellers | COVERED | checkout.test.ts :: splits a cross-shop cart; product-master-inventory.test.ts :: two shops stock the same master product
T2 | Same product → one Product Master | COVERED | product-master-inventory.test.ts (asserts 1 product row); pmd-review-bridge.test.ts
T3 | Independent price (95 / 90) | COVERED | product-master-inventory.test.ts; shop-inventory-fill.test.ts
T4 | Independent stock (A 20→10, B stays 5) | COVERED | product-master-inventory.test.ts (A restocked, B unchanged)
T5 | Low-stock alert only for shop B | PARTLY | product-master-inventory.test.ts :: raises LOW_STOCK alert | Single shop; does not check shop A gets no alert
T6 | Out of stock at B, A still available | PARTLY | product-master-inventory.test.ts :: OUT_OF_STOCK marks line unavailable | Single shop
T7 | Customer search shows shops with price / availability | PARTLY | price-comparison.test.ts | Prices only; "Low stock" not shown to customers
T8 | Barcode scan finds master and adds to shop A | PARTLY | product-master-inventory.test.ts :: finds master by GTIN; product-import.test.ts :: barcode links shop | Scan-and-add not built
T9 | MRP stays 100 with shop prices 95 / 90 | COVERED | product-master-inventory.test.ts
T10 | Shop owner cannot change MRP | COVERED | product-master-inventory.test.ts :: refuses a shop owner writing master MRP | Service level; no /api/mrp route test
T11 | Bulk inventory upload changes only shop A | PARTLY | excel-goods-upload.test.ts; product-import.test.ts :: cannot import into another shop | Cross-shop stock not asserted
T12 | Shop A cannot modify shop B inventory | PARTLY | shop-inventory-fill.test.ts (403 on prices); inventory-accounting.test.ts | No test on stock routes (shop-products, stock-settings, inventory)
T13 | Order from shop A decreases only shop A stock | PARTLY | checkout.test.ts :: decrements stock | Other shop's stock not asserted
T14 | Concurrent orders cannot oversell | NOT COVERED | - | Protected in code (conditional update) but no last-unit race test
T15 | Below reorder level → in that shop's Reorder List | PARTLY | product-master-inventory.test.ts :: reorder level separate signal | No Reorder List feature to test

## Phases
Phase | Name | Spec scope | Status | Comment | Feature IDs
Phase 1 | Product catalogue | Product Master, brands, categories, subcategories, GTIN, pack, manufacturer, origin, HSN, GST, MRP, MRP history, images | PARTIAL | Tables and data built; admin edit screens for master fields, brands and subcategories missing; a few columns missing | PM-01, PM-02, PM-03, PM-04, PM-05, PM-06, PM-07, PM-08, PM-11
Phase 2 | Shop inventory | Shop → master link, independent inventory, price, stock, thresholds, reorder, dashboard, reorder list, status, history | PARTIAL | Engine, alerts and dashboard done; reorder list page, MRP column and add-product form fields missing | SI-01, SI-05, SI-06, SI-07, SI-08, SI-09, SI-10, SI-11, IT-01
Phase 3 | Barcode | Mobile scanning, scanner support, GTIN lookup, master lookup | NOT BUILT | Only a back-end GTIN lookup function exists | SI-03, SI-04
Phase 4 | Bulk import | Master import, shop inventory import, validation, error reports, duplicates | PARTIAL | Shop bulk upload live on gokesari.com (15 Oct); master-only Excel import, thresholds and hard validation missing | IM-01, IM-02, IM-03
Phase 5 | External product data | Provider abstraction, GS1 / DataKart, lookup, sync, MRP verification | PARTIAL | Batch adapters built; per-GTIN lookup, live GS1 and sync missing; GS1 agreement pending | EX-01, EX-02, EX-03
Phase 6 | Advanced inventory | Reservation, order deduction, purchase / restock, supplier, purchase orders | PARTIAL | Order deduction and purchase bills done; reservation holds, purchase orders and GRN missing | OR-01, OR-02, OR-03, OR-04, SU-01
Phase 7 | AI | Image recognition, OCR, matching, AI categorisation, duplicates | PARTIAL | AI used for bills and KYC documents only | AI-01

## Gap List
# | Priority | What to build / fix | Spec IDs
1 | High | Barcode scanning for shop owners (camera + scanner) with GTIN → master lookup and add-to-shop | SI-03, WF-B, T8
2 | High | Controlled Request New Product: request record, not sellable until approved, no "Create anyway" bypass | SI-04, PM-12
3 | High | Customer returns after delivery must restock the shop (shop_products + ledger) | OR-03, WF-D.7
4 | High | Stop shop flows writing master MRP / identity (purchase bill creates product with MRP, no history) | PM-10, PM-16
5 | High | Admin edit screens: product master fields, brands, subcategories | PM-03, PM-04, PM-13
6 | Medium | Add Product form: show brand / pack / GTIN / MRP / image; take stock, threshold, reorder, discount; search by GTIN | SI-02, WF-A
7 | Medium | Dedicated Reorder List page and filter | SI-10, WF-C.7, T15
8 | Medium | MRP column in shop inventory table; "Low stock" label for customers | SI-11, CU-01
9 | Medium | Shop inventory import: thresholds and reorder fields; reject missing GTIN / invalid GST; master-only admin import | IM-01..03
10 | Medium | Canonical GTIN-14 storage and use of the duplicate-candidate check | PM-12
11 | Medium | Tests: last-unit oversell race, cross-shop stock / alert assertions, /api/mrp 403 | T5, T6, T11-T14
12 | Low | Columns: shortName, brandCode, currency, taxCategory, imageType, pack / flavour / size / colour; migrated MRP status PENDING | PM-02..09, PM-11
13 | Low | Per-GTIN ProductDataProvider + GS1 DataKart client and background sync (after GS1 agreement) | EX-01, EX-02
14 | Low | Purchase orders and goods-received notes; stock reservation holds | SU-01, OR-04
15 | Low | Paginate shop product list and stock summary; durable job queue | SC-01
16 | Low | AI: product image recognition, label OCR, AI categorisation / duplicates | AI-01