## Issue register
ID | Source | Role | Screen | Problem | Severity | Fix | Status | Evidence / reason
AUD-01 | UI audit | Admin, Operator | /admin | Admin/operator console was one page of 17 stacked sections: 11.8 desktop / 19 phone screens (local demo); on test.gokesari.com with real data 28 / 71 screens (admin) and 25 / 63 (operator). | Critical | /admin is now only the Tile Board (one screen). Each section moved to its own page /admin/console/{section}; old /admin#… links forward to it. | Fixed | Before: site-before Admin-Home 70.88 screens (360×800). After: board fits 360×800…1920×1080.
AUD-02 | UI audit | Shop owner, Admin, Operator | Site header | Role menus were long flat dropdowns (shop owner 21, operator 26, admin 39 links), scrolling inside themselves; on phones a drawer of up to 39 links. | Critical | Dropdowns and hamburger drawer removed. One “Board” button back to the role's home board; every function sits on the board (≤7 per group) or on its tile's menu page. | Fixed | Unit test: every old role-menu link reachable within 2 clicks (39/39 tests pass).
AUD-03 | UI audit | Shop owner, Operator | Site header (1366 px) | Header wrapped to two rows (112 px) on a 1366 px laptop. | High | New one-row header (64 px desktop, 56 px phone) on every page. | Fixed | Measured header height 64 px at 1366×768.
AUD-04 | UI audit | Admin, Operator | Site header | Back-office roles saw customer items (Deliver to, Cart, ₹0 wallet); two different admin “dashboards”. | High | Admin/operator header shows Board, language, notifications and account only. The board is the single home; the KPI dashboard is Reports › Dashboard. | Fixed | Screenshots Admin-*-After.
AUD-05 | UI audit | Customer | Product cards | Every product showed the same grey placeholder image. | High | Products without a photo show a category picture on a tinted tile (milk, bread, grocery, medicine…). | Fixed | Customer-Category-Dairy-360x800 screenshot.
AUD-05b | UI audit | Customer | Shop cards | Every shop card shows the same cart icon. | Medium | Not changed in this pass: needs shop photos (data). Shop cards keep the icon. | Not fixed | Reason: needs uploaded shop photos, not a UI change.
AUD-06 | UI audit | Customer | Search, category pages | One product per phone screen: search ‘milk’ 7.3 screens, Dairy 13 screens. | High | Two products a row on phones with a compact card (one full-width Add; −/+ once in cart). | Partly fixed | Local: Dairy 13 → 5.0 screens, search 7.3 → 2.6. Still more than one screen when a category has many products (paging of product lists not added).
AUD-07 | UI audit | Shop owner | /shop | Morning rush buried: new orders a number in a pastel KPI tile; page 6,450 px; account notices (suspended, wallet, documents) 8 screens down. | High | “Do now” strip (New orders, Returns, Low stock) and account alerts at the top of the board; Orders opens on the New tab. | Fixed | ShopOwner-Home screenshots; nav test.
AUD-08 | UI audit | Customer | Product cards | Confusing units: “₹100 / ml online”, three unit formats on one page. | Medium | One wording: “/ L”, “/ kg”, “each”, “per pack” (ml and g packs); “online” only when the in-shop price differs. | Fixed | Unit test ‘never prices a pack per millilitre’.
AUD-09 | UI audit | All | /signin | Consent asked three times; “Get code” faded to 2.1:1 with no reason. | Medium | One consent box (staging #121) kept; this pass adds a readable disabled button (6.6:1) and the reason “Tick ‘I agree’ above to continue”, 44 px targets. | Fixed | Signin screenshots.
AUD-10 | UI audit | Customer | /, /categories | Two search boxes on the phone home; 44 text-only category cards (6.9 phone screens). | Medium | One search on the board; categories page = picture tiles with a search box (44 in ~1.9 phone screens, filter as you type). | Fixed | Customer-Categories screenshot.
AUD-11 | UI audit | Customer | /shops/{slug} | No product on a shop page's first screen (address, owner and 7-line hours first). | High | Delivery line kept; address, hours, owner and reviews folded under “Shop info, opening hours and reviews”. | Fixed | Customer-Shop-page screenshot.
AUD-12 | UI audit | All | All pages | Pages ran 4–14 screens on a phone. | High | Role homes are one screen; long lists use tabs + paging (shop orders, returns, disputes, customer orders); sections split into their own pages. | Partly fixed | Second-level pages: median 2.1 phone screens (was 2.1–2.9); forms, policies and long data tables still scroll — see open items.
AUD-13 | UI audit | Customer | Header (phone) | 155 px header on 3 rows; main menu hidden behind the menu icon; cart without label. | Medium | 56 px one-row header; every customer menu on the board; cart icon has its count and accessible name. | Fixed | Measured.
AUD-14 | UI audit | Customer | Product cards | 107 of 175 text items 12 px; buttons ~30 px; three action rows per card. | Medium | Smallest text 12 px site-wide (badges/captions), buttons 40–44 px, compare link 44 px; phone card has one action row. | Partly fixed | Card still shows Add and Subscribe (two rows) when subscription is offered.
AUD-15 | UI audit | All | All pages | English only; no Hindi/Marathi switch. | High | EN/हिं/मरा switch on every page. Boards, menu pages, header, tabs, Do now, alerts and error/empty/offline states translated. | Partly fixed | Body text of second-level pages (forms, tables) is still English — open item.
AUD-16 | UI audit | Operator | /admin | Operator console: 14 KPI tiles that could not be clicked; no work queue. | High | Operator board with “Do now” (late orders, shop applications, open tickets, rider applications), every count clickable. | Fixed | Operator-Home screenshots.
AUD-17 | UI audit | Shop owner, Admin | Dashboards | ‘Rainbow’ KPI tiles (blue/purple/green/orange) with no meaning; some figures 3.2:1. | Medium | KPI cards white with dark figures; red only for ‘needs attention’. | Fixed | Contrast ≥4.5:1 measured.
AUD-18 | UI audit | Customer | Shop cards | Red “Closed · opens …” pills louder than the shop name. | Low | Closed shown in a neutral pill; open stays green; wording unchanged. | Fixed
AUD-19 | UI audit | Customer | Shop cards | Kesari quality badge has the same pill style as type/closed/delivery pills. | Low | Not changed in this pass. | Not fixed | Reason: low impact; needs a badge design decision (open item).
AUD-20 | UI audit | Visitor | Header | Signed-out visitors saw Orders and Subscriptions (both lead to sign-in). | Low | Visitors see Shops only; account tiles on the board lead to sign-in. | Fixed
AUD-21 | UI audit | Customer | /search | Search ‘milk’ lists products but “0 shops” although shops sell milk. | Medium | Not changed: shop matching is search logic (back-end), outside the UI-only scope. | Not fixed | Reason: business logic; recorded as open item.
AUD-22 | UI audit | All | Many pages | Grey text (ink-400) at 2.56:1 (“Unavailable”, “Ask shop”, captions). | Medium | All ink-400 text darkened to ink-500 (4.76:1). | Fixed | All-pages scan: lowest text contrast 4.52:1 after.
AUD-23 | UI audit | All | Forms | Disabled buttons faded to 1.69:1 with no reason. | Medium | Disabled = ink-600 on cream (6.6:1) in the shared Button; reason shown where the rule is known (sign-in). | Fixed
AUD-24 | UI audit | Operator | /operator | /operator just redirected to the admin console. | Medium | /operator → /admin, which is now the operator's own board. | Fixed
BEN-01 | Benchmark: Amazon | Customer | Home | No reorder; no delivery promise on cards; search not scoped. | Medium | “Buy again” on the desktop board (already there) kept; delivery promise and scoped search not added. | Not fixed | Reason: ETA and scoped search need new back-end data/logic.
BEN-02 | Benchmark: Flipkart | Customer | Home | No category icon strip, no bottom bar, English only. | High | Picture category strip on the board; every menu on the board instead of a bottom bar; EN/हिं/मरा. | Fixed | Decision D-05 (board instead of bottom bar).
BEN-03 | Benchmark: Blinkit | Customer | Product cards | Placeholder images; no ADD→stepper; no sticky cart bar; one product per row. | High | Category pictures, cart bar on the board, two products a row; Add then −/+ in place. | Fixed
BEN-04 | Benchmark: Zepto | Customer | Cart | Savings not shown. | Low | Not added. | Not fixed | Reason: needs MRP/savings data on every line (back-end).
BEN-05 | Benchmark: Swiggy Instamart | Customer | Home | Live order not surfaced on home; free-delivery progress not shown. | Medium | Live order in “Do now” (phone) and banner (desktop). Free-delivery progress not added. | Partly fixed | Reason (progress bar): needs the shop's free-delivery rule in the cart bar data.
BEN-06 | Benchmark: BigBasket | Customer | Subscriptions | Daily-milk subscription only behind a header link. | High | “Tomorrow” in Do now and as a banner; Subscriptions › Tomorrow opens the change/skip card. | Fixed
BEN-07 | Benchmark: Meesho | Customer | All | Text-heavy categories, English only, small prices. | Medium | Picture categories, local languages on boards, larger prices on phone cards. | Fixed
BEN-08 | Benchmark: Amazon Seller Central | Shop owner | /shop | No grouping, no ‘needs action’ view. | High | Sixteen grouped menus with live counts and a Do now strip. | Fixed
BEN-09 | Benchmark: Shopify Admin | Admin, Operator | /admin | Flat list, no saved views, no command search. | Medium | Grouped tiles + menu pages; status tabs on lists. Ctrl+K command search not added. | Partly fixed | Reason (command search): new feature, not UI regrouping.
BEN-10 | Benchmark: Flipkart | Customer | Search | No voice search. | Low | Not added. | Not fixed | Reason: new feature (speech input), outside UI-only scope.
USA-01 | Usability proof | All | Role homes | Smallest text on the approved mockups and build: 11–12 px (brief: body ≥14 px on mobile). | High | Tile labels 14–15 px; Do now 13–14 px; badges and captions 12 px; on screens shorter than 760 / 660 px labels step to 13 / 12 px to keep one screen. | Partly fixed | Measured min 12 px (was 10–11). 14 px body met at 360×800 and taller; not on 360×728 / 320×640 boards.
USA-02 | Usability proof | All | Role homes | Smallest tap target 24–32 px on the mockups; 15–20 px on the deployed boards. | High | Phones: whole-tile targets (≥60 px), Do now 48 px, header controls 48 px (44 px below 360 px width), categories 56 px. | Fixed | Measured phone min 44 px (320 wide) / 48 px (≥360); desktop chips 36 px (mouse) — decision D-03.
USA-03 | Usability proof | All | Role homes | One-screen check passed on mockups but the deployed boards ran 2–41 px past a 728 px app screen; pages continued below the board. | High | Boards fill exactly one screen; nothing below the board except the site footer. | Fixed | 105/105 fits: 5 roles × 7 sizes × 3 languages.
USA-04 | Usability proof | All | All pages | Contrast: role pages 1.69:1 (disabled) and 2.56:1 (grey text) found in the full scan. | High | See AUD-22, AUD-23, AUD-17. | Fixed | Lowest text contrast after: 4.52:1 (all 209 role pages).
USA-05 | Usability proof | All | Role homes | Click counts not proven for submenus that all opened the same unfiltered page (New/Packing/Ready/Out; Active/Past; Open/Resolved). | High | Tabs that match the board badges; each submenu opens its own filtered view. | Fixed | Nav test 240/240 links.
USA-06 | Usability proof | All | Role homes | Truncated labels (“Open n…”, “Fruits & …”, “Tomorrow's d…”) in the deployed boards. | Medium | Short phone labels, urgent-only counts on narrow tiles, wider Do now (2×2 when 4 items). | Partly fixed | Zero cut-off labels at 360×800+ except place/shop names (data); 320×640: a few shop-owner/admin submenu labels hidden.
DT-01 | Design review | All | All pages | No error, not-found or offline screens; navigation gave no visible feedback for 1–5 s on slow 4G. | High | Translated error (Try again / Home) and not-found (Back to board) screens, offline banner, top progress bar from the tap. | Fixed
DT-02 | Design review | Admin, Operator | /admin | Many functions only reachable from the removed dropdown (GST settings, accounting sync, self-registration, rider documents, customer referrals, subscriptions, bank accounts, societies for admin…). | High | Each tile's menu page lists the rest of its area (“More”), filtered by permission. | Fixed | Unit test (one clear path).
DT-03 | Design review | Customer, Shop owner | Addresses, cart, shop orders | Delete address, ‘Cancel this order’ and ‘Cancel & refund customer’ acted on one tap. | High | Inline confirmation (“Yes, delete / Keep”) before each. | Fixed
DT-04 | Design review | Admin | /admin | Every visit to /admin loaded all 17 sections' data (users, 500 shops, audit log…) — slow on 4G. | High | /admin loads only the board counts; each section loads its own data. | Fixed | Admin home: 70.9 → 1 screen; server work per visit cut to the counts.
DT-05 | Design review | Operator | /admin | No ‘Do now’ panel for operators (only two banners when non-zero). | High | Operator Do now with four live counts; banners kept on wide screens. | Fixed
DT-06 | Design review | Admin | /admin | ‘Escalated’ and several counts missing on admin (counts loaded per role). | Medium | Same read-only counts loaded for admin and operator (additive). | Fixed | Back-end change B-01.
DT-07 | Design review | All | Header | Language switch only on the four boards; other pages English-only chrome. | High | Switch on every page; header in the chosen language; on phones one 48 px button opens the three languages. | Fixed
DT-08 | Design review | Customer | /profile | Profile tile opened a page where its submenus (Addresses, Society, Refer, Bank, Help) were not at the top. | Medium | Quick links row at the top of My Profile. | Fixed
DT-09 | Design review | Shop owner, Customer | Inventory, Prices, Wallet | Tile → menu page → page added a tap for the most common jobs. | Medium | These tiles open their page directly; submenus as a strip of large links at the top. | Fixed
DT-10 | Design review | Shop owner | Old dashboard | Old dashboard repeated Excel upload and price approvals that also live on Price updates (two paths). | Low | One path: Price updates holds both; old links forward. | Fixed
DT-11 | Design review | All | Forms | Native tick boxes 13 px. | Medium | 20 px tick boxes and radios in the brand colour (site-wide). | Fixed
DT-12 | Design review | Shop owner, Admin | Boards at 320×640 | On the smallest phones (320×640) 1–3 submenu labels per board are hidden inside their tile. | Low | Menus and counts stay visible; tiles still open their page/menu page where every submenu is listed. | Not fixed | Reason: physical limit of one screen with 48 px targets; see decision D-02.
DT-13 | Design review | All | Second-level pages | Body content of forms, tables and policy pages not translated. | High | Not done in this pass. | Not fixed | Reason: thousands of strings; needs native-speaker review. Open item O-02.
DT-14 | Design review | All | Second-level pages | Inside older pages, some links and inputs remain under 44 px (inline text links, date inputs). | Medium | Shared Button/LinkButton raised to 40–44 px; tick boxes 20 px; remaining inline links unchanged. | Partly fixed | All-pages scan: smallest target 13 px (native inputs) on some admin forms.
DT-15 | Design review | All | Footer | Footer links 28 px tall. | Low | 44 px link rows. | Fixed
PERF-01 | PageSpeed | All | gokesari.com / | Mobile Speed Index 8.6 s (score 92): the server took ~4 s to send the page when idle (Lighthouse: document latency 1,050–4,010 ms). The page itself scores 98–100 locally. | High | Root cause found: database connections close after 20 s idle (DATABASE_IDLE_TIMEOUT_SECONDS), so most visits open new TLS connections to a distant database. Owner setting: raise to ~300 on Hostinger (check Neon cost). | Not fixed | Owner/hosting setting; after release, home scored 99 when warm and 93–94 when cold.
PERF-02 | Performance test | All signed-in | All signed-in pages | Signed-in pages take 3.4–5.1 s server time on test.gokesari.com (slow-4G check: 5 of 6 pages 3.6–5.0 s, target 3 s). Database is in Neon us-east-2 (Ohio): every query pays an India↔Ohio round trip. | Critical | Owner/hosting decision: put the database and the web server in the same region (e.g. Neon ap-southeast-1 Singapore, or host near the database). | Not fixed | Reproduced locally with a 200 ms database round trip: 2.1 s per signed-in page.
PERF-03 | Performance test | All signed-in | Layout, header, boards | 52 database queries per signed-in home page; the same user, wallet, addresses, unread count, roles and 8 business rules read several times. | High | React cache() on these read-only lookups; concurrent rule reads share one query: 52 → 24 queries. | Partly fixed | In PR #124 (tests 1,662 pass locally); waiting for GitHub CI (billing) before staging/production.
PERF-04 | Performance test | All | Database driver | Every query costs two database round trips (Drizzle sends unprepared queries; postgres-js describes, then executes). | High | DATABASE_PREPARED_STATEMENTS switch (default off). Measured with a 200 ms round trip: customer home 2.08 → ~1.05 s, admin 2.09 → ~0.67 s, shop orders 2.45 → ~1.65 s. | Partly fixed | In PR #124; owner turns it on for test first (pooler must support prepared statements), then production.
PERF-05 | PageSpeed | Customer | /shops, /search | Lighthouse accessibility 99: heading order skipped a level; the phone language button's spoken name did not include its visible label. | Low | Hidden h2 for the list; accessible name starts with the visible label. | Partly fixed | In PR #124.
PERF-06 | PageSpeed | All | All pages | Render-blocking stylesheet (16 KB): 110–150 ms. | Low | Not changed: inlining saved 10–50 ms in the local run and is an experimental flag (decision D-23). | Not fixed | Decision D-23.
PERF-07 | PageSpeed | All | All pages | Unused JavaScript 68 KiB, legacy JavaScript 17 KiB. | Low | Not changed: the chunks are the Next.js/React runtime itself, not app code. | Not fixed | Framework-owned.
TST-01 | Testing | Admin | /admin/disputes | Resolving a dispute gave no visible confirmation within 5 s (the server took several seconds); a second click was refused (409). | Medium | Not changed in this pass: add a busy state and a success message to the dispute queue. | Not fixed | Test A-06.
TST-02 | Testing | Shop owner, Operator | Returns | An approved return waiting for a rider cannot be completed by staff until a rider is on the way; with no rider online it waits. | Medium | Not changed: business rule (returns pickup). | Not fixed | Test S-11b not run.
TST-03 | Testing | Customer | /orders?tab=returns | The Returns tab links to /returns; /orders?tab=returns shows the Active tab. | Low | Not changed. | Not fixed | Test C-10.
TST-04 | Testing | Shop owner, Admin | /shop/manage/products | 126 products on one list (5 phone screens). | High | Tabs (My products / Add products), search, six a page. | Partly fixed | In PR #124.
TST-05 | Testing | Admin, Operator | /admin/shop-categories | Category list 8.3 phone screens. | Medium | Tabs and eight rows a page. | Partly fixed | In PR #124.
TST-06 | Testing | Admin | /admin/settings | Business rules page 34.8 phone screens. | High | Searchable list, one rule's editor at a time. | Partly fixed | In PR #124.
TST-07 | Testing | Shop owner | Board at 320×640 (real data) | With two account alerts the shop owner's board is 2 px taller than a 320×640 screen; 1–6 submenu labels hidden on the smallest phones. | Low | Accepted limit (decision D-02); 104/105 board checks fit on test.gokesari.com. | Not fixed | Decision D-02.
TST-08 | Testing | Customer, Admin | Profile, dashboard, finance, compliance, Today, category, shop, search | Long second-level pages (5–9 phone screens). | High | Tabs and paging on each. | Partly fixed | In PR #124; second-level pages median 2.2 phone screens, 38 still over 3 (forms, legal texts, admin tools).

## Totals
Group | Total | Fixed | Partly fixed | Not fixed
All issues | 71 | 39 | 16 | 16
Severity: Critical | 3 | 2 | 0 | 1
Severity: High | 31 | 20 | 9 | 2
Severity: Medium | 24 | 13 | 6 | 5
Severity: Low | 13 | 4 | 1 | 8
Source: UI audit | 25 | 18 | 4 | 3
Source: Benchmark | 10 | 5 | 2 | 3
Source: Usability proof | 6 | 4 | 2 | 0
Source: Design review | 15 | 12 | 1 | 2
Source: PageSpeed | 4 | 0 | 1 | 3
Source: Performance test | 3 | 0 | 2 | 1
Source: Testing | 8 | 0 | 4 | 4