## Summary
GoKesari – open features (3 Oct 2026)
Source: GOKESARI_FEATURE_STATUS_REPORT_2026-10-03.xlsx (code on main), updated for PRs #42/#43 merged 3 Oct. Status = development status, not QA sign-off.
Item | Count | Note
In progress – total | 23
of which waiting on a decision | 8 | Blocked by design decisions or external dependencies
of which ready to build | 15 | No dependencies, ready to start
Yet to start | 1 | Design complete, awaiting go-ahead to build
Decisions pending | 8 | Critical and priority decisions listed in the "Decisions pending" sheet
Go-live blockers open | 3 | Critical issues blocking go-live (see "Go-live blockers" sheet)
Completed features (from 3-Oct report) | 132 | Hardcoded from the 3-Oct status report (157 tracked total)
Total features tracked (from 3-Oct report) | 157 | Baseline from the 3-Oct feature status report
% complete | 84% | 132 ÷ 157

## In progress
# | ID | Feature | Area (wave) | Status | Type | Blocked on | What is built | Remaining scope | Note
1 | GS-001 | Mobile/email/Gmail login | Access & security foundation | IN PROGRESS | Waiting on a decision | D2 – SMS/OTP vendor | Google + email magic link + mobile-number login with a code sent to the account email (main). On STAGING ONLY (5f64ea2): rebuilt single form taking mobile OR email, first-time /onboarding profile (name, gender, mobile, address with map pin), My Profile with verified email change, checkout requires a mobile, admin can release a wrongly-claimed number | SMS delivery of the OTP so a mobile number is proven; promote the staging login rebuild to main | Login rebuild + first-time profile merged to main on 3 Oct (PRs #42/#43); only SMS delivery remains.
2 | GS-074 | SMS/WhatsApp/email/push | Notifications | IN PROGRESS | Waiting on a decision | D2 – SMS/OTP vendor | Email and in-app are real and live (email needs SMTP in production; without it email is skipped, not failed). SMS, PUSH and WHATSAPP are enum values with a provider seam and one plug-in point | Real SMS / push / WhatsApp providers
3 | GS-028 | UPI/card/netbanking gateway | Checkout & payments | IN PROGRESS | Waiting on a decision | Per-order payment go-ahead | Cashfree is live but only for wallet top-up (create-order, server-side verify, HMAC webhook, mock mode). Orders are still WALLET or COD only. A full design for per-order ONLINE payment was signed off on 1 Oct (generalise payments.purpose, orders.payment_method += ONLINE, migration 0036) - no code written | Build per-order gateway payment
4 | GS-073 | Payment gateway | Checkout & payments | IN PROGRESS | Waiting on a decision | Needs GS-028 (per-order payment) | Gateway plumbing exists and is reusable; refunds today are wallet credits through refundDeliveredOrder (journaled, idempotent). Gateway refunds and order payments are designed, not built | Gateway refunds; order payments
5 | SM-005 | Payment state machine | State model extension (map, don't replace) | IN PROGRESS | Waiting on a decision | Needs GS-028 (per-order payment) | Unchanged. payment_status is still CREATED / PENDING / SUCCESS / FAILED / REFUNDED | AUTHORIZED/CAPTURED, RECONCILED, CHARGEBACK
6 | WF-001 | Customer product purchase | Checkout & payments | IN PROGRESS | Waiting on a decision | Needs GS-028 (per-order payment) | Location, eligible shops, comparison, serviceability block, substitution, minimum order, paused shops, and (1 Oct) ordering from a closed shop behind an explicit customer confirmation with two shop alerts | Direct gateway payment for orders (GS-028)
7 | GS-023 | E-commerce price benchmark | Phase 2 features | IN PROGRESS | Waiting on a decision | D7 – licensed price source | External reference prices with source, time, location, URL and verification plus an audit history, kept strictly separate from MRP and selling price and never written into either. Visibility is a rule: shops and operations see them, customers do not | Turn on the customer display (code is in place, the rule is off)
8 | SM-006 | Issue state machine | State model extension (map, don't replace) | IN PROGRESS | Waiting on a decision | SM-006 scope decision | Tickets linked to orders; returns have a 13-status state machine; NEW: dispute cases carry exactly the missing states (TRIAGED / INVESTIGATING / RESOLUTION_PROPOSED / ESCALATED). Grievance ladder itself still OPEN / IN_PROGRESS / RESOLVED / CLOSED | Either add the four states to grievances, or decide that dispute cases satisfy SM-006 and close it
9 | SM-002 | Shop state machine | State model extension (map, don't replace) | IN PROGRESS | Ready to build | — | shop_status unchanged (PENDING_APPROVAL/APPROVED/REJECTED/SUSPENDED/INACTIVE), but the suspension half now has a real lifecycle: configurable policy per open-order status, impact preview, per-order decisions, owner notice, reinstatement; plus an orders_paused switch | KYC_PENDING, PAYMENT_PENDING, VERIFIED vs ACTIVE, CLOSED
10 | SM-003 | Gig state machine | State model extension (map, don't replace) | IN PROGRESS | Ready to build | — | delivery_partner_status unchanged (REGISTERED/UNDER_REVIEW/APPROVED/REJECTED/SUSPENDED/DEACTIVATED); the delivery leg gained arrival checkpoints (arrived_at_shop_at, arrived_at_customer_at), which is where DELIVERING-style granularity now lives | KYC_PENDING, BLOCKED, DELIVERING on the partner itself
11 | SM-004 | Subscription state machine | State model extension (map, don't replace) | IN PROGRESS | Ready to build | — | Final states locked; subscription_events history; resume/cancel notifications. Enum unchanged: ACTIVE/PAUSED/CANCELLED/COMPLETED/PAYMENT_PENDING | DRAFT, RENEWAL_PENDING, ORDER_CREATED/FULFILLED states
12 | GS-072 | Maps/navigation | Location & serviceability | IN PROGRESS | Ready to build | — | Google Geocoding (one call per shop, cached), Places address search, haversine distance, turn-by-turn handed off as a Google Maps deep link for riders and return pickups, and a feasibility-based estimated-minutes figure at checkout | Road routing, a real ETA from a routing API, in-app navigation
13 | GS-007 | Business KYC | Shop onboarding completion | IN PROGRESS | Ready to build | — | GSTIN, PAN and FSSAI numbers are captured and verified/rejected by operations with their own status enums and encrypted storage; an image store now exists (stored_images, /api/images) that documents could use | Document upload/storage wired to a shop; one tracked KYC status instead of separate GST/PAN states
14 | WF-008 | Shop onboarding | Shop onboarding completion | IN PROGRESS | Ready to build | — | Service area complete (radius + extra PIN zones + minimum order + pause switch); categories required at registration; duplicate-registration guard; MRP/price correction queues; registration-fee gate before approval now ENFORCED (GS-008) | KYC document upload wired to a shop (see GS-007)
15 | NAV-001 | Customer portal - Home | Discovery & local price comparison | IN PROGRESS | Ready to build | — | Location picker, 'Shops that deliver to you', featured / Kesari / Green shelves, and a product-search-first hero (the category grid was deliberately removed) | Price-comparison widgets on the home page itself
16 | NAV-002 | Customer portal - Shop | Discovery & local price comparison | IN PROGRESS | Ready to build | — | Shop rating + recent reviews; opening hours with closed-now state; delivery options now shown (fee, free-above threshold, pickup-only, minimum order) | Offers / vouchers on the shop page
17 | GS-027 | Delivery slot | Checkout & payments | IN PROGRESS | Ready to build | — | EXPRESS_30 / STANDARD_60 / SCHEDULED windows with a feasibility preview that will not promise a window the system cannot back, plus an estimated-minutes figure | Slot capacity rules; real scheduled slot times
18 | GS-033 | Shop order split | Checkout & payments | IN PROGRESS | Ready to build | — | Checkout already produces one order per shop from a multi-shop cart, with per-shop validation and delivery charges | A master order row linking the child orders (single customer-facing reference)
19 | NAV-003 | Customer portal - Cart & Checkout | Checkout & payments | IN PROGRESS | Ready to build | — | Cart now re-validates against the chosen location and shows each issue with an action (change address / add items / remove these items); minimum order and paused shops enforced | Order-level coupons; gateway payment
20 | GA-005 | Current load | Delivery & gig assignment | IN PROGRESS | Ready to build | — | Unchanged: a rider already on a delivery is EXCLUDED from the candidate pool (row-locked to stop races). Ranking weights are distance + reliability + fairness only - no load term | Lower priority instead of exclusion; multi-order batching
21 | NAV-013 | Gig portal - Profile | Delivery & gig assignment | IN PROGRESS | Ready to build | — | The profile page is read-only: vehicle type and registration are displayed, identity and bank details are stored encrypted and deliberately not shown. The only PATCH on a partner is operations' verification actions | Rider self-edit of KYC / vehicle / bank details
22 | GS-014 | Product images/specifications | P1 MVP features | IN PROGRESS | Ready to build | — | Image store (stored_images, /api/images) with validation, browser-side shrink and a safe fallback; several images per product or per listing, primary image, reorder, replace, delete, alt text. products.specifications exists | Image moderation (the product-approval queue does not review images)
23 | GS-054 | Referral program | Phase 2 features | IN PROGRESS | Ready to build | — | What exists is SHOP referral attribution: referral codes, usable-code resolution, attributing a registering shop to a code, performance report. There is no customer referral | Customer referral rewards and the fraud checks that go with them

## Yet to start
# | ID | Feature | Status | What exists | Remaining scope | Blocked on
1 | NEW-007 | Direct per-order payments, tax invoicing, photo POD, accept timeout | YET TO START | Design only - no code, no migrations. Covers ONLINE payment method via Cashfree hosted checkout per order, shop invoices goods while the platform invoices its own fees, photo proof of delivery on the existing handover, and auto-cancel with full refund when a shop does not accept in time | The whole build | Awaiting go-ahead after design review; decisions D1 and D6 already taken

## Decisions pending
# | Decision | What is needed | Unblocks | Priority | Status
1 | Per-order payment (GS-028 / NEW-007) | Approve building per-order online payment, OR launch with wallet + COD only | GS-028, GS-073, SM-005, WF-001, NEW-007, go-live | High – go-live blocker | PENDING
2 | D2 – SMS / OTP vendor | Pick a DLT-registered SMS provider (India) | GS-001 (proven mobile), GS-074 (SMS/WhatsApp/push) | High | PENDING
3 | D7 – external price source | Approve a lawful/licensed source for customer-visible reference prices | GS-023 (one setting: externalPrices.showToCustomers) | Medium | PENDING
4 | D10 – cancellation policy | Confirm customer cannot cancel at ACCEPTED/ASSIGNED, and PICKED_UP refunds goods only | Sign-off of cancellation feature (NEW-006) | Medium | PENDING
5 | RBAC-003 – Operator 'Limited' shop management | Define what an operator may change on a shop (feature status UNCLEAR, nothing built) | RBAC-003 | Medium | PENDING
6 | SM-006 scope | Does the dispute case lifecycle satisfy the issue state machine, or must grievances get the same states? | SM-006 | Low | PENDING
7 | D6 – settlement model | How the delivery fee kept on a cancelled (dispatched) order is shared/reported | Finance reporting | Low | PENDING
8 | Default business rules (/admin/settings) | Confirm or change: 48 h return window; "changed my mind" not accepted; defect returns charged to shop; rider return fee = base delivery fee; suspension policy; dispatch retry 60 s × 10 / 30 min; OTP 6 digits / 10 min / 5 attempts; images 2 MB, 8 per product; MRP enforced only when verified | Day-to-day app behaviour | Medium | PENDING

## Go-live blockers
# | Blocker | Detail | Status
1 | No browser / QA sign-off | Nothing since Phase 1 has been tested and signed off in a browser; status is code + automated tests only | OPEN
2 | Production migrations | Apply migrations up to 0039 in production, plus cron jobs for notifications and dispute escalation (see DEPLOY_RUNBOOK.md) | OPEN
3 | Per-order payment decision | See Decisions pending #1 | OPEN