## Summary
Item | Value
Report | GoKesari — Homepage UI/UX upgrade (F1–F6): status, product tracker update and testing report
Generated | 20 Oct 2026, 12:20 IST (06:50 UTC) — staging deployed and tested; production released (#219) but not yet built by Hostinger (DEF-14)
Branch / PR | Feature #214, fixes #215 / #218, release #219 (staging → main); results #217 (branch claude/gifted-brahmagupta-nj0bt9 → staging)
Features (sub-items) | 28
Features done | 28
End-to-end flows | 21
Automated test cases (Playwright, unique) | 37
Playwright pass rate — Local | 35/35 (100%)
run used for Local | localhost_3000 (http://localhost:3000, 2026-10-19T22:38)
Playwright pass rate — Staging | 30/30 (100%)
run used for Staging | test.gokesari.com (https://test.gokesari.com, 2026-10-20T05:51)
Playwright pass rate — Production | Blocked (DEF-14)
Playwright pass rate — Android | 20/20 (100%)
run used for Android | test.gokesari.com-app-android (https://test.gokesari.com, 2026-10-20T05:54)
Playwright pass rate — iOS | 22/22 (100%)
run used for iOS | test.gokesari.com-app-ios (https://test.gokesari.com, 2026-10-20T05:56)
Unit + integration (Vitest, local, single DB) | 2,254 / 2,255 first run; the 1 failure (SEC-03) was a BOOTSTRAP_ADMIN_EMAILS value in the local .env; re-run of that file 28/28 → effectively 2,255 / 2,255
New tests on the split layout (local) | 39 / 39 (homepage-uiux unit + integration, price-comparison, db-split ownership); migrations 0086 → core, 0087 → seller applied on an existing split layout
Mobile app (mobile/) | typecheck ✓, lint ✓, 36 / 36 tests, Expo bundles Android + iOS ✓
Lint / typecheck (web) | 0 errors (4 pre-existing warnings), tsc clean, production build ✓
Android APK 1.3.0 (GitHub 'Android APK' workflow, PR #214) | Built ✓ — artifacts GoKesari-preview-apk and GoKesari-production-apk (run 39333658232, expire 18 Nov 2026)
CI on PR #214 | scope ✓, test ✓ (full suite), test-split ✓ (two-database layout), mobile ✓, APK preview ✓, APK production ✓ — merged into staging 19 Oct 22:49 UTC
Existing E2E regression (local) | acceptance 5/5 (sign-in, wallet top-up, subscribe 2 L/day, daily order + charge, change tomorrow, offline-only, access control, cron auth); mobile-app 5/7 (2 need the dev sign-in form, run on the dev server); branding-footer 8/8 (updated to the new footer); inventory-accounting, document-browser-read pass on the production build; regression-items-a-e 10 pass, then stops at the stale C1 step (Seller Central moved the shop contact card on 14 Oct — predates this change; later serial steps not reached, covered by integration tests)
Staging remote regression (batch-2026-10-remote + branding-footer) | 20 / 20 passed on test.gokesari.com (20 Oct 05:58 UTC)
Deploy — Staging — PR #214 merged | 19 Oct 2026 22:49 UTC (merge 1f4cd76)
Deploy — Staging — fix PR #215 merged | 19 Oct 2026 23:50 UTC (merge e6dab2d)
Deploy — Staging database (split: core + seller) | Test database run 39344001502, 23:51 UTC: backup ✓, 0086 → core, 0087 → seller, verify newest 0087 ✓
Deploy — Staging — site build | 20 Oct 04:47 UTC: staging c2b1018 (#214 + #215 + #218) after Hostinger's SELLER_DATABASE_URL was corrected (DEF-13)
Deploy — Split layout — staging | split: core neondb, seller gokesari_seller (Database split switch-status, run 39376681434, 05:46 UTC)
Deploy — Split layout — production | split: core neondb, seller PROD_SELLER_DATABASE_URL (Database split switch-status, run 39376683693, 05:46 UTC)
Deploy — Production database (0086, 0087) | Production database run 39372089225, 04:55 UTC: restore point, migrate, state after ✓
Deploy — Production — release #219 (staging → main) | merged 20 Oct 05:39 UTC (80189e2), owner-approved
Deploy — Production — site build | Not live at 06:49 UTC: gokesari.com serves a build of 06:02 UTC without the release (DEF-14)
Open blockers | 5
Blocker | Production deploy: gokesari.com has not built release #219 (DEF-14) — check the Hostinger build log for gokesari.com (most likely SELLER_DATABASE_URL, as on the test site) and redeploy. The production-safe suite, app checks and Lighthouse run as soon as the new home is live.
Blocker | iOS native build: the 'iPhone app' workflow needs the repository secret EXPO_TOKEN and the Expo project id in mobile/app.config.ts (last run 18 Oct failed on both). Owner: add them (mobile/README.md 'iPhone builds from GitHub'), then Actions → iPhone app → Run (preview).
Blocker | Android emulator / iOS simulator: this cloud environment has no Android SDK / KVM and no macOS. App checks ran as Playwright emulation of the app WebView (app user agent, touch, phone widths); the Android APKs are built by the 'Android APK' workflow on the PR.
Blocker | Signed-in flows on staging / production: they need the emailed sign-in code of a test account. Reading it from the test mailbox was refused by this session's permission check (D-28); signed-in flows ran locally (F1-ACCOUNT-DESKTOP, F3-EMPTY-STATES, F6-FLOATING-CART, F2-RECENT-ACCOUNT, F1-BANNER-ADMIN). Staging sandbox payment (Cashfree) needs a signed-in session → not run in this pass.

## Features
ID | Feature | Sub-item | Files changed | Status | Local | Staging | Production | Android | iOS | Notes
F1.1 | F1 De-clutter home | Orders / Subscription / Wallet / Tracking / Profile tiles removed from the home page body | src/app/page.tsx; src/components/home/home-page.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F1.2 | F1 De-clutter home | Desktop 'Account' dropdown: 'Sign in / Create account' for guests, grouped menu (Orders, Subscriptions, Wallet, Tracking, Profile) when signed in | src/components/home/account-nav.tsx; src/components/home/home-header.tsx | Done | Pass | Pass | Blocked (DEF-14) | Not run | Not run | Signed-in check runs locally (dev sign-in); staging/production need an emailed OTP
F1.3 | F1 De-clutter home | Phone side drawer (☰): guest → Sign in / Create account only; signed in → the five account groups | src/components/home/account-nav.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass | Drawer and location sheet render in a portal (above the bottom navigation)
F1.4 | F1 De-clutter home | Phone bottom navigation: Home · Categories · Compare · Orders · Account (44 px+) | src/components/home/mobile-shop-nav.tsx; src/app/layout.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F1.5 | F1 De-clutter home | Home order: sticky header → search → hero → categories → shops near you (filters) → Buy again / Popular → Sell / Deliver → footer | src/components/home/home-page.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F1.6 | F1 Hero banners | Carousel: reserved height (no layout shift), first image eager / rest lazy, auto-rotate, pause on hover / touch / focus / button, swipe, ← →; built-in banners when none is live | src/components/home/hero-carousel.tsx; src/lib/home-banners.ts | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass | Lighthouse CLS 0
F1.7 | F1 Hero banners | Admin / operator: create, schedule (start/end), reorder, switch on/off, picture upload, CTA link, city / PIN targeting; audited | src/app/admin/home-banners/page.tsx; src/components/home/home-banner-manager.tsx; src/app/api/admin/home-banners/*; src/server/services/home-banners.ts; drizzle/0086; permission HOME_BANNER_MANAGE | Done | Pass | Not run | Blocked (DEF-14) | Not run | Not run | Integration tests (permissions, schedule, targeting, order) pass locally; staging/production need a signed-in admin
F2.1 | F2 Search | Wide search centred in the desktop header; full width under the header on phones, sticky with it | src/components/home/home-header.tsx; src/components/home/search-box.tsx; src/components/site-header.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F2.2 | F2 Search | Placeholder in the active language: 'Search for milk, bread, or medicines…' | src/lib/home-i18n.ts | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F2.3 | F2 Search | Predictive suggestions (≥ 2 chars, 250 ms): Products · Shops · Categories, highlight, ↑ ↓ Enter Esc | src/components/home/search-box.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F2.4 | F2 Search | On focus: recent searches (account; localStorage for guests) and trending | src/server/services/search-suggest.ts; src/app/api/search/recent/route.ts; drizzle/0086 | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F2.5 | F2 Search | Voice search (Web Speech API) in en-IN / hi-IN / mr-IN; mic hidden where unsupported and in app builds before 1.3.0 | src/components/home/search-box.tsx; src/lib/mobile-app.ts | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass | Android WebView has no Web Speech API → mic hidden in the Android app
F2.6 | F2 Search | Suggestion API with trigram indexes, nearby shops ranked first; submit → existing /search?q= | src/app/api/search/suggest/route.ts; drizzle/0087; src/app/search/page.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F3.1 | F3 Empty states | Cart empty: basket illustration, 'Start shopping' + 'Explore bestsellers'; shown once (never on the home page) | src/components/cart-view.tsx; src/components/empty-illustrations.tsx; src/app/cart/page.tsx | Done | Pass | Not run | Blocked (DEF-14) | Not run | Not run
F3.2 | F3 Empty states | 'Popular items in your area' for guests / new customers (area → city → platform → on sale nearby) with Add; real Buy again kept | src/server/services/home-discovery.ts; src/components/home/product-tiles.tsx; src/server/services/board-counts.ts | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F3.3 | F3 Empty states | Same pattern for Orders, Subscriptions, Wallet history, search no-results | src/app/orders/page.tsx; src/app/subscriptions/page.tsx; src/components/wallet-view.tsx; src/app/search/page.tsx; src/components/ui.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F4.1 | F4 Compare | 'Compare prices' chip filled accent + 'Smart tool' badge; 'Compare all shops' the same | src/components/home/home-page.tsx; src/components/home-price-comparison.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F4.2 | F4 Compare | Product cards sold by 2+ nearby shops: 'Compare N prices' → /search/compare?product=… | src/components/product-card.tsx; product-grid.tsx; product-tiles.tsx; search, category, shop pages | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass | Counts are per the visitor's location; integration test nearbyOfferCounts
F4.3 | F4 Compare | Compare page: lowest price tagged 'Best price', saving vs highest | src/app/search/compare/page.tsx; src/server/services/price-comparison.ts | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F5.1 | F5 Footer | Company / Make Money / Support / Legal columns; accordions on phones | src/components/site-footer.tsx; src/components/footer-columns.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F5.2 | F5 Footer | Bottom bar: language switch, '© ASMY GLOBAL TRADING & CONSULTANCY INDIA PRIVATE LIMITED · GSTIN 27ABCCA8318D1ZV' | src/components/site-footer.tsx; src/components/board/board-header.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F6.1 | F6 Mobile | Sticky header with 'Deliver to' and cart badge, compacting on scroll (site-wide sticky fix: overflow-x clip) | src/components/home/home-header.tsx; src/app/globals.css | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F6.2 | F6 Mobile | Floating 'View cart · N items · ₹total' above the bottom navigation | src/components/home/mobile-shop-nav.tsx; src/app/layout.tsx | Done | Pass | Not run | Blocked (DEF-14) | Not run | Not run
F6.3 | F6 Mobile | 'Deliver to' bottom sheet: GPS, saved addresses, PIN; refreshes shops, banners, popular | src/components/home/location-sheet.tsx | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass
F6.4 | F6 Mobile | Safe-area insets, no sideways scroll 320–430 px, 44 px tap targets | src/components/home/*; mobile app (native insets) | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass | Overflow measured at 320/360/390/414
F7.1 | Languages & themes | All new text in EN / हिं / मरा; works in the one existing theme (CSS tokens) | src/lib/home-i18n.ts | Done | Pass | Pass | Blocked (DEF-14) | Pass | Pass | Unit test: every label has three languages
F7.2 | Switch | Rule homeDiscovery (Admin → Settings → Rules): off restores the Tile Board home | src/server/config/rules.ts; src/app/page.tsx | Done | Pass | Pass | Pass | N/A | N/A | Unit test; default on
F8.1 | Mobile apps | App 1.3.0: iPhone mic / speech descriptions, /search/compare deep links, white strip under the bottom nav | mobile/app.config.ts; mobile/src/deep-links.ts; mobile/src/App.tsx; src/lib/deep-links.ts | Done | Not run | Not run | Blocked (DEF-14) | Not run | Pass | Bundles for Android and iOS built; native builds: see Summary blockers

## Flows
Flow ID | Flow | New / existing | Steps | Expected result | Local | Staging | Production | Android | iOS | Evidence / notes
NF-01 | Guest discovers products from the home page | New | Open / → type 'mil' in search → pick a suggestion or Enter | Grouped suggestions with highlight; Enter opens /search?q= | Pass | Pass | Blocked (DEF-14) | Pass | Pass
NF-02 | Set delivery location from the bottom sheet | New | Tap 'Deliver to' → enter PIN 411014 → Use PIN | Label shows 411014; 'Shops near you' and banners refresh | Pass | Pass | Blocked (DEF-14) | Pass | Pass
NF-03 | Add a popular item and check out from the floating bar | New | Sign in → home → Add on a popular item → floating 'View cart · 1 item · ₹…' → cart | Bar above the bottom nav, cart badge 1, opens /cart | Pass | Not run | Blocked (DEF-14) | Not run | Not run
NF-04 | Admin manages a home banner | New | Admin → Home banners → add → home shows it → switch off → gone → delete | Banner live, then hidden, then removed; audited | Pass | Not run | Blocked (DEF-14) | Not run | Not run
NF-05 | Compare prices from the accent chip | New | Home → 'Compare prices' (Smart tool) → compare page | Best price tagged; saving against the highest shown | Pass | Pass | Blocked (DEF-14) | Pass | Pass
NF-06 | Voice search | New | Tap mic → speak | Recogniser runs in the page language (mr-IN for मरा); hidden where unsupported | Pass | Pass | Blocked (DEF-14) | Pass | Pass
NF-07 | Phone navigation (drawer + bottom nav) | New | ☰ → drawer; bottom nav items | Guest sees only Sign in / Create account; 5 bottom items ≥ 44 px | Pass | Pass | Blocked (DEF-14) | Pass | Pass
NF-08 | Footer and language | New | Open each footer column → follow every link → switch to हिं | 16 links open (no 404); page switches to Hindi | Pass | Pass | Blocked (DEF-14) | Pass | Pass
NF-09 | Empty states | New | New customer: /cart, /orders, /subscriptions, /wallet; search with no results | Illustration + next-step CTA; cart empty said once | Pass | Pass | Blocked (DEF-14) | Pass | Pass
EF-01 | Sign-in / OTP | Existing (regression) | /signin → email or mobile → code | Signed in, lands on home or onboarding | Not run | Not run | Not run | Not run | Not run | Local: e2e dev sign-in + integration OTP tests; remote: /signin page renders (code needs a mailbox)
EF-02 | Browse shops by category | Existing (regression) | / → category tile → /shops?type=… | Shops of that type | Not run | Not run | Not run | Not run | Not run | Routes + HP category tiles
EF-03 | Nearby / Open now / Delivers here filters | Existing (regression) | /shops/nearby, /shops?open=1, /shops?delivery=true | Filtered lists | Not run | Not run | Not run | Not run | Not run | REG-ROUTES + shop filter integration tests
EF-04 | Add to cart → checkout → wallet / UPI payment | Existing (regression) | Add → /cart → place order (wallet, or Cashfree UPI) | Order placed, wallet charged once | Not run | Not run | Not run | Not run | Not run | Local: acceptance e2e + checkout/payment integration (mock gateway); staging sandbox needs a signed-in session
EF-05 | Subscription create / pause | Existing (regression) | Subscribe 2 L/day → pause / change tomorrow | Daily order generated, charged correctly | Not run | Not run | Not run | Not run | Not run | acceptance e2e + subscription integration
EF-06 | Order tracking + delivery OTP | Existing (regression) | Active order → live map → delivery code | Code verifies; order delivered | Not run | Not run | Not run | Not run | Not run | Integration (delivery OTP, tracking) + regression e2e
EF-07 | Returns | Existing (regression) | Delivered order → return request | Return created and handled | Not run | Not run | Not run | Not run | Not run | Integration + regression e2e
EF-08 | Seller registration | Existing (regression) | /sell → register shop | Registration saved, pending approval | Not run | Not run | Not run | Not run | Not run | /sell renders; integration registration tests
EF-09 | Delivery partner apply | Existing (regression) | /delivery-partner/apply | Application saved | Not run | Not run | Not run | Not run | Not run | Route + integration
EF-10 | Shop owner / admin / operator dashboards | Existing (regression) | /shop, /admin, /operator boards | Boards render with counts | Not run | Not run | Not run | Not run | Not run | Unchanged code; integration + e2e regression; remote: sign-in redirect
EF-11 | Footer / legal links | Existing (regression) | Every footer link | No 404s | Not run | Not run | Not run | Not run | Not run | F5-FOOTER, REG-ROUTES
EF-12 | Language switch EN / हिं / मरा | Existing (regression) | Header / footer switch | Page re-renders in that language | Not run | Not run | Not run | Not run | Not run | HP-* in three languages, F5-FOOTER

## Test Cases
Test ID | Feature | Scenario | Device / breakpoint | Language | User type | Local | Staging | Production | Android | iOS | Evidence (screenshot)
APP-VOICE-1.2.0 | F2/App | Mic in iPhone app 1.2.0 | ios app 390px | en | guest | Not run | Not run | Not run | Not run | Pass | iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/APP-VOICE-1.2.0.png
APP-VOICE-1.3.0 | F2/App | Mic in iPhone app 1.3.0 | ios app 390px | en | guest | Not run | Not run | Not run | Not run | Pass | iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/APP-VOICE-1.3.0.png
F1-ACCOUNT-DESKTOP | F1 | Account dropdown, grouped | 1440px | en | customer | Pass | Not run | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/F1-ACCOUNT-DESKTOP.png
F1-BANNER-ADMIN | F1 | Admin banner create → live → off → delete | 1440px | en | admin | Pass | Not run | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/F1-BANNER-ADMIN.png
F1-DRAWER-GUEST | F1 | Hamburger drawer for a guest | 390px | hi | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F1-DRAWER-GUEST.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F1-DRAWER-GUEST.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F1-DRAWER-GUEST.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F1-DRAWER-GUEST.png
F1-HERO | F1 | Carousel controls | 1024px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F1-HERO.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F1-HERO.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F1-HERO.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F1-HERO.png
F2-API | F2 | GET /api/search/suggest | API | en | guest | Pass | Pass | Not run | Pass | Pass
F2-RECENT-ACCOUNT | F2 | Recent searches kept on the account | 390px | en | customer | Pass | Not run | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/F2-RECENT-ACCOUNT.png
F2-SUGGEST-DESKTOP | F2 | Autosuggest with keyboard | 1440px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F2-SUGGEST-DESKTOP.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F2-SUGGEST-DESKTOP.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F2-SUGGEST-DESKTOP.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F2-SUGGEST-DESKTOP.png
F2-VOICE | F2 | Mic shown when supported, hidden when not | 390px | mr | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F2-VOICE.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F2-VOICE.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F2-VOICE.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F2-VOICE.png
F3-EMPTY-STATES | F3 | Cart, orders, subscriptions, wallet empty states | 1440px | en | customer | Pass | Not run | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/F3-EMPTY-STATES.png
F3-SEARCH-EMPTY | F3 | No-results empty state | 390px | mr | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F3-SEARCH-EMPTY.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F3-SEARCH-EMPTY.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F3-SEARCH-EMPTY.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F3-SEARCH-EMPTY.png
F4-COMPARE | F4 | Compare page tags best price | 1440px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F4-COMPARE.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F4-COMPARE.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F4-COMPARE.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F4-COMPARE.png
F5-FOOTER | F5 | Footer links and accordions | 390px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F5-FOOTER.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F5-FOOTER.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F5-FOOTER.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F5-FOOTER.png
F6-FLOATING-CART | F6/F3 | Popular item → floating cart bar | 390px | en | customer | Pass | Not run | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/F6-FLOATING-CART.png
F6-LOCATION-SHEET | F6 | Location bottom sheet, PIN 411014 | 390px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F6-LOCATION-SHEET.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F6-LOCATION-SHEET.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F6-LOCATION-SHEET.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F6-LOCATION-SHEET.png
F6-STICKY | F6 | Sticky, compacting header | 360px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/F6-STICKY.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/F6-STICKY.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/F6-STICKY.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/F6-STICKY.png
HP-1024-en | F1/F2/F5/F6 | Home renders the discovery layout | 1024px | en | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-1024-en.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-1024-en.png
HP-1024-hi | F1/F2/F5/F6 | Home renders the discovery layout | 1024px | hi | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-1024-hi.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-1024-hi.png
HP-1024-mr | F1/F2/F5/F6 | Home renders the discovery layout | 1024px | mr | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-1024-mr.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-1024-mr.png
HP-1440-en | F1/F2/F5/F6 | Home renders the discovery layout | 1440px | en | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-1440-en.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-1440-en.png
HP-1440-hi | F1/F2/F5/F6 | Home renders the discovery layout | 1440px | hi | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-1440-hi.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-1440-hi.png
HP-1440-mr | F1/F2/F5/F6 | Home renders the discovery layout | 1440px | mr | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-1440-mr.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-1440-mr.png
HP-360-en | F1/F2/F5/F6 | Home renders the discovery layout | 360px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-360-en.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-360-en.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-360-en.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-360-en.png
HP-360-hi | F1/F2/F5/F6 | Home renders the discovery layout | 360px | hi | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-360-hi.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-360-hi.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-360-hi.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-360-hi.png
HP-360-mr | F1/F2/F5/F6 | Home renders the discovery layout | 360px | mr | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-360-mr.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-360-mr.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-360-mr.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-360-mr.png
HP-390-en | F1/F2/F5/F6 | Home renders the discovery layout | 390px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-390-en.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-390-en.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-390-en.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-390-en.png
HP-390-hi | F1/F2/F5/F6 | Home renders the discovery layout | 390px | hi | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-390-hi.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-390-hi.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-390-hi.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-390-hi.png
HP-390-mr | F1/F2/F5/F6 | Home renders the discovery layout | 390px | mr | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-390-mr.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-390-mr.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-390-mr.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-390-mr.png
HP-414-en | F1/F2/F5/F6 | Home renders the discovery layout | 414px | en | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-414-en.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-414-en.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-414-en.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-414-en.png
HP-414-hi | F1/F2/F5/F6 | Home renders the discovery layout | 414px | hi | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-414-hi.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-414-hi.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-414-hi.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-414-hi.png
HP-414-mr | F1/F2/F5/F6 | Home renders the discovery layout | 414px | mr | guest | Pass | Pass | Not run | Pass | Pass | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-414-mr.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-414-mr.png Android: e2e-evidence/homepage-uiux/test.gokesari.com-app-android/HP-414-mr.png iOS: e2e-evidence/homepage-uiux/test.gokesari.com-app-ios/HP-414-mr.png
HP-768-en | F1/F2/F5/F6 | Home renders the discovery layout | 768px | en | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-768-en.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-768-en.png
HP-768-hi | F1/F2/F5/F6 | Home renders the discovery layout | 768px | hi | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-768-hi.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-768-hi.png
HP-768-mr | F1/F2/F5/F6 | Home renders the discovery layout | 768px | mr | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/HP-768-mr.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/HP-768-mr.png
REG-ROUTES | Regression | Existing routes (no 404/500) | HTTP | en | guest | Pass | Pass | Not run | Pass | Pass
REG-SITE-HEADER | F2/Regression | Site header on /shops | 1024px | en | guest | Pass | Pass | Not run | Not run | Not run | Local: e2e-evidence/homepage-uiux/localhost_3000/REG-SITE-HEADER.png Staging: e2e-evidence/homepage-uiux/test.gokesari.com/REG-SITE-HEADER.png

## Regression
Existing feature | How it was checked | Local | Staging | Production | Notes

## Defects
ID | Description | Severity | Environment found | Fix | Status
DEF-00 | Staging deploy of #214 blocked: the first migration on the split test site failed — migrate-on-build opened the seller DB with a Neon URL (channel_binding=require → 'unrecognized configuration parameter'), and the Test-database workflow's seller backup failed on the secret's trailing newline. | Blocker | Staging (deploy) | cleanDatabaseUrl() in the migration scripts; workflow trims the URL (PR #215); reproduced and verified on a local split layout | Fixed (PR #215)
DEF-01 | Header 'Deliver to' and cart scrolled away on every page — position: sticky disabled because body had overflow-x: hidden (scroll container). | High | Production (pre-existing), Local | overflow-x: clip with @supports fallback | Fixed
DEF-02 | Empty cart 'Your cart is empty / View cart' rendered twice on the home page (phone bar + wide panel both in the DOM). | Medium | Production (pre-existing) | Home no longer renders a cart-empty block; the cart page shows one illustrated empty state | Fixed
DEF-03 | Suggestion API 500 with no location: ORDER BY constant 0 read as a column position. | High | Local (new code) | Order by nearby count only when there are nearby shops; integration test added | Fixed
DEF-04 | Phone drawer and location sheet sat under the bottom navigation (sticky header's stacking context). | Medium | Local (new code) | Rendered through a portal to <body> | Fixed
DEF-05 | '1 shops' in suggestions. | Low | Local (new code) | Singular / plural labels | Fixed
DEF-06 | Double focus ring on the search field. | Low | Local (new code) | Field shows focus through its border | Fixed
DEF-07 | Carousel arrows covered the banner button at 360 px. | Low | Local (new code) | Arrows from 640 px; phones swipe; dots + pause stay | Fixed
DEF-08 | CSS minifier dropped the overflow-x 'hidden' fallback when 'clip' followed it. | Low | Local build | Fallback kept with @supports | Fixed
DEF-09 | Risk: iPhone app (≤ 1.2.0) could be closed by iOS if the page reached for the microphone (no NSMicrophoneUsageDescription). | High | Code review | Mic hidden in app builds before 1.3.0; 1.3.0 declares microphone and speech recognition | Fixed
DEF-10 | E2E acceptance 'offline-only' looked on the shop page's first category tab (stale since the 9 Oct tabs change). | Low | Local regression (pre-existing) | Test opens ?cat=Paneer | Fixed
DEF-11 | E2E regression 'business rules page' expected every rule editor on one page (stale since 9 Oct: searchable list). | Low | Local regression (pre-existing) | Test opens each rule's editor (?rule=<key>) | Fixed
DEF-12 | E2E regression C1 looks for the shop contact card on /shop; Seller Central moved it on 14 Oct, so the serial spec stops there. | Low | Local regression (pre-existing) | Not in this change's scope: the test should open the shop settings page — flows after it are covered by the integration suite | Open
DEF-13 | test.gokesari.com did not build #213–#215 (19 Oct 22:24 → 20 Oct 04:45 UTC): Hostinger's build stopped in migrate-on-build. Root cause (found from the Hostinger build log, PR #218): the test site's SELLER_DATABASE_URL opened a different database from the seller database the core's foreign tables read (its migration log ended at 0075), so the split migrator refused to go on. The test database itself was already migrated by the Test database workflow. | Blocker | Staging (deploy) | Hostinger's SELLER_DATABASE_URL corrected; #218 makes migrateSplit refuse a seller URL that is not the core's linked seller database (clear message, nothing touched). test.gokesari.com built staging c2b1018 (#214 + #215 + #218) at 04:47 UTC on 20 Oct. | Fixed (#218)
DEF-14 | gokesari.com has not deployed release #219 (merged 05:39 UTC) or #221 (06:15 UTC): at 06:49 UTC the site serves a build made at 06:02 UTC without the release (old home; /api/search/suggest and /admin/home-banners answer 404). The production databases already have 0086–0087 (run 39372089225) and are on the split layout. | Blocker | Production (deploy) | Outside the repository: the Hostinger build log for gokesari.com is not visible from this run. Most likely the same cause as DEF-13 on the test site — the build's migration step (since #218) stops when SELLER_DATABASE_URL is not the seller database the core's foreign tables read (production: the database named PROD_SELLER_DATABASE_URL). Owner: hPanel → gokesari.com → Deployments → latest build log; fix SELLER_DATABASE_URL if the log says so, then Redeploy → 'Settings and redeploy'. | Blocked

## Lighthouse
Environment | When | Page | Form factor | Performance | Accessibility | Best practices | SEO | Target (Perf ≥ 85, A11y ≥ 95) | Notes
Staging (test.gokesari.com) | Before (19 Oct, old home) | / | Mobile (Lighthouse 12, simulated throttling) | 98 | 100 | 100 | 100 | Pass | Measured from the build container while other jobs ran
Production (gokesari.com) | Before (19 Oct, old home) | / | Mobile (Lighthouse 12, simulated throttling) | 84 | 100 | 100 | 100 | Fail | Below the 85 target before this change
Local (production build) | After — run 1 | / | Mobile (Lighthouse 12, simulated throttling) | 99 | 100 | 100 | 100 | Pass | LCP 1.8 s, TBT 100 ms, CLS 0
Local (production build) | After — run 2 | / | Mobile (Lighthouse 12, simulated throttling) | 97 | 100 | 100 | 100 | Pass | LCP 2.3 s, TBT 120 ms, CLS 0
Staging (test.gokesari.com) | After — run 1 | / | Mobile (Lighthouse 12, simulated throttling) | 88 | 100 | 100 | 100 | Pass | LCP 2.4 s, TBT 310 ms, CLS 0
Staging (test.gokesari.com) | After — run 2 | / | Mobile (Lighthouse 12, simulated throttling) | 96 | 100 | 100 | 100 | Pass | LCP 2.3 s, TBT 50 ms, CLS 0

## Decisions
ID | Decision | Why | Where
D-01 | Work branched from staging (with main merged in, no content change) and goes branch → staging (test.gokesari.com) → main (gokesari.com). | The repo's documented promotion path (DEPLOYMENT.md §3, decision-log D-002). | branch claude/gifted-brahmagupta-nj0bt9
D-02 | The new home is behind rule homeDiscovery (on by default). Off restores the Tile Board home and hides the bottom navigation and floating cart bar. | Additive-only brief: an instant way back without a deploy (decision-log D-004). | src/server/config/rules.ts; src/app/page.tsx; src/app/layout.tsx
D-03 | Banners and search history are new platform tables in the core database (migration 0086, '-- split: core'); trigram indexes on products / shops are a seller migration (0087, '-- split: seller'). | CLAUDE.md two-database rules: classify every table; tags say where a migration runs; no FK between seller and customer tables. | drizzle/0086, 0087; src/server/db/split/ownership.ts
D-04 | Code tolerates the new tables being absent (no banners → built-in banners; searches not recorded). | Production migrates by hand; the code may go live before the migration runs. | home-banners.ts, search-suggest.ts
D-05 | New permission HOME_BANNER_MANAGE for admin and operator (not operator-limited). | Brief: 'Admin/operator can create, schedule, reorder…'. | src/server/authz/permissions.ts
D-06 | Trending = searches made at least twice in 7 days (anonymous for guests), topped up with fixed defaults (milk, bread, paneer, curd, eggs, atta) labelled in the visitor's language. | No search log existed; defaults keep the list useful on a new site. | src/server/services/search-suggest.ts
D-07 | Recent searches: account (server) for signed-in customers, this browser's localStorage for guests; only the normalised query text is stored. | Brief; data minimisation. | search_queries; search-box.tsx
D-08 | Search page records a search only on the first page of results (no ?page / ?view), after the response (next/server after()). | Pagination and tab switches are not new searches; never slows the page. | src/app/search/page.tsx
D-09 | Category suggestions come from the home category tiles (all three languages) and the 44 shop types → /shops?type=…, plus product categories → /search?q=…. | Hindi / Marathi typing finds categories although product names are English. | matchCategories()
D-10 | Voice search hidden inside app builds before 1.3.0 and wherever the browser lacks the Web Speech API (e.g. Android WebView). | iOS terminates an app that uses the microphone without NSMicrophoneUsageDescription; 1.3.0 adds it. | src/lib/mobile-app.ts; mobile/app.config.ts
D-11 | 'Compare N prices' for a single product works whatever rule homePriceComparison says; the general compare list still follows the rule. | It is the same comparison the product page already offers; the brief requires the link. | src/server/services/price-comparison.ts
D-12 | 'Popular in your area' = most-ordered listings (paid, not cancelled) in 60 days at shops serving the location → their city → platform → products on sale nearby; one card per product. | Brief's fallback chain; the last step keeps the grid useful on a new site. | src/server/services/home-discovery.ts
D-13 | Homepage shows no 'Do now' / tracking strip; an active order is one tap away (bottom nav Orders, Account → Tracking). | Brief: 'Homepage becomes product discovery only'. | home-page.tsx
D-14 | Bottom navigation and floating cart bar appear on the shopping pages only (home, categories, shops, search, products, the customer's own pages) — not in Seller Central, admin, operator, rider, sign-in, cart/checkout or payment return. | Those screens have their own bottom actions; avoids covering checkout buttons. | src/components/home/mobile-shop-nav.tsx
D-15 | Bottom nav 'Account' opens /profile (signed in) or /signin (guest); the full grouped account menu is in the ☰ drawer. | One tap to the profile; the drawer holds everything else. | mobile-shop-nav.tsx
D-16 | Site-wide CSS: html/body overflow-x 'clip' (with 'hidden' fallback via @supports) instead of 'hidden'. | 'hidden' made <body> a scroll container, which disabled every sticky header — the cause of 'not sticky on mobile'. | src/app/globals.css
D-17 | Footer 'Help' links to /support (help desk; asks guests to sign in). | Brief lists Help separately from Contact Us; /support is the help portal. | src/components/site-footer.tsx
D-18 | Old compact footer test replaced by the organised-footer checks. | The brief replaces the compact two-row footer with labelled columns. | tests/e2e/branding-footer.spec.ts
D-19 | Only one theme exists ('Theme 1 Tile Board'); new components use its CSS tokens (--gk-bg, --gk-line, kesari palette). | No theme switcher exists to test against. | src/app/globals.css
D-20 | Product card 'Compare N prices' wording is English like the rest of that card (the card has no language prop); home tiles are translated. | Keeps the card consistent; translation of the whole card is a separate change. | src/components/product-card.tsx
D-21 | Android / iOS 'run on emulator/simulator' replaced by Playwright emulation of the app WebView (app user agent, touch, phone widths) plus Expo bundles for both platforms; APK built by the repo's 'Android APK' workflow on the PR. | This environment has no Android SDK / KVM and no macOS; the app is a WebView shell, so the website checks are what the app shows. | tests/e2e/homepage-uiux.spec.ts (E2E_APP)
D-22 | Lighthouse run from this container (mobile preset, simulated throttling) with a temporary install in the session scratchpad — not a project or global dependency. | Brief: no new global tools. | scratchpad
D-23 | Staging and production tests are guest-only (production-safe: GETs, browser cookies; search submit intercepted on production). Signed-in flows run locally. | Remote sign-in needs an emailed OTP from a mailbox this run cannot read; brief: production read-only. | tests/e2e/homepage-uiux.spec.ts
D-24 | Report date uses India time (APP_TIMEZONE Asia/Kolkata). | The owner's date. | reports/
D-25 | Fixed the split-site migration path (PR #215) rather than migrating staging by hand. | Every future migration on a split site would hit it; the documented path (Test database workflow + Hostinger MIGRATE_ON_BUILD) stays the only way schema changes reach the sites. | scripts/split-migrate.mjs; scripts/migrate-on-build.mjs; src/server/db/migrate.ts; .github/workflows/test-db.yml
D-26 | Staging not rebuilt after 55 min → recorded as a blocker and production held until staging passed. | The brief allows the next environment only after the previous one passes. | docs/homepage-uiux-2026-10/run-log.json
D-27 | Release checked against the two-database rules before it went further (owner request, 20 Oct): new tables classified (platform), migration tags (0086 core, 0087 seller), no seller↔customer foreign key, no writes to seller tables, no ON CONFLICT / session settings, the only transaction (banner order) touches core only with the audit after commit, no query joins seller and customer tables. CI test-split green on #214, #218 and the release. | CLAUDE.md 'Two databases' rules. | src/server/services/*; drizzle/0086, 0087; src/server/db/split/ownership.ts
D-28 | Signed-in checks on staging not run: reading the sign-in code from the test accounts' mailbox (Gmail connector) to sign in was refused by this session's permission check; not worked around. | Owner decides whether this run may sign in to the staging test accounts. | tests/e2e/homepage-uiux.spec.ts ('signed in' group, local only)