## Summary
GoKesari feature status - 6 Oct 2026
Your workbook (Gokesari_Complete_Features_and_Workflows.xlsx: 148 rows + flow diagram) compared with the code on main @579fd42 (6 Oct 2026). Status is development status from code and tests, not QA sign-off.
Checked on main @579fd42 (6 Oct 2026), fresh PostgreSQL 16 with migrations 0000-0050 applied: typecheck clean, lint 0 errors (4 unused-variable warnings), 1152/1152 tests passed in 83 files (vitest).
Buckets: COMPLETED = built and merged to main (some behind a business rule that is off by default - see 'Switched on?'); IN PROGRESS = partly built, remaining work needs no one else; BLOCKED = remaining work waits on a decision, vendor or another feature; YET TO START = no code. A row stays COMPLETED when its only gap is tracked by another open row (named in 'Remaining scope / caveat').
Headline | 3 Oct | 6 Oct (now) | Change
Total features tracked | 157 | 158 | 1
COMPLETED | 132 | 143 | 11
IN PROGRESS | 23 | 4 | -19
BLOCKED | 0 | 10 | 10
YET TO START | 1 | 1 | 0
UNCLEAR | 1 | 0 | -1
% complete | 84.08% | 90.51% | 6.43%
3 Oct column is counted from the 'Status 3 Oct' column (source: GOKESARI_FEATURE_STATUS_REPORT_2026-10-03.xlsx); NEW-010 has no 3 Oct status.
Section | Total | COMPLETED | IN PROGRESS | BLOCKED | YET TO START | % complete
Feature Master | 74 | 68 | 1 | 5 | 0 | 91.89%
Workflow Master | 10 | 9 | 0 | 1 | 0 | 90%
RBAC Matrix | 15 | 14 | 0 | 1 | 0 | 93.33%
State Machines | 6 | 2 | 2 | 2 | 0 | 33.33%
Gig Assignment Rules | 9 | 8 | 1 | 0 | 0 | 88.89%
Navigation | 19 | 18 | 0 | 1 | 0 | 94.74%
KPIs | 15 | 15 | 0 | 0 | 0 | 100%
Added after the target workbook | 10 | 9 | 0 | 0 | 1 | 90%
TOTAL | 158 | 143 | 4 | 10 | 1 | 90.51%
Your flow diagram | Steps
COMPLETED | 44
IN PROGRESS | 1
BLOCKED | 3
YET TO START | 0
Total steps | 48

## Flow diagram status
Your flow diagram, step by step, against the build
Status is the weakest part a step needs; 'What works' says what a user can do today.
# | Box in your diagram | Step | Status 6 Oct | Feature IDs | What works in the build | Gap
1 | Customer | Location / Society | COMPLETED | GS-004, GS-005 | Saved address, device position or PIN; address linked to a registered society. | -
2 | Customer | Search shop or product | COMPLETED | GS-019, GS-020, GS-021 | Shops that deliver here, nearest first; product search limited to serviceable shops; every shop selling a product. | -
3 | Customer | Compare local + online prices | BLOCKED | GS-022, NAV-001, GS-023 | Local comparison per unit / pack with lowest price; home-page comparison (F9, off by default). | Online (e-commerce) prices hidden from customers until D7 - licensed source - is decided.
4 | Customer | Cart / Subscription | COMPLETED | GS-024, GS-025, GS-048, GS-049, NAV-003 | Single and multi-shop cart; coupons (F7) and shop offers (F8) off by default; milk and daily-goods subscriptions. | -
5 | Customer | Payment | BLOCKED | GS-028, GS-029, GS-030 | Wallet (topped up through Cashfree UPI / card / netbanking) and COD with risk limits. | No per-order UPI / card / netbanking payment - waits on the go-ahead (GS-028 / NEW-007).
6 | Order engine | Validate stock + service area | COMPLETED | GS-026, GS-016 | Checkout hard-blocks non-serviceable shops, out-of-stock lines, paused shops and minimum order. | -
7 | Order engine | Split order by shop | COMPLETED | GS-033, GS-025 | One order per shop; one parent GK- reference for the checkout (F6, off by default). | -
8 | Order engine | Confirm payment | BLOCKED | GS-028, SM-005 | Wallet debit or COD confirmed inside the order transaction, idempotent. | Gateway confirmation and the payment state machine wait on GS-028.
9 | Order engine | Create fulfillment tasks | COMPLETED | GS-032, WF-002 | Shop order created and the shop notified. | -
10 | Shop owner | Receive order | COMPLETED | GS-055, NAV-008 | In-app + email notice; orders board. | SMS / WhatsApp alerts wait on D2.
11 | Shop owner | Accept / reject / substitute | COMPLETED | GS-034, GS-035 | Accept, reject (full refund + restock), substitution with customer approval; late acceptance flagged to ops. | Auto-cancel on accept timeout is part of NEW-007 (yet to start).
12 | Shop owner | Pick + pack | COMPLETED | GS-036 | Per-line picking and packing. | -
13 | Shop owner | Mark READY | COMPLETED | GA-006 | READY triggers rider search automatically. | -
14 | Gig assignment | Check society authorization | COMPLETED | GA-001, GS-045 | Society whitelist honoured (exclusive or priority per society). | -
15 | Gig assignment | Priority partner rules | COMPLETED | GA-002, GS-040 | Preferred riders ranked higher. | -
16 | Gig assignment | Distance / ETA / load | IN PROGRESS | GA-003, GS-072, GA-005 | Distance + reliability + fairness ranking; road ETA (F4) and busy-rider ranking (F3) built, off by default. | Multi-order batching not built.
17 | Gig assignment | Assign / broadcast | COMPLETED | GS-039, GA-009 | Offer to the best rider, 2-min expiry, cron retries, ops can intervene. | Sequential offers, not a broadcast; no radius widening.
18 | Delivery partner | Accept job | COMPLETED | NAV-011 | Jobs screen: available, active, history. | -
19 | Delivery partner | Pickup OTP / QR | COMPLETED | GS-041 | Pickup code required at handover. | Code only - no QR.
20 | Delivery partner | Navigate | COMPLETED | GS-072 | Google Maps deep link; road ETA on the rider dashboard (F4, off by default). | No in-app turn-by-turn.
21 | Delivery partner | Society access | COMPLETED | GS-047, GS-046 | Gate / parking instructions; security notified of the assigned rider. | -
22 | Delivery partner | Customer OTP / POD | COMPLETED | GS-043 | Delivery OTP (5 attempts), ops override with a proof note, arrival checkpoints. | Photo / signature POD is part of NEW-007 (yet to start).
23 | Society | Whitelist / revoke Gig workers | COMPLETED | GS-045, RBAC-009 | Society admin approves / revokes riders, effective immediately, audited. | -
24 | Society | Delivery instructions | COMPLETED | GS-047 | Shown to the assigned rider only. | -
25 | Society | Security notification | COMPLETED | GS-046 | Configurable per society. | -
26 | Society | Priority zone rules | COMPLETED | GS-040, GA-001 | Society priority in rider ranking. | -
27 | Post-order | Delivered / failed / returned | COMPLETED | SM-001 | Full order state machine with history and audit. | -
28 | Post-order | Refund / replacement | COMPLETED | GS-057, WF-007 | Returns, return pickups, refunds, replacement. | Refunds go to the wallet; card / UPI refunds wait on GS-073.
29 | Post-order | Ratings + support | COMPLETED | GS-059, GS-060, GS-056, GS-058 | Shop and rider ratings with moderation; issues, grievances, dispute cases with escalation. | -
30 | Post-order | Shop settlement + Gig payout | COMPLETED | GS-062, GS-064, WF-010 | Weekly settlements and payouts with reconciliation. | Bank transfer is manual.
31 | Subscription engine | Milk / vegetables / daily goods | COMPLETED | GS-048, GS-049 | Daily and weekday schedules. | -
32 | Subscription engine | Schedule | COMPLETED | GS-051 | Skip / pause / resume / cancel with cutoffs. | Extra lifecycle stages (SM-004) in progress.
33 | Subscription engine | Auto-create order | COMPLETED | WF-006 | Daily generation, idempotent per subscription and date. | -
34 | Subscription engine | Payment | COMPLETED | GS-050 | Charged from the wallet; PAYMENT_PENDING when short. | -
35 | Subscription engine | Fulfillment + delivery | COMPLETED | WF-006 | Generated orders go through the normal shop and rider flow. | -
36 | Admin / operations | KYC + shop approval | COMPLETED | GS-007, GS-008, WF-008 | Seller document verification with admin queue; fee gate before approval. | Runs on the mock vendor until Gridlines keys are set.
37 | Admin / operations | Product master | COMPLETED | GS-011, NEW-008 | Product master and category master. | -
38 | Admin / operations | Payments / reconciliation | COMPLETED | GS-031 | Reconciliation with exception queue. | -
39 | Admin / operations | Disputes / refunds | COMPLETED | GS-058, GS-057, RBAC-011 | Dispute queue with auto-escalation; refund approval. | -
40 | Admin / operations | RBAC + audit | COMPLETED | GS-002, GS-067, GS-071 | Role and scope permissions; append-only audit log. | RBAC-003 (operator 'Limited' shop management) waits on a definition.
41 | Admin / operations | Analytics / controls | COMPLETED | GS-069, KPI-001..015, GS-068, NEW-001 | KPI dashboards, risk rules, business-rules console. | -
42 | Marketplace data | Product master | COMPLETED | GS-011 | Canonical products (GTIN / HSN / GST / brand / pack). | -
43 | Marketplace data | Shop catalog | COMPLETED | GS-012, NEW-010 | Shop listings with own price and stock; category fill. | -
44 | Marketplace data | Inventory | COMPLETED | GS-016, GS-017 | Stock and low-stock thresholds. | -
45 | Marketplace data | Price history | COMPLETED | GS-015 | product_price_history and an immutable MRP trail. | -
46 | Marketplace data | Customer consent | COMPLETED | GS-070 | Consent history and admin consent view. | -
47 | Marketplace data | Orders / ledger | COMPLETED | GS-032, GS-029 | Orders, wallet ledger, finance snapshot on delivery. | -
48 | Marketplace data | Analytics | COMPLETED | GS-069 | KPI suite. | -
Flow steps by status
| COMPLETED | 44
| IN PROGRESS | 1
| BLOCKED | 3
| YET TO START | 0
| Total | 48

## All features
Seq | Section (your workbook) | ID | Module / portal | Feature | Priority | Phase | Requirement (your workbook) | Rule / note (your workbook) | Status 3 Oct | Status 6 Oct | Change since 3 Oct | Switched on? | What is built (checked in code, 6 Oct) | Remaining scope / caveat | Blocked on | Evidence (file)
1 | Feature Master | GS-001 | Identity & Access | Mobile/email/Gmail login | P0 | MVP | Secure registration and authentication. (Roles: Customer, Shop, Gig, Operator, Admin, Society) | RBAC mandatory. | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Live (email OTP); SMS OTP not available | Google, email magic link and a single mobile-or-email form; first-time /onboarding profile; My Profile with verified email change; checkout requires a mobile; admin can release a wrongly claimed number. Login rebuild now on main (was staging-only on 3 Oct). | SMS delivery of the OTP so a mobile number is proven (OTP provider seam ready). | D2 - SMS/OTP vendor with DLT registration | src/server/otp/providers.ts; src/app/onboarding; src/app/profile; drizzle/0038_login_profile.sql
2 | Feature Master | GS-002 | Identity & Access | Role-based access control | P0 | MVP | Permissions by role and scope. (Roles: All roles) | Least privilege. | COMPLETED | COMPLETED | No change | Live | SOCIETY_ADMIN role; society roles scoped per membership (ADMIN/OPERATOR/RESIDENT) | - | - | src/server/authz/permissions.ts; src/server/db/schema.ts (userRoleEnum)
3 | Feature Master | GS-003 | Identity & Access | Multi-role user account | P1 | Phase 2 | Allow approved users to hold multiple roles. (Roles: All) | Separate approval per role. | COMPLETED | COMPLETED | No change | Live | user_role_grants; active role switcher in the header; /api/me/roles; admin revoke; shop/rider/society flows grant roles; staff roles exclusive | - | - | src/server/services/roles.ts; src/app/api/me/roles/route.ts
4 | Feature Master | GS-004 | Location | PIN / address selection | P0 | MVP | Select delivery address and service area. (Roles: Customer) | Use address geocoding. | COMPLETED | COMPLETED | No change | Live | 'Deliver to' location: saved address, device position or PIN, remembered in a cookie. Phase B added Maps Places address search, a 'save this place' path, and recipient name / recipient mobile / Home-Work-Other on addresses | - | - | src/lib/geo/provider.ts; src/components/location-bar.tsx; drizzle/0026
5 | Feature Master | GS-005 | Location | Society identification | P0 | MVP | Associate address with registered society. (Roles: Customer, Society) | Society rules apply. | COMPLETED | COMPLETED | No change | Live | Society membership; address <-> society link; orders.society_id | - | - | src/server/services/societies.ts
6 | Feature Master | GS-006 | Shop Onboarding | Shop registration | P0 | MVP | Create shop profile, category, owner and location. (Roles: Shop, Operator) | Operator approval before live. | COMPLETED | COMPLETED | No change | Live | - | 6 Oct: GST field added at registration; at least one of PAN / Udyam / GST / Shop Act required (135f29a). | - | -
7 | Feature Master | GS-007 | Shop Onboarding | Business KYC | P0 | MVP | Collect GST/PAN/license and required documents. (Roles: Shop, Operator, Admin) | Verification status tracked. | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Live; vendor checks run on the MOCK vendor until Gridlines keys are set (KYC_PROVIDER) | Seller verification Parts 1-4: PAN, GSTIN, Udyam, FSSAI and Shop Act per shop with document upload, vendor check (provider-agnostic, Gridlines adapter + mock), name matching, cross-document consistency score, per-document status, admin review queue (approve / reject with reason / re-check), daily re-check and expiry job, auto-suspend on lapse, DPDP retention/erasure. | Real vendor: Gridlines sandbox then live keys and written confirmation of response fields, Shop Act coverage, prices, DPA. By design, verification informs shop approval but does not block it. | - | src/server/services/seller-verification*.ts; src/server/kyc/; /shop/verification; /admin/seller-verification; drizzle/0040, 0041; docs/seller-verification/
8 | Feature Master | GS-008 | Shop Onboarding | Payment reference verification | P0 | MVP | Verify onboarding/subscription payment and authorize shop. (Roles: Operator) | Audit every action. | COMPLETED | COMPLETED | No change | Live | approveShop() now refuses unless fee_payment_status = PAID (derived from the shop_payments ledger), naming the amount outstanding; waived fee (zero snapshot) is written PAID at registration; approval queue shows each pending shop's fee state. Gate is on the transition only - shops already APPROVED untouched | - | - | src/server/services/shops.ts (approveShop); src/components/shop-approval-panel.tsx; tests/integration/registration-fees.test.ts
9 | Feature Master | GS-009 | Shop Onboarding | Shop categories | P0 | MVP | Support grocery, dairy, pharmacy, clothing, electronics, repair, etc. (Roles: Admin, Operator) | Configurable category master. | COMPLETED | COMPLETED | No change | Live | Admin-configurable category master: shop_categories + shop_category_mapping (many per shop), seeded from the 44 shop types and backfilled; registration requires at least one category; owners edit their own on /shop; operators/admins manage the list at /admin/shop-categories and assign per shop; uncategorised shops flagged; categories feed search relevance | - | - | src/server/services/shop-categories.ts; src/app/admin/shop-categories/page.tsx; drizzle/0035
10 | Feature Master | GS-010 | Shop Onboarding | Service radius / delivery zone | P0 | MVP | Define where shop can serve customers. (Roles: Shop, Operator) | Geospatial validation. | COMPLETED | COMPLETED | No change | Live | shops.service_radius_km (1-50 km) editable by the shop; Phase B added extra delivery zones by PIN code (shops.delivery_pincodes), honoured by serviceability, checkout and discovery | - | - | src/server/services/serviceability.ts; src/server/db/schema.ts:691; drizzle/0019, 0026
11 | Feature Master | GS-011 | Catalog | Product master | P0 | MVP | Central product catalog with SKU/GTIN/HSN/GST/brand/pack size. (Roles: Admin, Operator) | One canonical product identity. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
12 | Feature Master | GS-012 | Catalog | Shop catalog mapping | P0 | MVP | Map products to shop-specific price, stock and availability. (Roles: Shop, Operator) | Shop-specific sellable SKU. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
13 | Feature Master | GS-013 | Catalog | Bulk product upload | P0 | MVP | CSV/Excel upload with validation. (Roles: Shop, Operator) | Error report + retry. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
14 | Feature Master | GS-014 | Catalog | Product images/specifications | P1 | MVP | Manage images, descriptions and attributes. (Roles: Shop, Operator) | Moderation rules. | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: imageModeration.enabled) | Image store with several images per product/listing, primary, reorder, alt text; F10 moderation queue (pending -> approve / reject with reason) at /admin/image-moderation; existing photos stay live. | - | - | src/server/services/product-images.ts; drizzle/0049_image_moderation.sql; tests/integration/image-moderation.test.ts
15 | Feature Master | GS-015 | Catalog | MRP / selling price / discount | P0 | MVP | Maintain MRP and shop selling price. (Roles: Shop) | Prevent invalid discount display. | COMPLETED | COMPLETED | No change | Live | MRP governance: a selling price above an enforced MRP is refused everywhere a shop price is written (assertPriceWithinMrp on both catalogue write paths); MRP provenance and verification status; MRP drops notify shops without touching prices; shop MRP corrections decided by operations; violations report; MRP shown on the product page | - | - | src/server/services/mrp-governance.ts; src/server/services/catalogue.ts:617,710; src/app/admin/mrp/page.tsx; drizzle/0032
16 | Feature Master | GS-016 | Inventory | Stock quantity | P0 | MVP | Update available quantity. (Roles: Shop, Operator) | Real-time or near-real-time. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
17 | Feature Master | GS-017 | Inventory | Low-stock threshold | P1 | MVP | Alert when stock falls below threshold. (Roles: Shop) | Configurable per SKU. | COMPLETED | COMPLETED | No change | Live | Extended by GS-018 (three-level thresholds, Phase I) | - | - | -
18 | Feature Master | GS-018 | Inventory | Reorder level / quantity | P1 | Phase 2 | Suggest replenishment. (Roles: Shop) | Analytics-driven. | COMPLETED | COMPLETED | No change | Live | Low-stock threshold, reorder level and reorder quantity resolved at listing -> product -> shop level with an explicit opt-out and the source reported; reserved / available / on-hand; one notification per new alert; hand-edited stock now writes the ledger and re-checks alerts | Analytics-driven replenishment suggestions (enhancement) | - | src/server/services/inventory-alerts.ts; src/app/shop/inventory/page.tsx; drizzle/0033
19 | Feature Master | GS-019 | Search | Shop search | P0 | MVP | Search shops by name/category/location. (Roles: Customer) | Distance filter. | COMPLETED | COMPLETED | No change | Live | Shops that deliver to the location, nearest first, with distance | - | - | src/server/services/serviceability.ts
20 | Feature Master | GS-020 | Search | Product search | P0 | MVP | Search product across nearby shops. (Roles: Customer) | Product-centric discovery. | COMPLETED | COMPLETED | No change | Live | Product search limited to serviceable shops, nearest first | - | - | src/app/search/page.tsx; src/server/services/catalogue.ts
21 | Feature Master | GS-021 | Search | All shops selling product | P0 | MVP | Show same product across eligible local shops. (Roles: Customer) | Availability + distance. | COMPLETED | COMPLETED | No change | Live | /products/{id}: every shop selling the product | - | - | src/app/products/[id]/page.tsx
22 | Feature Master | GS-022 | Comparison | Local price comparison | P0 | MVP | Compare same product among local shops. (Roles: Customer) | Normalize pack/unit. | COMPLETED | COMPLETED | No change | Live | Per-unit / per-pack comparison, 'Lowest price', delivers-to-you | - | - | src/app/products/[id]/page.tsx
23 | Feature Master | GS-023 | Comparison | E-commerce price benchmark | P1 | Phase 2 | Show external online price where legally/technically available. (Roles: Customer) | Label source and timestamp. | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Hidden from customers (externalPrices.showToCustomers = false) | External reference prices with source, time, location, URL, verification and audit history; shops and operations see them. | Turn on the customer display - one rule flip, no code. | D7 - lawful / licensed price source | src/server/config/rules.ts (externalPrices)
24 | Feature Master | GS-024 | Cart | Single-shop cart | P0 | MVP | Build cart from one shop. (Roles: Customer) | Simple fulfillment. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
25 | Feature Master | GS-025 | Cart | Multi-shop cart | P1 | Phase 2 | Allow multiple shops and split into child orders. (Roles: Customer) | Separate fulfillment. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
26 | Feature Master | GS-026 | Checkout | Address validation | P0 | MVP | Validate serviceability before payment. (Roles: Customer) | Hard block if unavailable. | COMPLETED | COMPLETED | No change | Live | Cart warning, then a checkout hard block when a shop does not deliver to the address. Phase B added a cart-validation service that re-checks every shop in the cart against the chosen location - deliverable, paused, unavailable items, minimum order, delivery charge, closed-now - each with an action, re-running when the address changes | - | - | src/server/services/cart-validation.ts; src/app/api/cart/validate/route.ts
27 | Feature Master | GS-027 | Checkout | Delivery slot | P0 | MVP | Immediate or scheduled delivery. (Roles: Customer) | Slot capacity rules. | IN PROGRESS | IN PROGRESS | Progressed, same status | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: deliverySlots.enabled) | EXPRESS_30 / STANDARD_60 / SCHEDULED windows with feasibility preview, plus F5 slot capacity per shop / PIN code / default with an advisory lock so a slot cannot be overbooked (full slots shown unavailable). | Customer cannot pick a date or time for a scheduled delivery - a scheduled order is booked against the day it is placed. | - | src/server/services/delivery-slots.ts; drizzle/0045_delivery_slots.sql; tests/integration/delivery-slots.test.ts
28 | Feature Master | GS-028 | Payments | UPI/card/netbanking gateway | P0 | MVP | Secure online payment. (Roles: Customer) | Gateway webhook reconciliation. | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Live | Cashfree live for wallet top-up only (create order, server verify, HMAC webhook, mock mode). Orders are paid by WALLET or COD; payment_method enum is still WALLET ¦ COD. | Per-order ONLINE payment via Cashfree hosted checkout (design signed off 1 Oct). | Go-ahead to build per-order payment, or a decision to launch wallet + COD only | src/server/db/schema.ts:197 (paymentMethodEnum); src/server/services/payments.ts
29 | Feature Master | GS-029 | Payments | Wallet | P1 | Phase 2 | Wallet top-up and usage. (Roles: Customer) | Ledger based. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
30 | Feature Master | GS-030 | Payments | COD | P1 | Phase 2 | Optional cash-on-delivery with configurable rules. (Roles: Customer, Shop) | Risk limits. | COMPLETED | COMPLETED | No change | Live | COD at checkout with risk limits; shop opt-in; rider/operator cash confirmation; collection nets into finance batches; deposits at /admin/cod; COD refunds as wallet credit | - | - | src/server/services/cod.ts; src/app/admin/cod/page.tsx
31 | Feature Master | GS-031 | Payments | Payment reconciliation | P0 | MVP | Match gateway transactions to orders. (Roles: Operator, Admin) | Exception queue. | COMPLETED | COMPLETED | No change | Live | Reconciliation records + exception queue (order/payment/rider/settlement/payout) | Reconciles the gateway transactions that exist today (wallet top-ups). | - | src/app/api/finance/reconciliation/route.ts; src/server/services/finance.ts
32 | Feature Master | GS-032 | Orders | Order creation | P0 | MVP | Create order after checkout. (Roles: Customer) | Idempotent order creation. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
33 | Feature Master | GS-033 | Orders | Shop order split | P0 | MVP | Create shop-specific fulfillment order(s). (Roles: System, Shop) | Master + child order model. | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: parentOrders.enabled) | One order per shop from a multi-shop cart, plus F6 parent reference (GK-...) linking them; customer page /orders/group/[reference]. | - | - | src/server/services/order-groups.ts; drizzle/0046_order_groups.sql; tests/integration/order-groups.test.ts
34 | Feature Master | GS-034 | Orders | Shop accept/reject | P0 | MVP | Confirm order and availability. (Roles: Shop) | Timeout escalation. | COMPLETED | COMPLETED | No change | Live | Shop accept / reject (reject = full refund + restock); ops exceptions flag 'Shop not accepting' and 'Shop slow to prepare' | Accept-timeout auto-cancel (designed 1 Oct, not built) Late acceptance is flagged in the ops exceptions queue; auto-cancel on timeout is part of NEW-007 (yet to start). | - | src/server/services/fulfilment.ts; src/server/services/ops-exceptions.ts
35 | Feature Master | GS-035 | Orders | Substitution approval | P1 | MVP | Allow replacement for unavailable items. (Roles: Customer, Shop) | Customer preference configurable. | COMPLETED | COMPLETED | No change | Live | Shop proposes a substitute; customer approves/rejects; price difference refunded | - | - | src/app/api/orders/[id]/items/[itemId]/substitution/route.ts
36 | Feature Master | GS-036 | Orders | Pick and pack | P0 | MVP | Prepare order and mark ready. (Roles: Shop) | SLA tracking. | COMPLETED | COMPLETED | No change | Live | Per-line picking, pack -> READY | SLA reporting SLA measured by the pick-pack KPI; SLA reporting per shop is part of NEW-007. | - | src/server/services/fulfilment.ts
37 | Feature Master | GS-037 | Delivery | Gig worker onboarding | P0 | MVP | KYC, vehicle and bank details. (Roles: Gig, Operator) | Approval workflow. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
38 | Feature Master | GS-038 | Delivery | Online/offline status | P0 | MVP | Worker controls availability. (Roles: Gig) | Location only when required/consented. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
39 | Feature Master | GS-039 | Delivery | Job assignment | P0 | MVP | Assign delivery after shop ready. (Roles: System, Gig) | Rules engine. | COMPLETED | COMPLETED | No change | Live | Auto-trigger on READY; cron retry; no re-offer to decliners; Phase C made the whole search bounded and logged (rider_searches, dispatch_attempts) with admin-tunable retry interval, attempt cap and time limit | - | - | src/server/services/delivery-assignment.ts; drizzle/0027
40 | Feature Master | GS-040 | Delivery | Society priority assignment | P0 | MVP | Prefer authorized workers for specific society. (Roles: System, Gig, Society) | Priority ≠ exclusive unless society config says so. | COMPLETED | COMPLETED | No change | Live | Society preference in dispatch ranking | - | - | src/server/services/delivery-assignment.ts:123
41 | Feature Master | GS-041 | Delivery | Pickup OTP/QR | P0 | MVP | Validate handover. (Roles: Shop, Gig) | Audit timestamp. | COMPLETED | COMPLETED | No change | Live | Pickup code issued on accept; rider must enter it | QR variant Pickup code only - no QR. | - | src/server/services/delivery-assignment.ts
42 | Feature Master | GS-042 | Delivery | Live tracking | P0 | MVP | Track active delivery. (Roles: Customer, Gig, Admin) | Privacy-aware location sharing. | COMPLETED | COMPLETED | No change | Live | Tracking API with role/privacy checks + polling LiveTrackingMap, now MOUNTED: on /orders inside an in-flight order card that has a rider, and on /admin/orders behind a per-row Track toggle. isTrackableOrderStatus() limits polling to orders actually in flight. Rider privacy: area only until pickup, no ETA from a stale fix | - | - | src/app/orders/page.tsx:199; src/components/order-monitoring-table.tsx:171; src/lib/tracking.ts; tests/unit/tracking.test.ts
43 | Feature Master | GS-043 | Delivery | Delivery OTP/POD | P0 | MVP | Confirm successful delivery. (Roles: Customer, Gig) | Photo/signature optional. | COMPLETED | COMPLETED | No change | Live | Customer delivery OTP (5 attempts); operations override with a proof note; 'Delivery code locked' is an ops exception | Photo / signature proof of delivery (designed 1 Oct, not built) Delivery OTP with ops override; photo POD (optional in your table) is part of NEW-007. | - | src/server/services/delivery-assignment.ts; docs/gokesari-audit/DESIGN_PAYMENTS_INVOICING_POD_SLA.md
44 | Feature Master | GS-044 | Society | Society registration | P1 | MVP | Create society profile and service rules. (Roles: Society, Operator) | Verified society admin. | COMPLETED | COMPLETED | No change | Live | Registration -> operator verify/reject/suspend/reinstate | Map pin picker on the society form | - | src/app/api/societies/[id]/decision/route.ts
45 | Feature Master | GS-045 | Society | Authorized Gig worker whitelist | P0 | MVP | Approve/revoke specific workers. (Roles: Society) | Effective immediately with audit. | COMPLETED | COMPLETED | No change | Live | Authorised rider list by mobile; add / revoke / preferred; audited | - | - | src/app/api/societies/[id]/riders/route.ts
46 | Feature Master | GS-046 | Society | Security notification | P1 | Phase 2 | Notify security of assigned worker/order. (Roles: Society, Gig) | Configurable. | COMPLETED | COMPLETED | No change | Live | Society security alert on rider acceptance (opt-in) | - | - | src/server/services/societies.ts
47 | Feature Master | GS-047 | Society | Delivery instructions | P1 | MVP | Gate/parking/access instructions. (Roles: Society, Customer) | Do not expose sensitive notes unnecessarily. | COMPLETED | COMPLETED | No change | Live | Society gate notes + customer landmark/instructions on the rider job; Phase C added a gate entry mode, an optional security-desk contact shared with the rider only if the society enables it, and a customer-at-gate notice | - | - | drizzle/0027; src/server/services/societies.ts
48 | Feature Master | GS-048 | Subscription | Daily milk subscription | P0 | MVP | Recurring milk order. (Roles: Customer, Shop) | Skip/pause/resume. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
49 | Feature Master | GS-049 | Subscription | Recurring vegetables/daily goods | P1 | Phase 2 | Recurring schedule and quantity. (Roles: Customer, Shop) | Generate order before cutoff. | COMPLETED | COMPLETED | No change | Live | Weekday schedules; generated orders carry address/society | - | - | src/server/services/subscriptions.ts
50 | Feature Master | GS-050 | Subscription | Subscription payment | P0 | MVP | Charge per cycle or wallet. (Roles: Customer, System) | Failed payment retry. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
51 | Feature Master | GS-051 | Subscription | Skip/pause/resume/cancel | P0 | MVP | Manage recurring service. (Roles: Customer) | Cutoff rules. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
52 | Feature Master | GS-052 | Marketing | Customer segmentation | P1 | Phase 2 | Filter by locality, prior purchase, consent. (Roles: Shop, Operator) | Consent required. | COMPLETED | COMPLETED | No change | Live | Segments by PIN, society, delivered orders, recency, lapse, spend; consent required; counts only | - | - | src/server/services/marketing.ts:89
53 | Feature Master | GS-053 | Marketing | Shop promotional campaigns | P1 | Phase 2 | Discounts, vouchers and campaigns. (Roles: Shop) | Budget/rate limits. | COMPLETED | COMPLETED | No change | Live | Shop campaigns with budget, shop rate limit and customer frequency caps | - | - | src/server/services/marketing.ts
54 | Feature Master | GS-054 | Marketing | Referral program | P1 | Phase 2 | Referral codes and rewards. (Roles: Shop, Customer) | Fraud checks. | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: customerReferrals.enabled; rewards Rs 50 / Rs 50) | Shop referral attribution, plus F11 customer referral code and link (/refer, /r/CODE): both rewarded on the friend's first delivered order; self-referral, duplicate-account and per-referrer cap guards; /admin/customer-referrals. | - | - | src/server/services/customer-referrals.ts; drizzle/0050_customer_referrals.sql; tests/integration/customer-referrals.test.ts
55 | Feature Master | GS-055 | Notifications | Order notifications | P0 | MVP | Push/SMS/email/WhatsApp where available. (Roles: Customer, Shop, Gig) | Event driven. | COMPLETED | COMPLETED | No change | Live | Notification framework: in-app + email, queued per channel with retries and backoff, delivery log, dead-letter handling, per-category preferences (security notices always on), read/unread, and templates for every order, return, delivery, shop, wallet, subscription, society and security event. Sent by a one-minute cron | Email + in-app; SMS / WhatsApp / push wait on GS-074 (blocked). | - | src/server/notifications/{channels,templates,types}.ts; src/server/services/notifications.ts; src/app/api/cron/notifications/route.ts; drizzle/0030
56 | Feature Master | GS-056 | Support | Report an issue | P0 | MVP | Create issue from order. (Roles: Customer, Shop, Gig) | Ticket linked to order. | COMPLETED | COMPLETED | No change | Live | 'Report a problem' on an order -> linked ticket | - | - | src/app/api/orders/[id]/issue/route.ts
57 | Feature Master | GS-057 | Support | Returns/refunds | P0 | MVP | Rules by product/order status. (Roles: Customer, Operator, Admin) | Ledger + gateway refund. | COMPLETED | COMPLETED | No change | Live | Full returns workflow: request (reason, condition, quantity, photos, comments) -> automatic policy validation (window, per-reason policy, evidence, quantity held under an order lock) -> approval -> rider pickup (offer / accept / en route / handover code / failure and bounded re-offer) -> goods received -> inspection -> refund through the existing journaled refundDeliveredOrder, idempotent per return, 13 statuses with history. Customer, shop, operations and rider screens; rider pickup fee credited as an earning | Gateway refund (money back to card/UPI rather than wallet) Refunds go to the wallet; refunds to card / UPI wait on GS-073 (blocked). | - | src/server/services/returns.ts; src/server/services/return-pickups.ts; src/app/returns, /shop/returns, /admin/returns; drizzle/0029
58 | Feature Master | GS-058 | Support | Dispute management | P0 | MVP | Escalate delivery/product/payment disputes. (Roles: All) | Case lifecycle. | COMPLETED | COMPLETED | No change | Live | Dispute case entity (migration 0037): order, raiser, disputed amount, payment-method snapshot; 8 statuses (OPEN, TRIAGED, INVESTIGATING, RESOLUTION_PROPOSED, ESCALATED, RESOLVED, REJECTED, WITHDRAWN) with a transition table; auto-escalation by amount (default Rs 2,000) and age (default 48 h, hourly cron); escalated cases admin-only; refund resolution goes through refundDeliveredOrder with a double-pay guard; customer sees outcome, not working notes; /admin/disputes queue | Refund to card/UPI (today refunds are wallet credit) - depends on GS-028/GS-073 | - | src/lib/dispute-states.ts; src/server/services/disputes.ts; src/app/admin/disputes/page.tsx; src/app/api/cron/dispute-escalation/route.ts; drizzle/0037_dispute_cases.sql; tests/integration/disputes.test.ts
59 | Feature Master | GS-059 | Ratings | Shop rating | P1 | MVP | Rate shop/order. (Roles: Customer) | Moderation. | COMPLETED | COMPLETED | No change | Live | Eligibility, one per order, average, anonymous reviews, moderation | - | - | src/server/services/ratings.ts
60 | Feature Master | GS-060 | Ratings | Gig rating | P1 | MVP | Rate delivery. (Roles: Customer) | Quality metrics. | COMPLETED | COMPLETED | No change | Live | Rider rating: average visible to rider and operations | - | - | src/server/services/ratings.ts
61 | Feature Master | GS-061 | Finance | Shop commission | P0 | MVP | Calculate platform fee/commission. (Roles: Admin, Operator) | Configurable by category/shop. | COMPLETED | COMPLETED | No change | Live | Commission by default / shop type / shop, snapshotted per order | - | - | src/server/services/finance.ts:216
62 | Feature Master | GS-062 | Finance | Shop settlement | P0 | MVP | Pay shop after applicable adjustments. (Roles: Admin, Operator, Shop) | Settlement ledger. | COMPLETED | COMPLETED | No change | Live | Weekly shop settlements DRAFT -> APPROVED -> PAID, full lifecycle | - | - | src/app/api/finance/settlements/route.ts
63 | Feature Master | GS-063 | Finance | Gig earnings | P0 | MVP | Calculate delivery earnings. (Roles: Gig, Admin) | Distance/slot/incentive rules. | COMPLETED | COMPLETED | No change | Live | Configurable time slots (including overnight, weekdays, validity, priority) each with their own base, per-km, minimum, order component and peak bonus; incentives by order count, daily/weekly target, distance, peak hour and campaign; every earning stores its full breakdown plus append-only ledger lines and idempotent award rows; with no slots configured the result is exactly the old base + per-km; admin screen with a 'try a delivery' calculator. 12 unit tests on the calculation engine | - | - | src/server/services/delivery-earnings.ts; src/app/admin/rider-earnings/page.tsx; drizzle/0028; tests/unit/earnings-calc.test.ts
64 | Feature Master | GS-064 | Finance | Gig payout | P0 | MVP | Transfer earnings. (Roles: Admin, Operator, Gig) | Reconciliation. | COMPLETED | COMPLETED | No change | Live | Weekly rider payouts, full lifecycle | Payouts are recorded and reconciled; the bank transfer itself is manual. | - | src/app/api/finance/rider-payouts/route.ts
65 | Feature Master | GS-065 | Admin | Global dashboard | P0 | MVP | Manage all users, shops, orders, payments and settings. (Roles: Admin) | Full access. | COMPLETED | COMPLETED | No change | Live | getAdminDashboard() + /admin/dashboard: the marketplace's operational picture from live queries - in-flight orders by status, today's money, KPI cards, open risk flags, shops by status. No sample numbers | - | - | src/server/services/dashboards.ts:207; src/app/admin/dashboard/page.tsx
66 | Feature Master | GS-066 | Admin | Operator console | P0 | MVP | Onboarding, catalog upload, payments and exceptions. (Roles: Operator) | Restricted permissions. | COMPLETED | COMPLETED | No change | Live | Two exception queues: finance exceptions at /admin/finance/exceptions, and a general operations queue at /admin/exceptions with 12 categories (shop not accepting, shop slow, awaiting substitution, no rider, self-delivery overdue, rider not picked up, stuck after pickup, delivery code locked, failed delivery, returned-no-decision, disputed, past promised time), elapsed-time thresholds, severity and precedence | - | - | src/server/services/ops-exceptions.ts; src/app/admin/exceptions/page.tsx
67 | Feature Master | GS-067 | Admin | Audit logs | P0 | MVP | Track critical actions. (Roles: Admin, Auditor) | Immutable/event log. | COMPLETED | COMPLETED | No change | Live | audit_logs append-only, enforced by DB trigger | Dedicated Auditor role (optional) | - | drizzle/0018_audit_logs_append_only.sql; src/server/services/audit.ts
68 | Feature Master | GS-068 | Admin | Fraud/risk rules | P1 | Phase 2 | Detect suspicious orders, referrals, payments and accounts. (Roles: Admin, Operator) | Rules + review queue. | COMPLETED | COMPLETED | No change | Live | 11 risk rules (customer, rider, shop), hourly cron, review queue /admin/risk; a HIGH customer flag pauses COD | - | - | src/server/services/risk.ts; src/app/admin/risk/page.tsx
69 | Feature Master | GS-069 | Analytics | Marketplace KPI dashboard | P0 | MVP | GMV, orders, fill rate, delivery time, cancellations, retention. (Roles: Admin, Operator, Shop) | Role scoped. | COMPLETED | COMPLETED | No change | Live | /admin/analytics (marketplace) and /shop/analytics (own shop) | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
70 | Feature Master | GS-070 | Security | Privacy/consent management | P0 | MVP | Capture marketing and data consents. (Roles: All) | Consent history. | COMPLETED | COMPLETED | No change | Live | Marketing consent grant/withdraw with history; profile toggle; /api/consents/marketing | - | - | src/server/services/consents.ts; src/components/marketing-consent-toggle.tsx
71 | Feature Master | GS-071 | Security | Data access controls | P0 | MVP | Limit sensitive data visibility. (Roles: Admin, Operator) | Least privilege. | COMPLETED | COMPLETED | No change | Live | - | - | - | -
72 | Feature Master | GS-072 | Integration | Maps/navigation | P0 | MVP | Distance, routing and ETA. (Roles: Customer, Gig, Shop) | Provider abstraction. | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: routing.enabled) | F4: road distance and travel time from Google Routes or OSRM behind one provider interface, cached per ~100 m cell and logged; arrival time for customer (tracking map) and rider (dashboard); straight-line fallback when off or failing. Navigation is a Google Maps deep link. | In-app turn-by-turn navigation not built (Google Maps deep link used instead). | - | src/server/services/routing.ts; drizzle/0044_delivery_routes.sql; tests/integration/routing.test.ts
73 | Feature Master | GS-073 | Integration | Payment gateway | P0 | MVP | Payment intents, callbacks, refunds. (Roles: System) | Webhook verification. | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Live | Gateway plumbing reusable; refunds are wallet credits (journaled, idempotent). | Order payment intents, callbacks and gateway refunds. | Needs GS-028 | src/server/services/payments.ts
74 | Feature Master | GS-074 | Integration | SMS/WhatsApp/email/push | P1 | MVP | Notifications. (Roles: System) | Provider abstraction. | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Email + in-app live (email needs SMTP) | Email and in-app notifications live; SMS, PUSH and WHATSAPP channels have a provider seam with no vendor. | Real SMS / push / WhatsApp providers. | D2 - vendor choice (DLT registration) | src/server/notifications/channels.ts
75 | Workflow Master | WF-001 | Customer | Customer product purchase | n/a | n/a | Trigger: Customer selects product. Steps: Location → Search product → View all eligible shops → Compare price → Select shop → Cart → Address → Slot → Payment → Order created | Exception: Out of stock/service unavailable → alternate shop/substitution. Output: Shop fulfillment order | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Live | Every step works: location, search, eligible shops, comparison, cart, address, slot, payment by wallet or COD, order created; out-of-stock substitution; closed-shop confirmation. | Direct online payment for the order. | Needs GS-028 | src/server/services/orders.ts#checkout
76 | Workflow Master | WF-002 | Shop | Shop fulfillment | n/a | n/a | Trigger: New order received. Steps: Notify → Accept → Check stock → Substitute/reject items if needed → Pick → Pack → Ready | Exception: Timeout/reject → operations escalation. Output: Ready for pickup | COMPLETED | COMPLETED | No change | Live | Notify -> accept -> stock check -> substitute/remove -> pick -> pack -> READY | - | - | src/server/services/fulfilment.ts
77 | Workflow Master | WF-003 | System | Gig assignment | n/a | n/a | Trigger: Shop marks READY. Steps: Find eligible workers → society whitelist check → calculate priority → score ETA/distance/load → offer job → accept | Exception: No acceptance → widen radius/escalate. Output: Assigned | COMPLETED | COMPLETED | No change | Live | Auto-trigger, whitelist filter, priority, reliability, fairness, escalation, bounded retry with a full attempt log | Load batching tracked under GA-005 Offers go to one rider at a time (2-min expiry); no radius widening. | - | src/server/services/delivery-assignment.ts
78 | Workflow Master | WF-004 | System/Society | Society authorized delivery | n/a | n/a | Trigger: Order destination is society. Steps: Identify society → load active whitelist → filter/priority workers → notify security if enabled | Exception: No authorized worker → fallback policy or operations review. Output: Assigned to eligible worker | COMPLETED | COMPLETED | No change | Live | Identify society -> rider list -> filter/priority -> security alert; Phase C added gate entry mode and the security-desk contact | - | - | src/server/services/delivery-assignment.ts; src/server/services/societies.ts
79 | Workflow Master | WF-005 | Gig | Delivery | n/a | n/a | Trigger: Job accepted. Steps: Navigate to shop → Pickup OTP/QR → transport → society access → customer OTP/POD → Delivered | Exception: Customer unavailable → retry/return workflow. Output: Delivered or Failed | COMPLETED | COMPLETED | No change | Live | Pickup code -> OTP -> delivered; failed -> returned; society access notes; Phase C added 'arrived at shop' / 'arrived at customer' checkpoints with notifications, navigation deep links and rider-side privacy | In-app turn-by-turn navigation (deep link to Google Maps instead) | - | src/server/services/delivery-assignment.ts:599; src/components/delivery-partner-dashboard.tsx:634-667
80 | Workflow Master | WF-006 | Customer/System | Subscription | n/a | n/a | Trigger: Scheduled cycle. Steps: Check subscription → check payment → generate order → route to shop → fulfillment → gig assignment → delivery | Exception: Payment failed / shop unavailable → retry or exception. Output: Cycle completed | COMPLETED | COMPLETED | No change | Live | Subscription orders carry address/society -> fulfilment -> dispatch -> settlement | - | - | src/server/services/subscriptions.ts
81 | Workflow Master | WF-007 | Customer/Operator | Return/refund | n/a | n/a | Trigger: Issue reported. Steps: Validate policy → collect evidence → approve/refuse → pickup/replacement/refund → ledger update | Exception: Dispute → escalation. Output: Closed case | COMPLETED | COMPLETED | No change | Live | Report -> return request -> validation -> approval -> rider pickup -> inspection -> refund, end to end, with who bears the cost configurable per reason | Replacement instead of refund | - | src/server/services/returns.ts; src/server/services/return-pickups.ts
82 | Workflow Master | WF-008 | Shop/Operator | Shop onboarding | n/a | n/a | Trigger: Registration submitted. Steps: Capture business/KYC → document verification → payment reference → catalog → service area → approval | Exception: Missing/invalid docs → correction queue. Output: Shop Live / Rejected | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Live | Registration with categories, PAN/Udyam/GST/Shop Act IDs (at least one), duplicate guard; seller document verification with rejection reasons the seller sees (correction loop); registration-fee gate before approval; service area (radius + PIN zones + minimum order + pause); category fill of the catalogue; approval. | Approval is not blocked on verified documents - admins see the verification status and decide (documented design choice). | - | src/server/services/shops.ts; src/server/services/seller-verification.ts; docs/seller-verification/README.md
83 | Workflow Master | WF-009 | Shop | Marketing campaign | n/a | n/a | Trigger: Owner creates campaign. Steps: Select audience → consent check → budget/rate limit → approval if required → send → track | Exception: Opt-out/bounce/fraud → suppress. Output: Campaign report | COMPLETED | COMPLETED | No change | Live | Audience -> consent -> budget -> operations approval -> send -> tracking (opened, converted, revenue) | - | - | src/app/api/admin/campaigns/route.ts
84 | Workflow Master | WF-010 | System/Finance | Settlement | n/a | n/a | Trigger: Settlement cycle. Steps: Calculate GMV → commission → delivery charges → refunds → adjustments → shop payout → gig payout → reconcile | Exception: Mismatch → finance exception queue. Output: Settled | COMPLETED | COMPLETED | No change | Live | GMV -> commission -> refunds -> adjustments -> settlement -> payout -> reconciliation | - | - | src/server/services/finance.ts
85 | RBAC Matrix | RBAC-001 | Security | Browse/search | n/a | n/a | Customer: Y; Shop Owner: Y; Gig Worker: Y; Society Admin: Y; Operator: Y; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
86 | RBAC Matrix | RBAC-002 | Security | Place order | n/a | n/a | Customer: Y; Shop Owner: N; Gig Worker: N; Society Admin: N; Operator: N; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | Personal orders for every role; B2B a separate flow (order_type PERSONAL/B2B, buyer_shop_id, ORDER_PLACE_B2B) | - | - | src/server/db/schema.ts (orderTypeEnum); src/server/authz/permissions.ts
87 | RBAC Matrix | RBAC-003 | Security | Manage own shop | n/a | n/a | Customer: N; Shop Owner: Y; Gig Worker: N; Society Admin: N; Operator: Limited; Admin: Y | - | UNCLEAR | BLOCKED | UNCLEAR -> BLOCKED | Live | Shop owners manage their own shop; admins full. No 'Limited' operator scope for shop management. | Define what an operator may change on a shop, then implement. | Decision: what 'Limited' means | src/server/authz/permissions.ts
88 | RBAC Matrix | RBAC-004 | Security | Manage catalog | n/a | n/a | Customer: N; Shop Owner: Y; Gig Worker: N; Society Admin: N; Operator: Y; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
89 | RBAC Matrix | RBAC-005 | Security | Upload product lists | n/a | n/a | Customer: N; Shop Owner: Y; Gig Worker: N; Society Admin: N; Operator: Y; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
90 | RBAC Matrix | RBAC-006 | Security | Verify shop | n/a | n/a | Customer: N; Shop Owner: N; Gig Worker: N; Society Admin: N; Operator: Y; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
91 | RBAC Matrix | RBAC-007 | Security | Assign delivery | n/a | n/a | Customer: N; Shop Owner: N; Gig Worker: Limited; Society Admin: N; Operator: Y; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | Decision taken: shop retry KEPT but bounded and configurable. Assignment is automatic on READY; 'Find rider now' is now a bounded search (rider_searches, dispatch_attempts) with retry interval, attempt cap, total time limit, window expiry and manual cooldown; shop sees status, can retry or stop; every attempt logged; duplicate assignment impossible | - | - | src/server/services/delivery-assignment.ts; src/app/api/orders/[id]/assign/route.ts; drizzle/0027
92 | RBAC Matrix | RBAC-008 | Security | Manage own availability | n/a | n/a | Customer: N; Shop Owner: N; Gig Worker: Y; Society Admin: N; Operator: N; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
93 | RBAC Matrix | RBAC-009 | Security | Whitelist Gig workers | n/a | n/a | Customer: N; Shop Owner: N; Gig Worker: N; Society Admin: Y; Operator: N; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | Society-scoped roles; SOCIETY_MANAGE_ANY for platform staff | - | - | src/server/authz/permissions.ts
94 | RBAC Matrix | RBAC-010 | Security | View all orders | n/a | n/a | Customer: Own; Shop Owner: Own shop; Gig Worker: Own jobs; Society Admin: Society scope; Operator: Operational scope; Admin: All | - | COMPLETED | COMPLETED | No change | Live | ORDER_VIEW_OWN / _SHOP / _ANY; society dashboard shows society deliveries without customer PII; operator holds ORDER_VIEW_ANY and now has its own order-monitoring screen with status/shop/date filters | - | - | src/server/authz/permissions.ts:284-306; src/app/admin/orders/page.tsx; src/components/order-monitoring-table.tsx
95 | RBAC Matrix | RBAC-011 | Security | Refund approval | n/a | n/a | Customer: Request; Shop Owner: Request; Gig Worker: N; Society Admin: N; Operator: Y; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | ORDER_REFUND for operator/admin | - | - | src/server/authz/permissions.ts
96 | RBAC Matrix | RBAC-012 | Security | Settlement | n/a | n/a | Customer: Own statements; Shop Owner: Own earnings; Gig Worker: Own earnings; Society Admin: N; Operator: Y; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | Settlement visibility per role; operator exceptions-only view | - | - | src/server/authz/permissions.ts
97 | RBAC Matrix | RBAC-013 | Security | Manage users/roles | n/a | n/a | Customer: N; Shop Owner: N; Gig Worker: N; Society Admin: N; Operator: Limited; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
98 | RBAC Matrix | RBAC-014 | Security | System configuration | n/a | n/a | Customer: N; Shop Owner: N; Gig Worker: N; Society Admin: N; Operator: Limited; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | Extended by NEW-001 (business-rules console, Phase A-J) | - | - | -
99 | RBAC Matrix | RBAC-015 | Security | Audit logs | n/a | n/a | Customer: N; Shop Owner: N; Gig Worker: N; Society Admin: N; Operator: Limited; Admin: Y | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
100 | State Machines | SM-001 | Order | Order state machine | n/a | n/a | States: DRAFT → PAYMENT_PENDING → PAID → SHOP_PENDING → ACCEPTED → PREPARING → READY → ASSIGNED → PICKED_UP → OUT_FOR_DELIVERY → DELIVERED | Transitions: Each transition event logged. Exceptions: CANCELLED, FAILED, RETURNED, REFUNDED, DISPUTED | COMPLETED | COMPLETED | No change | Live | ACCEPTED, ASSIGNED, PICKED_UP, FAILED, RETURNED, DISPUTED added; full transition table + history + audit | - | - | src/server/db/schema.ts:123 (orderStatusEnum)
101 | State Machines | SM-002 | Shop | Shop state machine | n/a | n/a | States: APPLIED → KYC_PENDING → PAYMENT_PENDING → VERIFIED → ACTIVE → SUSPENDED → CLOSED | Transitions: Operator/admin approval. Exceptions: REJECTED | IN PROGRESS | IN PROGRESS | Progressed, same status | Live once migration 0042 is applied | F1: shop lifecycle PENDING / ACTIVE / PAUSED / SUSPENDED / REJECTED / CLOSED derived by trigger, transitions enforced and logged; suspension policy with impact preview; KYC status per document (seller verification) and registration-fee status exist as separate fields. | APPLIED -> KYC_PENDING -> PAYMENT_PENDING -> VERIFIED are all one PENDING stage; show them as lifecycle stages (the data already exists). | - | src/lib/status-models.ts; drizzle/0042_status_models.sql
102 | State Machines | SM-003 | Gig | Gig state machine | n/a | n/a | States: APPLIED → KYC_PENDING → VERIFIED → ACTIVE → ONLINE → ASSIGNED → PICKED_UP → DELIVERING → COMPLETED | Transitions: Availability + assignment events. Exceptions: SUSPENDED, BLOCKED | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Live once migration 0042 is applied (statusModels.enforceTransitions = true) | F1: rider lifecycle ONBOARDING / OFFLINE / AVAILABLE / BUSY / ON_DELIVERY / SUSPENDED / REJECTED / INACTIVE, derived from the existing columns by a database trigger; transitions enforced in the database and every change logged with its actor (status_changes, /admin/status-changes). | Mapping, not new enum values: APPLIED + KYC_PENDING = ONBOARDING (detail kept in REGISTERED / UNDER_REVIEW), ONLINE = AVAILABLE, ASSIGNED = BUSY, PICKED_UP / DELIVERING = ON_DELIVERY, BLOCKED = SUSPENDED. | - | src/lib/status-models.ts; drizzle/0042_status_models.sql; tests/integration/status-models.test.ts
103 | State Machines | SM-004 | Subscription | Subscription state machine | n/a | n/a | States: DRAFT → ACTIVE → PAUSED → SKIPPED → RENEWAL_PENDING → ORDER_CREATED → FULFILLED | Transitions: Cycle-based. Exceptions: PAYMENT_FAILED, CANCELLED | IN PROGRESS | IN PROGRESS | Progressed, same status | Live once migration 0042 is applied | F1: subscription lifecycle ACTIVE / PAUSED / CANCELLED / EXPIRED with enforced, logged transitions; PAYMENT_PENDING and per-date skips in the detailed status; subscription_events history. | DRAFT, RENEWAL_PENDING and per-cycle ORDER_CREATED / FULFILLED stages; SKIPPED and PAYMENT_FAILED as named lifecycle states. | - | src/lib/status-models.ts; src/server/services/subscriptions.ts
104 | State Machines | SM-005 | Payment | Payment state machine | n/a | n/a | States: INITIATED → AUTHORIZED → CAPTURED → RECONCILED | Transitions: Gateway webhook drives final state. Exceptions: FAILED, REFUNDED, CHARGEBACK | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Live | Unchanged: payment_status CREATED / PENDING / SUCCESS / FAILED / REFUNDED (wallet top-ups only). | INITIATED -> AUTHORIZED -> CAPTURED -> RECONCILED; CHARGEBACK. | Per-order online payment go-ahead (GS-028 / NEW-007) | src/server/db/schema.ts (paymentStatusEnum)
105 | State Machines | SM-006 | Issue | Issue state machine | n/a | n/a | States: OPEN → TRIAGED → INVESTIGATING → RESOLUTION_PROPOSED → RESOLVED → CLOSED | Transitions: Linked to order/payment. Exceptions: ESCALATED | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Live | Tickets linked to orders; returns 13-status machine; dispute cases have OPEN / TRIAGED / INVESTIGATING / RESOLUTION_PROPOSED / ESCALATED / RESOLVED; grievances still OPEN / IN_PROGRESS / RESOLVED / CLOSED. | Either add the four states to grievances or accept the dispute lifecycle as the issue state machine. | Decision: does the dispute lifecycle satisfy SM-006? | src/server/db/schema.ts (grievanceStatusEnum); src/lib/dispute-states.ts
106 | Gig Assignment Rules | GA-001 | Delivery | Society authorization | P0 | n/a | If society has active whitelist, authorized workers receive eligibility/priority; non-authorized workers are excluded when society policy is exclusive. | - | COMPLETED | COMPLETED | No change | Live | Exclusive society -> only listed riders offered | - | - | src/server/services/delivery-assignment.ts:97
107 | Gig Assignment Rules | GA-002 | Delivery | Society preferred partner | P0 | n/a | Preferred workers/fleet receive higher priority score. | - | COMPLETED | COMPLETED | No change | Live | Listed / preferred riders ranked first | - | - | src/server/services/delivery-assignment.ts:97-137
108 | Gig Assignment Rules | GA-003 | Delivery | Distance | P0 | n/a | Lower estimated travel distance/time improves score. | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
109 | Gig Assignment Rules | GA-004 | Delivery | Availability | P0 | n/a | Only ONLINE and eligible workers considered. | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
110 | Gig Assignment Rules | GA-005 | Delivery | Current load | P0 | n/a | Workers with active jobs receive lower priority unless batching is beneficial. | - | IN PROGRESS | IN PROGRESS | Progressed, same status | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: dispatch.busyRidersAsFallback) | F3: riders with active jobs are ranked after free riders (up to maxActiveDeliveriesPerRider, default 2) instead of being excluded. | Multi-order batching ('unless batching is beneficial') not built. | - | src/server/services/delivery-assignment.ts; tests/integration/busy-rider-fallback.test.ts
111 | Gig Assignment Rules | GA-006 | Delivery | Shop readiness | P0 | n/a | Assignment begins when order is READY or configurable pre-dispatch threshold is met. | - | COMPLETED | COMPLETED | No change | Live | Rider requested automatically when the shop marks READY | - | - | src/server/services/delivery-assignment.ts
112 | Gig Assignment Rules | GA-007 | Delivery | Reliability | P1 | n/a | Historical acceptance, on-time delivery and cancellation metrics may influence score. | - | COMPLETED | COMPLETED | No change | Live | Reliability score (30-day completions vs failures/declines) in ranking | - | - | src/server/services/delivery-assignment.ts:126
113 | Gig Assignment Rules | GA-008 | Delivery | Fairness | P1 | n/a | Do not starve eligible workers; apply rotation/cap rules. | - | COMPLETED | COMPLETED | No change | Live | Fairness penalty per offer received today | - | - | src/server/services/delivery-assignment.ts:85
114 | Gig Assignment Rules | GA-009 | Delivery | No worker | P0 | n/a | Expand search radius / retry / operations intervention. | - | COMPLETED | COMPLETED | No change | Live | Offers expire after 2 min; auto-retry; shop notified. Phase C added a bounded search with a total time limit, delivery-window expiry, manual cooldown, a stop control and a 'rider assignment failed' notification; 'No rider' is an ops exception | Radius widening Retry with cron + operations intervention; the search radius is not widened. | - | src/server/services/delivery-assignment.ts; src/server/notifications/templates.ts (DELIVERY_SEARCH_STOPPED)
115 | Navigation | NAV-001 | Customer | Customer portal - Home | n/a | n/a | Key screens: Location, Search, Categories, Nearby Shops, Product Comparison | - | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: homePriceComparison.enabled) | Location picker, shops that deliver to you, featured / Kesari / Green shelves, product-search-first hero, and F9 home-page price comparison across nearby delivering shops (cheapest highlighted, unpriced loose goods skipped). | The category grid was deliberately removed in favour of search-first; categories are reachable from shops and search. | - | src/app/page.tsx; src/server/services/price-comparison.ts; tests/integration/price-comparison.test.ts
116 | Navigation | NAV-002 | Customer | Customer portal - Shop | n/a | n/a | Key screens: Shop profile, catalog, offers, ratings, delivery options | - | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: shopOffers.enabled) | Shop profile, catalogue, rating + reviews, opening hours, delivery options, and F8 shop offers (product or category, dated) shown on the shop page and priced in cart and checkout. | - | - | src/server/services/shop-offers.ts; src/app/shop/offers; drizzle/0048_shop_offers.sql
117 | Navigation | NAV-003 | Customer | Customer portal - Cart & Checkout | n/a | n/a | Key screens: Cart, address, slot, coupons, payment | - | IN PROGRESS | BLOCKED | IN PROGRESS -> BLOCKED | Coupons: Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: coupons.enabled) | Cart, address re-validation with actions, slot choice with capacity (F5), F7 order-level coupons (flat / %, minimum order, dates, total and per-customer limits, split by goods value, server-validated), F8 offers priced in cart, wallet / COD payment. | Online payment at checkout. | Needs GS-028 | src/components/cart-view.tsx; src/server/services/coupons.ts; drizzle/0047_coupons.sql
118 | Navigation | NAV-004 | Customer | Customer portal - Orders | n/a | n/a | Key screens: Active orders, tracking, history, issues, refunds | - | COMPLETED | COMPLETED | No change | Live | Rate an order, report a problem, request a return (/orders/{id}/return, /returns), live tracking panel on in-flight orders, and raise / follow a dispute case | - | - | src/app/orders/page.tsx
119 | Navigation | NAV-005 | Customer | Customer portal - Subscriptions | n/a | n/a | Key screens: Active plans, schedule, skip/pause/resume, payment | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
120 | Navigation | NAV-006 | Shop | Shop portal - Dashboard | n/a | n/a | Key screens: Sales, orders, inventory alerts, performance | - | COMPLETED | COMPLETED | No change | Live | getShopDashboard(): the operator's day built entirely from live queries - today's orders and money, what needs action, stock alerts, ratings, performance. No sample numbers | - | - | src/server/services/dashboards.ts:63; src/app/shop/page.tsx
121 | Navigation | NAV-007 | Shop | Shop portal - Catalog | n/a | n/a | Key screens: Products, bulk upload, prices, inventory, categories | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
122 | Navigation | NAV-008 | Shop | Shop portal - Orders | n/a | n/a | Key screens: New, accepted, preparing, ready, completed, cancelled | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
123 | Navigation | NAV-009 | Shop | Shop portal - Marketing | n/a | n/a | Key screens: Customers, segments, campaigns, vouchers, referrals | - | COMPLETED | COMPLETED | No change | Live | /shop/marketing (customers, segments, campaigns, COD setting) | - | - | src/app/shop/marketing/page.tsx
124 | Navigation | NAV-010 | Shop | Shop portal - Finance | n/a | n/a | Key screens: Commission, invoices, settlements, payouts | - | COMPLETED | COMPLETED | No change | Live | /shop/finance | Invoices are part of NEW-007 (yet to start). | - | src/app/shop/finance/page.tsx
125 | Navigation | NAV-011 | Gig | Gig portal - Jobs | n/a | n/a | Key screens: Available, assigned, active, history | - | COMPLETED | COMPLETED | No change | Live | - | - | - | -
126 | Navigation | NAV-012 | Gig | Gig portal - Earnings | n/a | n/a | Key screens: Daily/weekly earnings, incentives, payouts | - | COMPLETED | COMPLETED | No change | Live | Rider earnings with status + payouts list, now with a per-earning breakdown | - | - | src/app/gig/orders/page.tsx; src/app/api/delivery-partner/earnings/route.ts
127 | Navigation | NAV-013 | Gig | Gig portal - Profile | n/a | n/a | Key screens: KYC, vehicle, bank, availability | - | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | Live | F2: rider edits own profile (vehicle, availability details) at /gig/profile; identity and bank changes go to an admin review queue, stored encrypted (/admin/rider-changes). | - | - | src/server/services/rider-profile.ts; drizzle/0043_rider_change_requests.sql; tests/integration/rider-profile.test.ts
128 | Navigation | NAV-014 | Society | Society portal - Dashboard | n/a | n/a | Key screens: Society profile, rules, authorized workers, deliveries | - | COMPLETED | COMPLETED | No change | Live | /society/{id} dashboard (rules, residents, riders, shops, deliveries) | - | - | src/app/society/[id]/page.tsx
129 | Navigation | NAV-015 | Operator | Operator portal - Operations | n/a | n/a | Key screens: Shop onboarding, product uploads, payments, exceptions | - | COMPLETED | COMPLETED | No change | Live | /admin/finance/exceptions and the non-finance /admin/exceptions queue with per-row actions | - | - | src/app/admin/exceptions/page.tsx; src/components/ops-exception-actions.tsx
130 | Navigation | NAV-016 | Operator | Operator portal - Orders | n/a | n/a | Key screens: Order monitoring, reassignment, support | - | COMPLETED | COMPLETED | No change | Live | /admin/orders order-monitoring screen with status, shop and date-range filters, gated on ORDER_VIEW_ANY | - | - | src/app/admin/orders/page.tsx; src/components/order-monitoring-table.tsx
131 | Navigation | NAV-017 | Admin | Admin portal - Control Tower | n/a | n/a | Key screens: All marketplace operations, users, shops, payments, settings | - | COMPLETED | COMPLETED | No change | Live | /admin/dashboard: live operations, in-flight orders, KPIs, risk flags, shop approvals, with links into orders, finance and exceptions | - | - | src/app/admin/dashboard/page.tsx
132 | Navigation | NAV-018 | Admin | Admin portal - Analytics | n/a | n/a | Key screens: GMV, orders, SLA, retention, seller/gig metrics | - | COMPLETED | COMPLETED | No change | Live | /admin/analytics and /shop/analytics | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
133 | Navigation | NAV-019 | Admin | Admin portal - Security | n/a | n/a | Key screens: RBAC, audit, fraud, consent, configuration | - | COMPLETED | COMPLETED | No change | Live | Fraud side: /admin/risk over 11 risk rules. NEW consent side: /admin/consents behind CONSENT_VIEW (operator + admin) - per-type consent standing vs live policy version, recent grant/withdrawal trail, per-person audited lookup; stored IP never returned | - | - | src/app/admin/consents/page.tsx; src/server/authz/permissions.ts (CONSENT_VIEW); tests/integration/consents.test.ts
134 | KPIs | KPI-001 | Analytics | GMV | n/a | n/a | Gross merchandise value of completed/paid orders | Owner: Admin | COMPLETED | COMPLETED | No change | Live | GMV plus a daily GMV trend | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
135 | KPIs | KPI-002 | Analytics | Order fill rate | n/a | n/a | Orders fulfilled without seller rejection/substitution failure | Owner: Operations | COMPLETED | COMPLETED | No change | Live | delivered / placed in window | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
136 | KPIs | KPI-003 | Analytics | Shop acceptance time | n/a | n/a | Time from order creation to shop acceptance | Owner: Shop/Operations | COMPLETED | COMPLETED | No change | Live | duration from placed to accepted | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
137 | KPIs | KPI-004 | Analytics | Pick-pack time | n/a | n/a | Time from acceptance to READY | Owner: Shop | COMPLETED | COMPLETED | No change | Live | duration from accepted to READY | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
138 | KPIs | KPI-005 | Analytics | Assignment time | n/a | n/a | Time from READY to Gig assigned | Owner: Delivery Ops | COMPLETED | COMPLETED | No change | Live | duration from READY to rider accepted | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
139 | KPIs | KPI-006 | Analytics | Delivery time | n/a | n/a | Pickup to delivered duration | Owner: Delivery Ops | COMPLETED | COMPLETED | No change | Live | duration from pickup to delivered | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
140 | KPIs | KPI-007 | Analytics | On-time delivery rate | n/a | n/a | Orders delivered within promised window | Owner: Operations | COMPLETED | COMPLETED | No change | Live | delivered within the promised window | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
141 | KPIs | KPI-008 | Analytics | Cancellation rate | n/a | n/a | Cancelled orders / total orders | Owner: Operations | COMPLETED | COMPLETED | No change | Live | cancelled / placed | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
142 | KPIs | KPI-009 | Analytics | Refund rate | n/a | n/a | Refunded order value / GMV | Owner: Finance | COMPLETED | COMPLETED | No change | Live | refund rate by count and by value | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
143 | KPIs | KPI-010 | Analytics | Customer repeat rate | n/a | n/a | Customers ordering again in defined period | Owner: Growth | COMPLETED | COMPLETED | No change | Live | ordering vs repeat vs returning customers | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
144 | KPIs | KPI-011 | Analytics | Subscription retention | n/a | n/a | Active subscriptions retained across cycles | Owner: Growth | COMPLETED | COMPLETED | No change | Live | retained subscriptions period over period | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
145 | KPIs | KPI-012 | Analytics | Gig acceptance rate | n/a | n/a | Accepted jobs / offered jobs | Owner: Delivery Ops | COMPLETED | COMPLETED | No change | Live | offers accepted / offers made | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
146 | KPIs | KPI-013 | Analytics | Gig utilization | n/a | n/a | Active delivery time / available time | Owner: Delivery Ops | COMPLETED | COMPLETED | No change | Live | active delivery time against availability | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
147 | KPIs | KPI-014 | Analytics | Shop retention | n/a | n/a | Active shops retained across period | Owner: Marketplace | COMPLETED | COMPLETED | No change | Live | shops active last period still active | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts
148 | KPIs | KPI-015 | Analytics | Marketing conversion | n/a | n/a | Orders attributable to campaign / recipients | Owner: Shop/Growth | COMPLETED | COMPLETED | No change | Live | Campaign conversion within the attribution window | - | - | src/server/services/analytics.ts
149 | Added after the target workbook | NEW-001 | Admin | Business-rules console (admin-tunable thresholds) | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | platform_settings + /admin/settings: nine rule groups (otp, dispatch, riderEarnings, returns, images, notifications, suspension, mrp, externalPrices) with code defaults, server-side validation and an audit trail. This is what makes 'configurable' true across the other features | Per-field forms instead of JSON editing | - | src/server/config/rules.ts; src/server/services/settings.ts; src/app/admin/settings/page.tsx; drizzle/0025
150 | Added after the target workbook | NEW-002 | Shop Onboarding | Shop suspension policy, impact preview & review | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | Configurable policy per open-order status (cancel & refund / continue / hold for review); impact preview before suspending and an impact list with per-order decisions after; the owner is told reason, time, expected action and impact; new orders stop at once; held orders are neither advanced by the shop nor dispatched; reinstatement. Review queue at /admin/suspensions | - | - | src/server/services/shop-suspension.ts; src/server/services/shop-suspension-guard.ts; src/app/admin/suspensions/page.tsx; drizzle/0031
151 | Added after the target workbook | NEW-003 | Orders | Order placed while the shop is closed | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | A customer can choose to order from a closed shop after an explicit confirmation; the order is flagged placed_while_closed, the shop gets an alert at once and a second one when it opens, and the customer is told the shop is closed and told again when it opens. Opening hours are evaluated in IST | - | - | src/server/db/schema.ts:1600,1653; src/server/services/shop-opening.ts; src/server/notifications/templates.ts
152 | Added after the target workbook | NEW-004 | Delivery | Rider arrival checkpoints & customer notices | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | 'Arrived at shop' and 'arrived at customer' checkpoints on the delivery, each with a notification; rider-side privacy (area only until pickup, never the customer's name, phone or handover codes) | - | - | drizzle/0027; src/server/services/delivery-assignment.ts:597-612; src/components/delivery-partner-dashboard.tsx
153 | Added after the target workbook | NEW-005 | Shop Onboarding | Minimum order value, pause new orders, extra delivery PIN zones | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | Per-shop minimum order value (CHECK-constrained), a 'pause new orders' switch and extra delivery PIN codes beyond the radius; serviceability, discovery, cart validation and checkout all honour them | - | - | src/server/db/schema.ts:691-702,875; drizzle/0026
154 | Added after the target workbook | NEW-006 | Orders | D10 cancellation & refund policy (verified) | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | Cancellation policy verified against code, history and tests at every stage (CONFIRMED / ACCEPTED / PREPARING / READY / ASSIGNED / PICKED_UP / OUT_FOR_DELIVERY) for customer and shop; two real gaps fixed; retained delivery fee journaled; 13 characterization tests | Confirm the ACCEPTED/ASSIGNED and PICKED_UP treatments with the business owner | - | tests/integration/d10-cancellation-policy.test.ts; docs/gokesari-audit/D10_VERIFICATION.md
155 | Added after the target workbook | NEW-007 | Payments | Direct per-order payments, tax invoicing, photo POD, accept timeout | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | YET TO START | YET TO START | Progressed, same status | - | Design only (DESIGN_PAYMENTS_INVOICING_POD_SLA.md). Re-checked 6 Oct: no ONLINE payment method, no invoice code, no photo proof of delivery, no accept-timeout auto-cancel. | Per-order online payment (needs the GS-028 go-ahead); tax invoicing (shop invoices goods, platform invoices its fees); photo proof of delivery; auto-cancel with full refund when a shop does not accept in time. The last three do not depend on the payment decision. | Go-ahead to build | docs/gokesari-audit/DESIGN_PAYMENTS_INVOICING_POD_SLA.md
156 | Added after the target workbook | NEW-008 | Catalog | Product category master & shop product-category visibility | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | product_categories as a master (unique names, permanent General category guarded by trigger); shop_product_categories decides which products a shop sees; removing a category moves products to General; removing it from a shop pauses its listings; screens /product-categories, /product-categories/products, /shop/product-categories, /admin/shops/[id]/product-categories; one-time categorisation script with dry run / apply / restore | Merge to main (migration renumbering needed - see Risks) Merged to main on 3 Oct (was staging-only in the 3 Oct report). | - | staging: drizzle/0038_product_category_management.sql; src/server/services/product-categories.ts; scripts/categorise-products.ts; tests/integration/product-categories.test.ts
157 | Added after the target workbook | NEW-009 | Admin | Explicit Save flow on admin screens (categories, privileges, user profiles) | n/a | n/a | Not in the target workbook; tracked since the 28 Sep / 3 Oct reports | - | COMPLETED | COMPLETED | No change | Live | Draft + Save Changes bar with dirty tracking, confirm step, unsaved-changes guard; privileges saved in one transaction (no half-applied role changes, last-admin protection, self-change blocked); profile edits limited to name/phone/status; every save audited. Editing moved to /admin/users/[id] and /admin/users/[id]/privileges | - | - | src/components/save-changes-bar.tsx; src/components/admin-privileges-form.tsx; tests/integration/admin-save-flows.test.ts
158 | Added after the target workbook | NEW-010 | Catalog | Shop inventory fill when a category is added; per-shop prices | n/a | n/a | Not in the target workbook; delivered 3-5 Oct (0e2d77f, 1221420) | - | - | COMPLETED | New row | Live | Adding a category to a shop lists every live product in it with stock 100; packaged goods start at master MRP and on sale, loose goods / no-MRP start unpriced and off sale; owner sees how many need a price and saves prices in bulk (PATCH /api/shops/[id]/prices); buyers see 'Price on request' + 'Ask shop'. | - | - | tests/integration/shop-inventory-fill.test.ts; commits 0e2d77f, 1221420

## Completed
# | ID | Section | Feature | Priority | Status 3 Oct | Switched on? | What is built | Remaining scope / caveat | Blocked on
1 | GS-002 | Feature Master | Role-based access control | P0 | COMPLETED | Live | SOCIETY_ADMIN role; society roles scoped per membership (ADMIN/OPERATOR/RESIDENT) | - | -
2 | GS-003 | Feature Master | Multi-role user account | P1 | COMPLETED | Live | user_role_grants; active role switcher in the header; /api/me/roles; admin revoke; shop/rider/society flows grant roles; staff roles exclusive | - | -
3 | GS-004 | Feature Master | PIN / address selection | P0 | COMPLETED | Live | 'Deliver to' location: saved address, device position or PIN, remembered in a cookie. Phase B added Maps Places address search, a 'save this place' path, and recipient name / recipient mobile / Home-Work-Other on addresses | - | -
4 | GS-005 | Feature Master | Society identification | P0 | COMPLETED | Live | Society membership; address <-> society link; orders.society_id | - | -
5 | GS-006 | Feature Master | Shop registration | P0 | COMPLETED | Live | - | 6 Oct: GST field added at registration; at least one of PAN / Udyam / GST / Shop Act required (135f29a). | -
6 | GS-007 | Feature Master | Business KYC | P0 | IN PROGRESS | Live; vendor checks run on the MOCK vendor until Gridlines keys are set (KYC_PROVIDER) | Seller verification Parts 1-4: PAN, GSTIN, Udyam, FSSAI and Shop Act per shop with document upload, vendor check (provider-agnostic, Gridlines adapter + mock), name matching, cross-document consistency score, per-document status, admin review queue (approve / reject with reason / re-check), daily re-check and expiry job, auto-suspend on lapse, DPDP retention/erasure. | Real vendor: Gridlines sandbox then live keys and written confirmation of response fields, Shop Act coverage, prices, DPA. By design, verification informs shop approval but does not block it. | -
7 | GS-008 | Feature Master | Payment reference verification | P0 | COMPLETED | Live | approveShop() now refuses unless fee_payment_status = PAID (derived from the shop_payments ledger), naming the amount outstanding; waived fee (zero snapshot) is written PAID at registration; approval queue shows each pending shop's fee state. Gate is on the transition only - shops already APPROVED untouched | - | -
8 | GS-009 | Feature Master | Shop categories | P0 | COMPLETED | Live | Admin-configurable category master: shop_categories + shop_category_mapping (many per shop), seeded from the 44 shop types and backfilled; registration requires at least one category; owners edit their own on /shop; operators/admins manage the list at /admin/shop-categories and assign per shop; uncategorised shops flagged; categories feed search relevance | - | -
9 | GS-010 | Feature Master | Service radius / delivery zone | P0 | COMPLETED | Live | shops.service_radius_km (1-50 km) editable by the shop; Phase B added extra delivery zones by PIN code (shops.delivery_pincodes), honoured by serviceability, checkout and discovery | - | -
10 | GS-011 | Feature Master | Product master | P0 | COMPLETED | Live | - | - | -
11 | GS-012 | Feature Master | Shop catalog mapping | P0 | COMPLETED | Live | - | - | -
12 | GS-013 | Feature Master | Bulk product upload | P0 | COMPLETED | Live | - | - | -
13 | GS-014 | Feature Master | Product images/specifications | P1 | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: imageModeration.enabled) | Image store with several images per product/listing, primary, reorder, alt text; F10 moderation queue (pending -> approve / reject with reason) at /admin/image-moderation; existing photos stay live. | - | -
14 | GS-015 | Feature Master | MRP / selling price / discount | P0 | COMPLETED | Live | MRP governance: a selling price above an enforced MRP is refused everywhere a shop price is written (assertPriceWithinMrp on both catalogue write paths); MRP provenance and verification status; MRP drops notify shops without touching prices; shop MRP corrections decided by operations; violations report; MRP shown on the product page | - | -
15 | GS-016 | Feature Master | Stock quantity | P0 | COMPLETED | Live | - | - | -
16 | GS-017 | Feature Master | Low-stock threshold | P1 | COMPLETED | Live | Extended by GS-018 (three-level thresholds, Phase I) | - | -
17 | GS-018 | Feature Master | Reorder level / quantity | P1 | COMPLETED | Live | Low-stock threshold, reorder level and reorder quantity resolved at listing -> product -> shop level with an explicit opt-out and the source reported; reserved / available / on-hand; one notification per new alert; hand-edited stock now writes the ledger and re-checks alerts | Analytics-driven replenishment suggestions (enhancement) | -
18 | GS-019 | Feature Master | Shop search | P0 | COMPLETED | Live | Shops that deliver to the location, nearest first, with distance | - | -
19 | GS-020 | Feature Master | Product search | P0 | COMPLETED | Live | Product search limited to serviceable shops, nearest first | - | -
20 | GS-021 | Feature Master | All shops selling product | P0 | COMPLETED | Live | /products/{id}: every shop selling the product | - | -
21 | GS-022 | Feature Master | Local price comparison | P0 | COMPLETED | Live | Per-unit / per-pack comparison, 'Lowest price', delivers-to-you | - | -
22 | GS-024 | Feature Master | Single-shop cart | P0 | COMPLETED | Live | - | - | -
23 | GS-025 | Feature Master | Multi-shop cart | P1 | COMPLETED | Live | - | - | -
24 | GS-026 | Feature Master | Address validation | P0 | COMPLETED | Live | Cart warning, then a checkout hard block when a shop does not deliver to the address. Phase B added a cart-validation service that re-checks every shop in the cart against the chosen location - deliverable, paused, unavailable items, minimum order, delivery charge, closed-now - each with an action, re-running when the address changes | - | -
25 | GS-029 | Feature Master | Wallet | P1 | COMPLETED | Live | - | - | -
26 | GS-030 | Feature Master | COD | P1 | COMPLETED | Live | COD at checkout with risk limits; shop opt-in; rider/operator cash confirmation; collection nets into finance batches; deposits at /admin/cod; COD refunds as wallet credit | - | -
27 | GS-031 | Feature Master | Payment reconciliation | P0 | COMPLETED | Live | Reconciliation records + exception queue (order/payment/rider/settlement/payout) | Reconciles the gateway transactions that exist today (wallet top-ups). | -
28 | GS-032 | Feature Master | Order creation | P0 | COMPLETED | Live | - | - | -
29 | GS-033 | Feature Master | Shop order split | P0 | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: parentOrders.enabled) | One order per shop from a multi-shop cart, plus F6 parent reference (GK-...) linking them; customer page /orders/group/[reference]. | - | -
30 | GS-034 | Feature Master | Shop accept/reject | P0 | COMPLETED | Live | Shop accept / reject (reject = full refund + restock); ops exceptions flag 'Shop not accepting' and 'Shop slow to prepare' | Accept-timeout auto-cancel (designed 1 Oct, not built) Late acceptance is flagged in the ops exceptions queue; auto-cancel on timeout is part of NEW-007 (yet to start). | -
31 | GS-035 | Feature Master | Substitution approval | P1 | COMPLETED | Live | Shop proposes a substitute; customer approves/rejects; price difference refunded | - | -
32 | GS-036 | Feature Master | Pick and pack | P0 | COMPLETED | Live | Per-line picking, pack -> READY | SLA reporting SLA measured by the pick-pack KPI; SLA reporting per shop is part of NEW-007. | -
33 | GS-037 | Feature Master | Gig worker onboarding | P0 | COMPLETED | Live | - | - | -
34 | GS-038 | Feature Master | Online/offline status | P0 | COMPLETED | Live | - | - | -
35 | GS-039 | Feature Master | Job assignment | P0 | COMPLETED | Live | Auto-trigger on READY; cron retry; no re-offer to decliners; Phase C made the whole search bounded and logged (rider_searches, dispatch_attempts) with admin-tunable retry interval, attempt cap and time limit | - | -
36 | GS-040 | Feature Master | Society priority assignment | P0 | COMPLETED | Live | Society preference in dispatch ranking | - | -
37 | GS-041 | Feature Master | Pickup OTP/QR | P0 | COMPLETED | Live | Pickup code issued on accept; rider must enter it | QR variant Pickup code only - no QR. | -
38 | GS-042 | Feature Master | Live tracking | P0 | COMPLETED | Live | Tracking API with role/privacy checks + polling LiveTrackingMap, now MOUNTED: on /orders inside an in-flight order card that has a rider, and on /admin/orders behind a per-row Track toggle. isTrackableOrderStatus() limits polling to orders actually in flight. Rider privacy: area only until pickup, no ETA from a stale fix | - | -
39 | GS-043 | Feature Master | Delivery OTP/POD | P0 | COMPLETED | Live | Customer delivery OTP (5 attempts); operations override with a proof note; 'Delivery code locked' is an ops exception | Photo / signature proof of delivery (designed 1 Oct, not built) Delivery OTP with ops override; photo POD (optional in your table) is part of NEW-007. | -
40 | GS-044 | Feature Master | Society registration | P1 | COMPLETED | Live | Registration -> operator verify/reject/suspend/reinstate | Map pin picker on the society form | -
41 | GS-045 | Feature Master | Authorized Gig worker whitelist | P0 | COMPLETED | Live | Authorised rider list by mobile; add / revoke / preferred; audited | - | -
42 | GS-046 | Feature Master | Security notification | P1 | COMPLETED | Live | Society security alert on rider acceptance (opt-in) | - | -
43 | GS-047 | Feature Master | Delivery instructions | P1 | COMPLETED | Live | Society gate notes + customer landmark/instructions on the rider job; Phase C added a gate entry mode, an optional security-desk contact shared with the rider only if the society enables it, and a customer-at-gate notice | - | -
44 | GS-048 | Feature Master | Daily milk subscription | P0 | COMPLETED | Live | - | - | -
45 | GS-049 | Feature Master | Recurring vegetables/daily goods | P1 | COMPLETED | Live | Weekday schedules; generated orders carry address/society | - | -
46 | GS-050 | Feature Master | Subscription payment | P0 | COMPLETED | Live | - | - | -
47 | GS-051 | Feature Master | Skip/pause/resume/cancel | P0 | COMPLETED | Live | - | - | -
48 | GS-052 | Feature Master | Customer segmentation | P1 | COMPLETED | Live | Segments by PIN, society, delivered orders, recency, lapse, spend; consent required; counts only | - | -
49 | GS-053 | Feature Master | Shop promotional campaigns | P1 | COMPLETED | Live | Shop campaigns with budget, shop rate limit and customer frequency caps | - | -
50 | GS-054 | Feature Master | Referral program | P1 | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: customerReferrals.enabled; rewards Rs 50 / Rs 50) | Shop referral attribution, plus F11 customer referral code and link (/refer, /r/CODE): both rewarded on the friend's first delivered order; self-referral, duplicate-account and per-referrer cap guards; /admin/customer-referrals. | - | -
51 | GS-055 | Feature Master | Order notifications | P0 | COMPLETED | Live | Notification framework: in-app + email, queued per channel with retries and backoff, delivery log, dead-letter handling, per-category preferences (security notices always on), read/unread, and templates for every order, return, delivery, shop, wallet, subscription, society and security event. Sent by a one-minute cron | Email + in-app; SMS / WhatsApp / push wait on GS-074 (blocked). | -
52 | GS-056 | Feature Master | Report an issue | P0 | COMPLETED | Live | 'Report a problem' on an order -> linked ticket | - | -
53 | GS-057 | Feature Master | Returns/refunds | P0 | COMPLETED | Live | Full returns workflow: request (reason, condition, quantity, photos, comments) -> automatic policy validation (window, per-reason policy, evidence, quantity held under an order lock) -> approval -> rider pickup (offer / accept / en route / handover code / failure and bounded re-offer) -> goods received -> inspection -> refund through the existing journaled refundDeliveredOrder, idempotent per return, 13 statuses with history. Customer, shop, operations and rider screens; rider pickup fee credited as an earning | Gateway refund (money back to card/UPI rather than wallet) Refunds go to the wallet; refunds to card / UPI wait on GS-073 (blocked). | -
54 | GS-058 | Feature Master | Dispute management | P0 | COMPLETED | Live | Dispute case entity (migration 0037): order, raiser, disputed amount, payment-method snapshot; 8 statuses (OPEN, TRIAGED, INVESTIGATING, RESOLUTION_PROPOSED, ESCALATED, RESOLVED, REJECTED, WITHDRAWN) with a transition table; auto-escalation by amount (default Rs 2,000) and age (default 48 h, hourly cron); escalated cases admin-only; refund resolution goes through refundDeliveredOrder with a double-pay guard; customer sees outcome, not working notes; /admin/disputes queue | Refund to card/UPI (today refunds are wallet credit) - depends on GS-028/GS-073 | -
55 | GS-059 | Feature Master | Shop rating | P1 | COMPLETED | Live | Eligibility, one per order, average, anonymous reviews, moderation | - | -
56 | GS-060 | Feature Master | Gig rating | P1 | COMPLETED | Live | Rider rating: average visible to rider and operations | - | -
57 | GS-061 | Feature Master | Shop commission | P0 | COMPLETED | Live | Commission by default / shop type / shop, snapshotted per order | - | -
58 | GS-062 | Feature Master | Shop settlement | P0 | COMPLETED | Live | Weekly shop settlements DRAFT -> APPROVED -> PAID, full lifecycle | - | -
59 | GS-063 | Feature Master | Gig earnings | P0 | COMPLETED | Live | Configurable time slots (including overnight, weekdays, validity, priority) each with their own base, per-km, minimum, order component and peak bonus; incentives by order count, daily/weekly target, distance, peak hour and campaign; every earning stores its full breakdown plus append-only ledger lines and idempotent award rows; with no slots configured the result is exactly the old base + per-km; admin screen with a 'try a delivery' calculator. 12 unit tests on the calculation engine | - | -
60 | GS-064 | Feature Master | Gig payout | P0 | COMPLETED | Live | Weekly rider payouts, full lifecycle | Payouts are recorded and reconciled; the bank transfer itself is manual. | -
61 | GS-065 | Feature Master | Global dashboard | P0 | COMPLETED | Live | getAdminDashboard() + /admin/dashboard: the marketplace's operational picture from live queries - in-flight orders by status, today's money, KPI cards, open risk flags, shops by status. No sample numbers | - | -
62 | GS-066 | Feature Master | Operator console | P0 | COMPLETED | Live | Two exception queues: finance exceptions at /admin/finance/exceptions, and a general operations queue at /admin/exceptions with 12 categories (shop not accepting, shop slow, awaiting substitution, no rider, self-delivery overdue, rider not picked up, stuck after pickup, delivery code locked, failed delivery, returned-no-decision, disputed, past promised time), elapsed-time thresholds, severity and precedence | - | -
63 | GS-067 | Feature Master | Audit logs | P0 | COMPLETED | Live | audit_logs append-only, enforced by DB trigger | Dedicated Auditor role (optional) | -
64 | GS-068 | Feature Master | Fraud/risk rules | P1 | COMPLETED | Live | 11 risk rules (customer, rider, shop), hourly cron, review queue /admin/risk; a HIGH customer flag pauses COD | - | -
65 | GS-069 | Feature Master | Marketplace KPI dashboard | P0 | COMPLETED | Live | /admin/analytics (marketplace) and /shop/analytics (own shop) | - | -
66 | GS-070 | Feature Master | Privacy/consent management | P0 | COMPLETED | Live | Marketing consent grant/withdraw with history; profile toggle; /api/consents/marketing | - | -
67 | GS-071 | Feature Master | Data access controls | P0 | COMPLETED | Live | - | - | -
68 | GS-072 | Feature Master | Maps/navigation | P0 | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: routing.enabled) | F4: road distance and travel time from Google Routes or OSRM behind one provider interface, cached per ~100 m cell and logged; arrival time for customer (tracking map) and rider (dashboard); straight-line fallback when off or failing. Navigation is a Google Maps deep link. | In-app turn-by-turn navigation not built (Google Maps deep link used instead). | -
69 | WF-002 | Workflow Master | Shop fulfillment | n/a | COMPLETED | Live | Notify -> accept -> stock check -> substitute/remove -> pick -> pack -> READY | - | -
70 | WF-003 | Workflow Master | Gig assignment | n/a | COMPLETED | Live | Auto-trigger, whitelist filter, priority, reliability, fairness, escalation, bounded retry with a full attempt log | Load batching tracked under GA-005 Offers go to one rider at a time (2-min expiry); no radius widening. | -
71 | WF-004 | Workflow Master | Society authorized delivery | n/a | COMPLETED | Live | Identify society -> rider list -> filter/priority -> security alert; Phase C added gate entry mode and the security-desk contact | - | -
72 | WF-005 | Workflow Master | Delivery | n/a | COMPLETED | Live | Pickup code -> OTP -> delivered; failed -> returned; society access notes; Phase C added 'arrived at shop' / 'arrived at customer' checkpoints with notifications, navigation deep links and rider-side privacy | In-app turn-by-turn navigation (deep link to Google Maps instead) | -
73 | WF-006 | Workflow Master | Subscription | n/a | COMPLETED | Live | Subscription orders carry address/society -> fulfilment -> dispatch -> settlement | - | -
74 | WF-007 | Workflow Master | Return/refund | n/a | COMPLETED | Live | Report -> return request -> validation -> approval -> rider pickup -> inspection -> refund, end to end, with who bears the cost configurable per reason | Replacement instead of refund | -
75 | WF-008 | Workflow Master | Shop onboarding | n/a | IN PROGRESS | Live | Registration with categories, PAN/Udyam/GST/Shop Act IDs (at least one), duplicate guard; seller document verification with rejection reasons the seller sees (correction loop); registration-fee gate before approval; service area (radius + PIN zones + minimum order + pause); category fill of the catalogue; approval. | Approval is not blocked on verified documents - admins see the verification status and decide (documented design choice). | -
76 | WF-009 | Workflow Master | Marketing campaign | n/a | COMPLETED | Live | Audience -> consent -> budget -> operations approval -> send -> tracking (opened, converted, revenue) | - | -
77 | WF-010 | Workflow Master | Settlement | n/a | COMPLETED | Live | GMV -> commission -> refunds -> adjustments -> settlement -> payout -> reconciliation | - | -
78 | RBAC-001 | RBAC Matrix | Browse/search | n/a | COMPLETED | Live | - | - | -
79 | RBAC-002 | RBAC Matrix | Place order | n/a | COMPLETED | Live | Personal orders for every role; B2B a separate flow (order_type PERSONAL/B2B, buyer_shop_id, ORDER_PLACE_B2B) | - | -
80 | RBAC-004 | RBAC Matrix | Manage catalog | n/a | COMPLETED | Live | - | - | -
81 | RBAC-005 | RBAC Matrix | Upload product lists | n/a | COMPLETED | Live | - | - | -
82 | RBAC-006 | RBAC Matrix | Verify shop | n/a | COMPLETED | Live | - | - | -
83 | RBAC-007 | RBAC Matrix | Assign delivery | n/a | COMPLETED | Live | Decision taken: shop retry KEPT but bounded and configurable. Assignment is automatic on READY; 'Find rider now' is now a bounded search (rider_searches, dispatch_attempts) with retry interval, attempt cap, total time limit, window expiry and manual cooldown; shop sees status, can retry or stop; every attempt logged; duplicate assignment impossible | - | -
84 | RBAC-008 | RBAC Matrix | Manage own availability | n/a | COMPLETED | Live | - | - | -
85 | RBAC-009 | RBAC Matrix | Whitelist Gig workers | n/a | COMPLETED | Live | Society-scoped roles; SOCIETY_MANAGE_ANY for platform staff | - | -
86 | RBAC-010 | RBAC Matrix | View all orders | n/a | COMPLETED | Live | ORDER_VIEW_OWN / _SHOP / _ANY; society dashboard shows society deliveries without customer PII; operator holds ORDER_VIEW_ANY and now has its own order-monitoring screen with status/shop/date filters | - | -
87 | RBAC-011 | RBAC Matrix | Refund approval | n/a | COMPLETED | Live | ORDER_REFUND for operator/admin | - | -
88 | RBAC-012 | RBAC Matrix | Settlement | n/a | COMPLETED | Live | Settlement visibility per role; operator exceptions-only view | - | -
89 | RBAC-013 | RBAC Matrix | Manage users/roles | n/a | COMPLETED | Live | - | - | -
90 | RBAC-014 | RBAC Matrix | System configuration | n/a | COMPLETED | Live | Extended by NEW-001 (business-rules console, Phase A-J) | - | -
91 | RBAC-015 | RBAC Matrix | Audit logs | n/a | COMPLETED | Live | - | - | -
92 | SM-001 | State Machines | Order state machine | n/a | COMPLETED | Live | ACCEPTED, ASSIGNED, PICKED_UP, FAILED, RETURNED, DISPUTED added; full transition table + history + audit | - | -
93 | SM-003 | State Machines | Gig state machine | n/a | IN PROGRESS | Live once migration 0042 is applied (statusModels.enforceTransitions = true) | F1: rider lifecycle ONBOARDING / OFFLINE / AVAILABLE / BUSY / ON_DELIVERY / SUSPENDED / REJECTED / INACTIVE, derived from the existing columns by a database trigger; transitions enforced in the database and every change logged with its actor (status_changes, /admin/status-changes). | Mapping, not new enum values: APPLIED + KYC_PENDING = ONBOARDING (detail kept in REGISTERED / UNDER_REVIEW), ONLINE = AVAILABLE, ASSIGNED = BUSY, PICKED_UP / DELIVERING = ON_DELIVERY, BLOCKED = SUSPENDED. | -
94 | GA-001 | Gig Assignment Rules | Society authorization | P0 | COMPLETED | Live | Exclusive society -> only listed riders offered | - | -
95 | GA-002 | Gig Assignment Rules | Society preferred partner | P0 | COMPLETED | Live | Listed / preferred riders ranked first | - | -
96 | GA-003 | Gig Assignment Rules | Distance | P0 | COMPLETED | Live | - | - | -
97 | GA-004 | Gig Assignment Rules | Availability | P0 | COMPLETED | Live | - | - | -
98 | GA-006 | Gig Assignment Rules | Shop readiness | P0 | COMPLETED | Live | Rider requested automatically when the shop marks READY | - | -
99 | GA-007 | Gig Assignment Rules | Reliability | P1 | COMPLETED | Live | Reliability score (30-day completions vs failures/declines) in ranking | - | -
100 | GA-008 | Gig Assignment Rules | Fairness | P1 | COMPLETED | Live | Fairness penalty per offer received today | - | -
101 | GA-009 | Gig Assignment Rules | No worker | P0 | COMPLETED | Live | Offers expire after 2 min; auto-retry; shop notified. Phase C added a bounded search with a total time limit, delivery-window expiry, manual cooldown, a stop control and a 'rider assignment failed' notification; 'No rider' is an ops exception | Radius widening Retry with cron + operations intervention; the search radius is not widened. | -
102 | NAV-001 | Navigation | Customer portal - Home | n/a | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: homePriceComparison.enabled) | Location picker, shops that deliver to you, featured / Kesari / Green shelves, product-search-first hero, and F9 home-page price comparison across nearby delivering shops (cheapest highlighted, unpriced loose goods skipped). | The category grid was deliberately removed in favour of search-first; categories are reachable from shops and search. | -
103 | NAV-002 | Navigation | Customer portal - Shop | n/a | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: shopOffers.enabled) | Shop profile, catalogue, rating + reviews, opening hours, delivery options, and F8 shop offers (product or category, dated) shown on the shop page and priced in cart and checkout. | - | -
104 | NAV-004 | Navigation | Customer portal - Orders | n/a | COMPLETED | Live | Rate an order, report a problem, request a return (/orders/{id}/return, /returns), live tracking panel on in-flight orders, and raise / follow a dispute case | - | -
105 | NAV-005 | Navigation | Customer portal - Subscriptions | n/a | COMPLETED | Live | - | - | -
106 | NAV-006 | Navigation | Shop portal - Dashboard | n/a | COMPLETED | Live | getShopDashboard(): the operator's day built entirely from live queries - today's orders and money, what needs action, stock alerts, ratings, performance. No sample numbers | - | -
107 | NAV-007 | Navigation | Shop portal - Catalog | n/a | COMPLETED | Live | - | - | -
108 | NAV-008 | Navigation | Shop portal - Orders | n/a | COMPLETED | Live | - | - | -
109 | NAV-009 | Navigation | Shop portal - Marketing | n/a | COMPLETED | Live | /shop/marketing (customers, segments, campaigns, COD setting) | - | -
110 | NAV-010 | Navigation | Shop portal - Finance | n/a | COMPLETED | Live | /shop/finance | Invoices are part of NEW-007 (yet to start). | -
111 | NAV-011 | Navigation | Gig portal - Jobs | n/a | COMPLETED | Live | - | - | -
112 | NAV-012 | Navigation | Gig portal - Earnings | n/a | COMPLETED | Live | Rider earnings with status + payouts list, now with a per-earning breakdown | - | -
113 | NAV-013 | Navigation | Gig portal - Profile | n/a | IN PROGRESS | Live | F2: rider edits own profile (vehicle, availability details) at /gig/profile; identity and bank changes go to an admin review queue, stored encrypted (/admin/rider-changes). | - | -
114 | NAV-014 | Navigation | Society portal - Dashboard | n/a | COMPLETED | Live | /society/{id} dashboard (rules, residents, riders, shops, deliveries) | - | -
115 | NAV-015 | Navigation | Operator portal - Operations | n/a | COMPLETED | Live | /admin/finance/exceptions and the non-finance /admin/exceptions queue with per-row actions | - | -
116 | NAV-016 | Navigation | Operator portal - Orders | n/a | COMPLETED | Live | /admin/orders order-monitoring screen with status, shop and date-range filters, gated on ORDER_VIEW_ANY | - | -
117 | NAV-017 | Navigation | Admin portal - Control Tower | n/a | COMPLETED | Live | /admin/dashboard: live operations, in-flight orders, KPIs, risk flags, shop approvals, with links into orders, finance and exceptions | - | -
118 | NAV-018 | Navigation | Admin portal - Analytics | n/a | COMPLETED | Live | /admin/analytics and /shop/analytics | - | -
119 | NAV-019 | Navigation | Admin portal - Security | n/a | COMPLETED | Live | Fraud side: /admin/risk over 11 risk rules. NEW consent side: /admin/consents behind CONSENT_VIEW (operator + admin) - per-type consent standing vs live policy version, recent grant/withdrawal trail, per-person audited lookup; stored IP never returned | - | -
120 | KPI-001 | KPIs | GMV | n/a | COMPLETED | Live | GMV plus a daily GMV trend | - | -
121 | KPI-002 | KPIs | Order fill rate | n/a | COMPLETED | Live | delivered / placed in window | - | -
122 | KPI-003 | KPIs | Shop acceptance time | n/a | COMPLETED | Live | duration from placed to accepted | - | -
123 | KPI-004 | KPIs | Pick-pack time | n/a | COMPLETED | Live | duration from accepted to READY | - | -
124 | KPI-005 | KPIs | Assignment time | n/a | COMPLETED | Live | duration from READY to rider accepted | - | -
125 | KPI-006 | KPIs | Delivery time | n/a | COMPLETED | Live | duration from pickup to delivered | - | -
126 | KPI-007 | KPIs | On-time delivery rate | n/a | COMPLETED | Live | delivered within the promised window | - | -
127 | KPI-008 | KPIs | Cancellation rate | n/a | COMPLETED | Live | cancelled / placed | - | -
128 | KPI-009 | KPIs | Refund rate | n/a | COMPLETED | Live | refund rate by count and by value | - | -
129 | KPI-010 | KPIs | Customer repeat rate | n/a | COMPLETED | Live | ordering vs repeat vs returning customers | - | -
130 | KPI-011 | KPIs | Subscription retention | n/a | COMPLETED | Live | retained subscriptions period over period | - | -
131 | KPI-012 | KPIs | Gig acceptance rate | n/a | COMPLETED | Live | offers accepted / offers made | - | -
132 | KPI-013 | KPIs | Gig utilization | n/a | COMPLETED | Live | active delivery time against availability | - | -
133 | KPI-014 | KPIs | Shop retention | n/a | COMPLETED | Live | shops active last period still active | - | -
134 | KPI-015 | KPIs | Marketing conversion | n/a | COMPLETED | Live | Campaign conversion within the attribution window | - | -
135 | NEW-001 | Added after the target workbook | Business-rules console (admin-tunable thresholds) | n/a | COMPLETED | Live | platform_settings + /admin/settings: nine rule groups (otp, dispatch, riderEarnings, returns, images, notifications, suspension, mrp, externalPrices) with code defaults, server-side validation and an audit trail. This is what makes 'configurable' true across the other features | Per-field forms instead of JSON editing | -
136 | NEW-002 | Added after the target workbook | Shop suspension policy, impact preview & review | n/a | COMPLETED | Live | Configurable policy per open-order status (cancel & refund / continue / hold for review); impact preview before suspending and an impact list with per-order decisions after; the owner is told reason, time, expected action and impact; new orders stop at once; held orders are neither advanced by the shop nor dispatched; reinstatement. Review queue at /admin/suspensions | - | -
137 | NEW-003 | Added after the target workbook | Order placed while the shop is closed | n/a | COMPLETED | Live | A customer can choose to order from a closed shop after an explicit confirmation; the order is flagged placed_while_closed, the shop gets an alert at once and a second one when it opens, and the customer is told the shop is closed and told again when it opens. Opening hours are evaluated in IST | - | -
138 | NEW-004 | Added after the target workbook | Rider arrival checkpoints & customer notices | n/a | COMPLETED | Live | 'Arrived at shop' and 'arrived at customer' checkpoints on the delivery, each with a notification; rider-side privacy (area only until pickup, never the customer's name, phone or handover codes) | - | -
139 | NEW-005 | Added after the target workbook | Minimum order value, pause new orders, extra delivery PIN zones | n/a | COMPLETED | Live | Per-shop minimum order value (CHECK-constrained), a 'pause new orders' switch and extra delivery PIN codes beyond the radius; serviceability, discovery, cart validation and checkout all honour them | - | -
140 | NEW-006 | Added after the target workbook | D10 cancellation & refund policy (verified) | n/a | COMPLETED | Live | Cancellation policy verified against code, history and tests at every stage (CONFIRMED / ACCEPTED / PREPARING / READY / ASSIGNED / PICKED_UP / OUT_FOR_DELIVERY) for customer and shop; two real gaps fixed; retained delivery fee journaled; 13 characterization tests | Confirm the ACCEPTED/ASSIGNED and PICKED_UP treatments with the business owner | -
141 | NEW-008 | Added after the target workbook | Product category master & shop product-category visibility | n/a | COMPLETED | Live | product_categories as a master (unique names, permanent General category guarded by trigger); shop_product_categories decides which products a shop sees; removing a category moves products to General; removing it from a shop pauses its listings; screens /product-categories, /product-categories/products, /shop/product-categories, /admin/shops/[id]/product-categories; one-time categorisation script with dry run / apply / restore | Merge to main (migration renumbering needed - see Risks) Merged to main on 3 Oct (was staging-only in the 3 Oct report). | -
142 | NEW-009 | Added after the target workbook | Explicit Save flow on admin screens (categories, privileges, user profiles) | n/a | COMPLETED | Live | Draft + Save Changes bar with dirty tracking, confirm step, unsaved-changes guard; privileges saved in one transaction (no half-applied role changes, last-admin protection, self-change blocked); profile edits limited to name/phone/status; every save audited. Editing moved to /admin/users/[id] and /admin/users/[id]/privileges | - | -
143 | NEW-010 | Added after the target workbook | Shop inventory fill when a category is added; per-shop prices | n/a | - | Live | Adding a category to a shop lists every live product in it with stock 100; packaged goods start at master MRP and on sale, loose goods / no-MRP start unpriced and off sale; owner sees how many need a price and saves prices in bulk (PATCH /api/shops/[id]/prices); buyers see 'Price on request' + 'Ask shop'. | - | -

## In progress
# | ID | Section | Feature | Priority | Status 3 Oct | Switched on? | What is built | Remaining scope / caveat | Blocked on
1 | GS-027 | Feature Master | Delivery slot | P0 | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: deliverySlots.enabled) | EXPRESS_30 / STANDARD_60 / SCHEDULED windows with feasibility preview, plus F5 slot capacity per shop / PIN code / default with an advisory lock so a slot cannot be overbooked (full slots shown unavailable). | Customer cannot pick a date or time for a scheduled delivery - a scheduled order is booked against the day it is placed. | -
2 | SM-002 | State Machines | Shop state machine | n/a | IN PROGRESS | Live once migration 0042 is applied | F1: shop lifecycle PENDING / ACTIVE / PAUSED / SUSPENDED / REJECTED / CLOSED derived by trigger, transitions enforced and logged; suspension policy with impact preview; KYC status per document (seller verification) and registration-fee status exist as separate fields. | APPLIED -> KYC_PENDING -> PAYMENT_PENDING -> VERIFIED are all one PENDING stage; show them as lifecycle stages (the data already exists). | -
3 | SM-004 | State Machines | Subscription state machine | n/a | IN PROGRESS | Live once migration 0042 is applied | F1: subscription lifecycle ACTIVE / PAUSED / CANCELLED / EXPIRED with enforced, logged transitions; PAYMENT_PENDING and per-date skips in the detailed status; subscription_events history. | DRAFT, RENEWAL_PENDING and per-cycle ORDER_CREATED / FULFILLED stages; SKIPPED and PAYMENT_FAILED as named lifecycle states. | -
4 | GA-005 | Gig Assignment Rules | Current load | P0 | IN PROGRESS | Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: dispatch.busyRidersAsFallback) | F3: riders with active jobs are ranked after free riders (up to maxActiveDeliveriesPerRider, default 2) instead of being excluded. | Multi-order batching ('unless batching is beneficial') not built. | -

## Blocked
# | ID | Section | Feature | Priority | Status 3 Oct | Switched on? | What is built | Remaining scope / caveat | Blocked on
1 | GS-001 | Feature Master | Mobile/email/Gmail login | P0 | IN PROGRESS | Live (email OTP); SMS OTP not available | Google, email magic link and a single mobile-or-email form; first-time /onboarding profile; My Profile with verified email change; checkout requires a mobile; admin can release a wrongly claimed number. Login rebuild now on main (was staging-only on 3 Oct). | SMS delivery of the OTP so a mobile number is proven (OTP provider seam ready). | D2 - SMS/OTP vendor with DLT registration
2 | GS-023 | Feature Master | E-commerce price benchmark | P1 | IN PROGRESS | Hidden from customers (externalPrices.showToCustomers = false) | External reference prices with source, time, location, URL, verification and audit history; shops and operations see them. | Turn on the customer display - one rule flip, no code. | D7 - lawful / licensed price source
3 | GS-028 | Feature Master | UPI/card/netbanking gateway | P0 | IN PROGRESS | Live | Cashfree live for wallet top-up only (create order, server verify, HMAC webhook, mock mode). Orders are paid by WALLET or COD; payment_method enum is still WALLET ¦ COD. | Per-order ONLINE payment via Cashfree hosted checkout (design signed off 1 Oct). | Go-ahead to build per-order payment, or a decision to launch wallet + COD only
4 | GS-073 | Feature Master | Payment gateway | P0 | IN PROGRESS | Live | Gateway plumbing reusable; refunds are wallet credits (journaled, idempotent). | Order payment intents, callbacks and gateway refunds. | Needs GS-028
5 | GS-074 | Feature Master | SMS/WhatsApp/email/push | P1 | IN PROGRESS | Email + in-app live (email needs SMTP) | Email and in-app notifications live; SMS, PUSH and WHATSAPP channels have a provider seam with no vendor. | Real SMS / push / WhatsApp providers. | D2 - vendor choice (DLT registration)
6 | WF-001 | Workflow Master | Customer product purchase | n/a | IN PROGRESS | Live | Every step works: location, search, eligible shops, comparison, cart, address, slot, payment by wallet or COD, order created; out-of-stock substitution; closed-shop confirmation. | Direct online payment for the order. | Needs GS-028
7 | RBAC-003 | RBAC Matrix | Manage own shop | n/a | UNCLEAR | Live | Shop owners manage their own shop; admins full. No 'Limited' operator scope for shop management. | Define what an operator may change on a shop, then implement. | Decision: what 'Limited' means
8 | SM-005 | State Machines | Payment state machine | n/a | IN PROGRESS | Live | Unchanged: payment_status CREATED / PENDING / SUCCESS / FAILED / REFUNDED (wallet top-ups only). | INITIATED -> AUTHORIZED -> CAPTURED -> RECONCILED; CHARGEBACK. | Per-order online payment go-ahead (GS-028 / NEW-007)
9 | SM-006 | State Machines | Issue state machine | n/a | IN PROGRESS | Live | Tickets linked to orders; returns 13-status machine; dispute cases have OPEN / TRIAGED / INVESTIGATING / RESOLUTION_PROPOSED / ESCALATED / RESOLVED; grievances still OPEN / IN_PROGRESS / RESOLVED / CLOSED. | Either add the four states to grievances or accept the dispute lifecycle as the issue state machine. | Decision: does the dispute lifecycle satisfy SM-006?
10 | NAV-003 | Navigation | Customer portal - Cart & Checkout | n/a | IN PROGRESS | Coupons: Off by default in code - switch on in Admin > Business rules (scripts/enable-new-features.sql does it for test) (rule: coupons.enabled) | Cart, address re-validation with actions, slot choice with capacity (F5), F7 order-level coupons (flat / %, minimum order, dates, total and per-customer limits, split by goods value, server-validated), F8 offers priced in cart, wallet / COD payment. | Online payment at checkout. | Needs GS-028

## Yet to start
# | ID | Section | Feature | Priority | Status 3 Oct | Switched on? | What is built | Remaining scope / caveat | Blocked on
1 | NEW-007 | Added after the target workbook | Direct per-order payments, tax invoicing, photo POD, accept timeout | n/a | YET TO START | - | Design only (DESIGN_PAYMENTS_INVOICING_POD_SLA.md). Re-checked 6 Oct: no ONLINE payment method, no invoice code, no photo proof of delivery, no accept-timeout auto-cancel. | Per-order online payment (needs the GS-028 go-ahead); tax invoicing (shop invoices goods, platform invoices its fees); photo proof of delivery; auto-cancel with full refund when a shop does not accept in time. The last three do not depend on the payment decision. | Go-ahead to build

## Changed since 3 Oct
ID | Feature | Status 3 Oct | Status 6 Oct | What changed | Delivered in
GS-001 | Mobile/email/Gmail login | IN PROGRESS | BLOCKED | Google, email magic link and a single mobile-or-email form; first-time /onboarding profile; My Profile with verified email change; checkout requires a mobile; admin can release a wrongly claimed number. Login rebuild now on main (was staging-only on 3 Oct). | PR #42/#43 (login rebuild to main)
GS-006 | Shop registration | COMPLETED | COMPLETED | 6 Oct: GST field added at registration; at least one of PAN / Udyam / GST / Shop Act required (135f29a). | -
GS-007 | Business KYC | IN PROGRESS | COMPLETED | Seller verification Parts 1-4: PAN, GSTIN, Udyam, FSSAI and Shop Act per shop with document upload, vendor check (provider-agnostic, Gridlines adapter + mock), name matching, cross-document consistency score, per-document status, admin review queue (approve / reject with reason / re-check), daily re-check and expiry job, auto-suspend on lapse, DPDP retention/erasure. | Seller verification 0a7fafa, 9cdec04, 896f082
GS-014 | Product images/specifications | IN PROGRESS | COMPLETED | Image store with several images per product/listing, primary, reorder, alt text; F10 moderation queue (pending -> approve / reject with reason) at /admin/image-moderation; existing photos stay live. | F10 0c9894f
GS-023 | E-commerce price benchmark | IN PROGRESS | BLOCKED | External reference prices with source, time, location, URL, verification and audit history; shops and operations see them. | Decision / dependency only
GS-027 | Delivery slot | IN PROGRESS | IN PROGRESS | EXPRESS_30 / STANDARD_60 / SCHEDULED windows with feasibility preview, plus F5 slot capacity per shop / PIN code / default with an advisory lock so a slot cannot be overbooked (full slots shown unavailable). | F5 742e6d2
GS-028 | UPI/card/netbanking gateway | IN PROGRESS | BLOCKED | Cashfree live for wallet top-up only (create order, server verify, HMAC webhook, mock mode). Orders are paid by WALLET or COD; payment_method enum is still WALLET ¦ COD. | Decision / dependency only
GS-033 | Shop order split | IN PROGRESS | COMPLETED | One order per shop from a multi-shop cart, plus F6 parent reference (GK-...) linking them; customer page /orders/group/[reference]. | F6 e95af6f
GS-054 | Referral program | IN PROGRESS | COMPLETED | Shop referral attribution, plus F11 customer referral code and link (/refer, /r/CODE): both rewarded on the friend's first delivered order; self-referral, duplicate-account and per-referrer cap guards; /admin/customer-referrals. | F11 db5c400
GS-072 | Maps/navigation | IN PROGRESS | COMPLETED | F4: road distance and travel time from Google Routes or OSRM behind one provider interface, cached per ~100 m cell and logged; arrival time for customer (tracking map) and rider (dashboard); straight-line fallback when off or failing. Navigation is a Google Maps deep link. | F4 e26d9c7
GS-073 | Payment gateway | IN PROGRESS | BLOCKED | Gateway plumbing reusable; refunds are wallet credits (journaled, idempotent). | Decision / dependency only
GS-074 | SMS/WhatsApp/email/push | IN PROGRESS | BLOCKED | Email and in-app notifications live; SMS, PUSH and WHATSAPP channels have a provider seam with no vendor. | Decision / dependency only
WF-001 | Customer product purchase | IN PROGRESS | BLOCKED | Every step works: location, search, eligible shops, comparison, cart, address, slot, payment by wallet or COD, order created; out-of-stock substitution; closed-shop confirmation. | Decision / dependency only
WF-008 | Shop onboarding | IN PROGRESS | COMPLETED | Registration with categories, PAN/Udyam/GST/Shop Act IDs (at least one), duplicate guard; seller document verification with rejection reasons the seller sees (correction loop); registration-fee gate before approval; service area (radius + PIN zones + minimum order + pause); category fill of the catalogue; approval. | Seller verification + 135f29a
RBAC-003 | Manage own shop | UNCLEAR | BLOCKED | Shop owners manage their own shop; admins full. No 'Limited' operator scope for shop management. | Decision / dependency only
SM-002 | Shop state machine | IN PROGRESS | IN PROGRESS | F1: shop lifecycle PENDING / ACTIVE / PAUSED / SUSPENDED / REJECTED / CLOSED derived by trigger, transitions enforced and logged; suspension policy with impact preview; KYC status per document (seller verification) and registration-fee status exist as separate fields. | F1 142d129
SM-003 | Gig state machine | IN PROGRESS | COMPLETED | F1: rider lifecycle ONBOARDING / OFFLINE / AVAILABLE / BUSY / ON_DELIVERY / SUSPENDED / REJECTED / INACTIVE, derived from the existing columns by a database trigger; transitions enforced in the database and every change logged with its actor (status_changes, /admin/status-changes). | F1 142d129
SM-004 | Subscription state machine | IN PROGRESS | IN PROGRESS | F1: subscription lifecycle ACTIVE / PAUSED / CANCELLED / EXPIRED with enforced, logged transitions; PAYMENT_PENDING and per-date skips in the detailed status; subscription_events history. | F1 142d129
SM-005 | Payment state machine | IN PROGRESS | BLOCKED | Unchanged: payment_status CREATED / PENDING / SUCCESS / FAILED / REFUNDED (wallet top-ups only). | Decision / dependency only
SM-006 | Issue state machine | IN PROGRESS | BLOCKED | Tickets linked to orders; returns 13-status machine; dispute cases have OPEN / TRIAGED / INVESTIGATING / RESOLUTION_PROPOSED / ESCALATED / RESOLVED; grievances still OPEN / IN_PROGRESS / RESOLVED / CLOSED. | Decision / dependency only
GA-005 | Current load | IN PROGRESS | IN PROGRESS | F3: riders with active jobs are ranked after free riders (up to maxActiveDeliveriesPerRider, default 2) instead of being excluded. | F3 950f730
NAV-001 | Customer portal - Home | IN PROGRESS | COMPLETED | Location picker, shops that deliver to you, featured / Kesari / Green shelves, product-search-first hero, and F9 home-page price comparison across nearby delivering shops (cheapest highlighted, unpriced loose goods skipped). | F9 62e53da
NAV-002 | Customer portal - Shop | IN PROGRESS | COMPLETED | Shop profile, catalogue, rating + reviews, opening hours, delivery options, and F8 shop offers (product or category, dated) shown on the shop page and priced in cart and checkout. | F8 3751c57
NAV-003 | Customer portal - Cart & Checkout | IN PROGRESS | BLOCKED | Cart, address re-validation with actions, slot choice with capacity (F5), F7 order-level coupons (flat / %, minimum order, dates, total and per-customer limits, split by goods value, server-validated), F8 offers priced in cart, wallet / COD payment. | F7 79300d8
NAV-013 | Gig portal - Profile | IN PROGRESS | COMPLETED | F2: rider edits own profile (vehicle, availability details) at /gig/profile; identity and bank changes go to an admin review queue, stored encrypted (/admin/rider-changes). | F2 142d129
NEW-007 | Direct per-order payments, tax invoicing, photo POD, accept timeout | YET TO START | YET TO START | Design only (DESIGN_PAYMENTS_INVOICING_POD_SLA.md). Re-checked 6 Oct: no ONLINE payment method, no invoice code, no photo proof of delivery, no accept-timeout auto-cancel. | -
NEW-008 | Product category master & shop product-category visibility | COMPLETED | COMPLETED | Merged to main on 3 Oct (was staging-only in the 3 Oct report). | -
NEW-010 | Shop inventory fill when a category is added; per-shop prices | - | COMPLETED | Adding a category to a shop lists every live product in it with stock 100; packaged goods start at master MRP and on sale, loose goods / no-MRP start unpriced and off sale; owner sees how many need a price and saves prices in bulk (PATCH /api/shops/[id]/prices); buyers see 'Price on request' + 'Ask shop'. | 0e2d77f, 1221420
- | Sign-out button in the header for every profile; owner name on the shop dashboard | - | - | UI polish (2db946b, 8512369). | 3 Oct
- | Migration number clash main vs staging | - | - | Resolved and merged (PR #42): migrations now run 0037 dispute_cases, 0038 login_profile, 0039 categories ... 0050 customer_referrals. | 3 Oct
- | Playwright acceptance tests | - | - | Updated to the current sign-in and wallet flows (b65fcec); 10/10 passing per docs/marketplace-features-2026-10/README.md. | 4 Oct

## Decisions & go-live
Type | Item | What is needed | Unblocks | Status
Decision | Per-order online payment (GS-028 / NEW-007) | Approve building per-order Cashfree payment, OR launch with wallet + COD only. | GS-028, GS-073, SM-005, NAV-003, WF-001, part of NEW-007 | Pending (no change since 3 Oct)
Decision / vendor | D2 - SMS / OTP vendor | Pick a DLT-registered SMS provider. | GS-001, GS-074 | Pending
Decision | D7 - external price source | Approve a lawful / licensed source for customer-visible reference prices. | GS-023 (one rule flip) | Pending
Decision | RBAC-003 - operator 'Limited' shop management | Define what an operator may change on a shop. | RBAC-003 | Pending
Decision | SM-006 scope | Accept the dispute lifecycle as the issue state machine, or add its states to grievances. | SM-006 | Pending
Decision | NEW-007 go-ahead | Approve building invoicing, photo POD and accept-timeout (these three do not need the payment decision). | NEW-007, NAV-010 invoices, GS-034 auto-cancel | Pending
Decision | D10 - cancellation policy | Confirm ACCEPTED / ASSIGNED (customer blocked) and PICKED_UP (goods-only refund). | NEW-006 sign-off | Pending (per 3 Oct)
Decision | Switch on F3-F11 in production | Decide which of the off-by-default features to switch on (Admin > Business rules). | GA-005, GS-072, GS-027, GS-033, NAV-001/002/003, GS-014, GS-054 | Pending
Vendor | Gridlines (seller verification) | Sandbox then live keys; written confirmation of FSSAI / GSTIN fields, Shop Act coverage, prices, IP whitelist, retention and DPA. | Automatic KYC checks for GS-007 (mock vendor until then) | Pending
Legal | Lawyer / CA confirmation | Retention period after closure (default 1,095 days) and Shop Act needs for non-MH / home sellers. | GS-007 compliance | Pending
Go-live blocker | No browser / QA sign-off | Nothing since Phase 1 has been signed off in a browser; status is code + automated tests. | Go-live | Open
Go-live blocker | Production migrations and cron jobs | Apply migrations up to 0050 and add the seller-verification and dispute-escalation crons (DEPLOY_RUNBOOK.md, docs/seller-verification/DEPLOY.md). | Everything delivered after Phase 1 | Open