## Summary
GoKesari: work in progress and gap analysis (local, staging, main), as of 25 Oct 2026, 03:50 UTC (09:20 IST)
Where | Branch / place | Commit | Latest migration | Note
gokesari.com (production) | main | 4a32386 | 0091 | Release #249 (25 Oct 01:48 UTC). Hostinger deploys main.
test.gokesari.com (staging) | staging | 438ab04 | 0091 | Merge of #253 (25 Oct 03:27 UTC). Hostinger deploys staging.
Local: this cloud session | claude/laughing-brown-c0vkcu (PR #251) | f952207 | 0091 | Working tree clean, nothing unpushed. staging merged in.
Local: owner's Mac | (not visible from the cloud) | - | - | Two sessions left Mac-only work to commit (section 5).
Recommended next steps
1. Merge #251 (CI re-running on the staging merge) and #254 into staging. Run migrations 0092-0094 on test.gokesari.com; they run on build (MIGRATE_ON_BUILD).
2. Re-test on test.gokesari.com: TC-FLD-114 (also the Excel upload), TC-CART-001, dates on order, wallet and admin pages, and #254's D-items.
3. Open one release PR staging -> main covering #250, #251, #252, #253 and #254. Apply production migrations in an approved window, one deploy at a time (E-02).
4. Bring main's 21 Oct status report (#223) back into staging so the two stay level.
5. On the Mac: commit the .claude/settings.json allowlist (claude/permissions-allowlist), and decide on the GoKesari spreadsheets from the 1 Oct session.
6. Delete the 6 stale branches in section 4, and archive the finished sessions in section 5.
Notes
Scope: GoKesari only. Sessions for other projects (Ladwani, Education, ATIP, Bkesari) are left out of this list as CLAUDE.md requires.
Comparisons use the full git history (the cloud clone was shallow at first and showed false gaps of 100+ commits).
'Commits not in staging' counts changes whose patch is not already in staging (git cherry), so squash-merged work counts as merged.
Which commit each site actually runs was not checked: the sites have no version endpoint, and the Hostinger connector needs authorising in claude.ai connector settings. The table assumes each site runs the head of its branch.
Release order: E-02 (25 Oct) showed two overlapping deploys stopped gokesari.com for about 14 minutes. Release one PR at a time, and check the site after each deploy.
34 branches named by sessions are no longer on GitHub: deleted after their PR merged, or the session wrote no code (checked for the two unclear GoKesari ones).

## Gap local-staging-main
Change | Kind | Local / open PR | staging (test) | main (prod) | Gap / action
Dates in India time everywhere: client components (React #418) and server pages (UTC times) | Code + test | PR #251 | No | No | Merge #251 into staging, test, then release
Voucher Excel upload refuses a past end date (TC-FLD-114, D-105) | Code + test | PR #251 | No | No | Same as above; re-test TC-FLD-114 after deploy
Owner decisions 25 Oct: D-103, D-57, D-91, D-25, D-96, D-23, D-69 | Code + migrations 0092-0094 | PR #254 | No | No | Merge #254; migrations run on test first, then production
Seven open bugs GAP-011 to GAP-019 (#250) | Code | - | Yes | No | Release staging -> main (no release PR open)
QA: staging re-tests of cart/checkout races D-102 (#252) | Docs | - | Yes | No | Goes with the next release
QA: production retest after #248; incident note E-02 (#253) | Docs | - | Yes | No | Goes with the next release; E-02 is Open (owner decision)
Feature status report 21 Oct (#223, merged straight into main) | Docs | - | No | Yes | Bring main back into staging (docs only)
Cart concurrent adds D-102 (#241, #243) and IST vouchers D-101 (#246) | Code | - | Yes | Yes | None - in both
.claude/settings.json permission allowlist (branch claude/permissions-allowlist) | Config | Owner's Mac only | No | No | Not on GitHub: run the commit on the Mac, open a PR
GoKesari spreadsheets on the Mac (session 'Moving local code to Claude Cloud', 1 Oct) | Docs | Owner's Mac only | No | No | Unanswered: copy into docs/ and push, or drop

## Open PRs
PR | Title | Base | State | CI | Mergeable | Migrations | Session
#251 | Dates in India time everywhere (React #418, UTC on server pages) + voucher upload past end date (TC-FLD-114) | staging | Draft | Green on 991fd2a; re-running on f952207 (staging merged in) | Yes (conflict in qa-defects.json resolved) | None | Pin India time in all client-side date formatting (this session)
#254 | Owner decisions of 25 Oct: D-103, D-57, D-91, D-25, D-96, D-23, D-69 | staging | Draft | test-split green; test running (03:40 UTC) | Yes; no conflict with #251 | 0092, 0093, 0094 | Feature status review and update #PR250+
(none) | Release staging -> main | main | Not opened | - | - | - | 3 commits waiting (section 2)

## Unmerged branches
Branch | Commits not in staging | Last commit | PR | Verdict
claude/laughing-brown-c0vkcu | 3 (+ merge) | 25 Oct | #251 open | Active - this session
claude/peaceful-pascal-jai8w2 | 8 | 25 Oct | #254 open | Active - waiting for CI
claude/trusting-allen-97xhex | 1 | 19 Oct | #212 closed, not merged | Superseded: staging fixes the same partition-identity problem differently (#211). Safe to delete
claude/serene-gates-7cymxj | 2 | 9 Oct | #121 squash-merged | Already in staging (sign-in consent box, 9 Oct report). Safe to delete
claude/busy-euler-5ipjns | 1 | 9 Oct | - | Same patch already in staging. Safe to delete
claude/tile-board-ui | 1 (WIP) | 9 Oct | none | Superseded by the shipped Tile Board (#112, #114). Safe to delete
claude/awesome-dijkstra-fmccpl | 18 | 3 Oct | #26 closed, not merged | Abandoned PostgreSQL -> MySQL port; the site stays on PostgreSQL. Delete or keep as archive
claude/amazing-cannon-5n3fro | 1 | 2 Oct | #27 closed, not merged | Old docs fix (deployment docs pointed at bkesari). Check docs, then delete

## Sessions
Session | Status | Last update (UTC) | Branch | State on GitHub | Waiting on | Suggested action
Pin India time in all client-side date formatting (this session) | Running | 25 Oct 03:40 | claude/laughing-brown-c0vkcu | PR #251 open | CI, then your review | Mark #251 ready and merge
Feature status review and update #PR250+ | Idle - review ready | 25 Oct 03:22 | claude/peaceful-pascal-jai8w2 | PR #254 open | CI | Review #254; plan migrations 0092-0094
Fix cart add race (D-99): 500 and lost units | Idle - review ready | 25 Oct 02:27 | claude/serene-curie-pwjjh2 | #240 closed, #252 merged | Its scheduled TC-FLD-114 voucher re-test at 19:00 UTC today | Let the re-test run after #251 is on test.gokesari.com
Gokesari.com test automation | Idle - done | 25 Oct 03:27 | claude/hopeful-cerf-x2gaow | #253 merged | - | Nothing; can be archived
Frequent "allow once" prompts | Idle - done (Mac step left) | 25 Oct 03:40 | claude/permissions-allowlist (Mac) | Not on GitHub | You: run the given commands on the Mac | Commit .claude/settings.json on the Mac and open a PR (yet to commit)
PostgreSQL frequent downtime | Idle - needs input | 24 Oct 21:30 | - | No code | You: which site, and what 'down' looks like | Answer it; it can then read Neon operations and logs
List all site cookies in the Cookie Policy | Idle - done | 25 Oct 01:48 | claude/confident-goldberg-c86f6q | #236, #249 merged | - | Archive
MySQL to PostgreSQL migration (release #245) | Idle - done | 24 Oct 20:30 | claude/focused-carson-4pa1e2 | #245 closed (superseded by #242) | - | Archive
Hostinger plugin installation (www redirect #224) | Idle - done | 24 Oct 21:07 | claude/hostinger-plugin-install-4js2f8 | #224 merged | - | Archive
Hostinger plugin installation (20 Oct) | Idle - needs input | 20 Oct 19:08 | - | No code | Approval of a .claude/settings.json edit | Superseded by the allowlist session; archive
DB Split | Idle - done | 21 Oct 00:44 | claude/vigilant-wright-0oyy7r | #222 merged | - | Archive
Inventory & Accounting module for shop owners | Idle - needs input | 15 Oct 18:27 | claude/nice-cori-6p1wb2 | #171, #172, #182 merged; released via #179 | An open 'Should I do it?' question | Read its last message; answer or archive
GitHub billing messages issue | Idle - needs input | 11 Oct 02:39 | claude/pensive-sagan-7kcr92 | - | PROD_DATABASE_URL secret / prod DB password reset | Confirm it was done (prod releases have run since), then archive
Older sessions, 3-14 Oct (crons not firing x2, Google Maps key, domain access, db:migrate output, deployment SQL scripts, mobile app, current location/login) | Idle - needs input / review ready | 3-14 Oct | various | Merged or no code | Old questions | Very likely overtaken by later releases; check, then archive
Older Mac sessions, 28 Sep-1 Oct (mobile login/OTP 'push staging?', Turbopack crash, git merge steps, gokesari.com not opening, moving local code to the cloud) | Idle | 28 Sep-2 Oct | Mac / various | - | Old questions; spreadsheets on the Mac | Archive; decide on the Mac spreadsheets
27 other GoKesari sessions, 6-21 Oct | Idle - done | 6-21 Oct | various | Their PRs merged | - | Nothing pending; can be archived