## Dealer programme
ID | Module | What it does | Priority | Build step | Migration | Commit(s) | Built | Local + CI tests | Staging (test.gokesari.com) | Production
FLAGS | Feature flags & geo areas | Four flags, per district; Maharashtra districts, Pune talukas / localities, PIN prefixes; DEALER role | P0 | 1 | 0101, 0102, 0103 | bc3f93a | Done | PASS | PASS — incl. operator refused | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
FEE-SLABS | Registration fee slabs | Admin-defined fee slabs by declared turnover (up to 20) | P0 | 1 | — | 973d520 | Done | PASS | Not run | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-DR-001 | Dealer registration | Application by type, mobile OTP, e-mail, documents per type, ₹1 bank check, agreement | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS — application with documents | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-DR-002 | Dealer documents & approval | Configurable document requirements; admin approval queue; suspend / reject / terminate | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS — approval; D-1 fixed | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-DR-003 | Dealer codes, link & QR | GKS-MH-<district>-code, share link /shop/register?ref=, QR, suspend / replace | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS — code, link, QR | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-DR-004 | Employees | Salespeople with optional Employee ID; legacy distributors migrated as dealers | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS — employee E01 | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-SH-001 | Self-registration attribution | Code typed or from ?ref=, optional Employee ID field | P0 | 3 | 0105 | 611f979 | Done | PASS | PASS — ?ref= prefill + Employee ID field | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-SH-002 | Dealer-assisted registration | Dealer registers with the owner; owner confirms with a code | P0 | 3 | 0105 | 611f979 | Done | PASS | PASS — owner code by e-mail | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-SH-003 | Duplicates | Phone / GSTIN / name within 150 m flagged; no commission | P0 | 3 | 0105 | 611f979 | Done | PASS | PARTIAL — automated tests only | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-RA-001 | Attribution & claims | 30-day leads (cap 200), attribution priority, dealer claims decided by staff | P0 | 3 | 0105 | 611f979 | Done | PASS | PASS — lead, attribution | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-SH-004 | Instant approval on GST/PAN + payment | Government check + gateway fee → approved; ready-for-upload e-mail; evidence log; retry when source down | P0 | 4 | 0106 | 4500808, 6db91cd | Done | PASS | PASS — approved + e-mail; D-2 fixed in code | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-CM-001 | Commission rules | Fixed / % / both, per shop type, district, milestone, versioned, admin only | P0 | 5 | 0107 | 22a74db | Done | PASS | PASS — rates; operator 403 | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-CM-002 | Ledger & payouts | Earned → approved → paid; cap with override; reversals; payouts with bank reference; CSV statement; hold for shops approved without documents | P0 | 5 | 0107 | 22a74db, 9e3e1b7 | Done | PASS | PASS — ₹100 + ₹150 earned; payout not run | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-CM-003 | Rating & bonus | Rating 0–10 by live shops (slabs), start rating, downgrade, bonus | P0 | 5 | 0107 | 22a74db | Done | PASS | PASS — activated shop counted | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-DB-001 | Dealer dashboard | Tiles, pending, performance by day / week / month, employees, areas; admin dealer list | P0 | 6 | — | 89f66b9, c9ea939 | Done | PASS | PASS — board, phone width | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-SP-001 | Support services | General (free), product upload, price update; admin charges; wallet / online pay; tickets; refunds | P0 | 7 | 0108 | c70e869 | Done | PASS | PASS — free, wallet, refund, online | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-GEO-001 | Coverage map & targets | Areas with dealers, shops, operational, target vs registered, gaps; drawn map | P1 | 8 | 0110 | bf53b23 | Done | PASS | PASS | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-AN-001 | Performance score | Weighted score (admin weights), ranked within district | P1 | 8 | — | bf53b23 | Done | PASS | PASS | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
GKS-AN-002 | Activation & 30-day activity | Per dealer and employee | P1 | 8 | — | bf53b23 | Done | PASS | PASS | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
APP | Mobile app parity | Website in the app shell; app links; downloads and print through the bridge | P0 | 9 | — | c89cf0b | Done | PASS | Not run | Released 28 Oct (ea7eecb, 8d6ef40) — flags off
DOCS | Guides & report | Admin guide, dealer onboarding guide, testing report | P0 | 10 | — | c9ea939 | Done | PASS | PASS | Released 28 Oct (ea7eecb, 8d6ef40) — flags off

## Feature flags
Flag | Switches on | Staging | Production
dealer_programme_enabled | Dealer application and portal, codes, attribution, commission, analytics | On, Pune only (28 Oct) | Off (checked 28 Oct)
gov_verification_auto_approval_enabled | Instant approval on GST/PAN + gateway fee | On, Pune only (28 Oct) | Off (checked 28 Oct)
dealer_rating_bonus_enabled | Rating bonus on commission | On, Pune only (28 Oct) | Off (checked 28 Oct)
paid_support_services_enabled | Paid Support services page | On, Pune only (28 Oct) | Off (checked 28 Oct)