## Billing v2 tracker
Billing v2 tracker — updated 02-Nov-2026 08.40 IST (released to gokesari.com, all billing flags off) — branch main 85a12aa6 (PR #324); staging 41ef27cc — testing report docs/billing/TESTING_REPORT.md
ID | Feature | Prompt § | Gap | Status | Environment | Web | Android | iOS | Test result | Notes / blockers
BV2-01 | Audit of existing billing / GST / accounts / sync code | §0 | — | Done | Prod (flags off) | n/a | n/a | n/a | — | docs/billing/AUDIT.md
BV2-02 | Feature flags (11) seeded OFF, admin screen labels | §0 | — | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local, both DB layouts) | Migration 0126
BV2-03 | Money-flow record per order (who received the money) | §5.1 | G2 | Done | Prod (flags off) | Done | n/a | n/a | Pass (local, both layouts) | order_money_flows per delivered order (mode, who received the money, TCS/TDS scope, s.9(5) delivery and food GST); admin summary on Tax returns; SETTLED once the payout is paid (daily job, D37)
BV2-04 | Tax engine (document kind, supply type, line tax, TCS, TDS scope, s.9(5), inter-state guard) | §2.4 | G7, G9 | Done | Prod (flags off) | Done | n/a | n/a | Pass (local, both layouts) | Engine drives the checkout guard, money flow, TCS/TDS scope and s.9(5); invoice kind follows the same rule (bill of supply for composition, Enrolment ID, s.9(5) restaurant)
BV2-05 | HSN/SAC master with UQC; product tax fields; unit→UQC mapping | §2.1–2.3 | G7 | Done | Prod (flags off) | Done | Not started | Not started | Pass (local, both layouts) | Dated HSN rate master with CSV import of the CBIC list (D37); unit→UQC map per shop with export block and fix list. Loading the CBIC list is data for the admin/CA
BV2-06 | Shop GST registration type (Regular/Composition/Enrolment ID/PAN-only) | §3.1–3.2 | G5 | Done | Prod (flags off) | Done | Not started | Not started | Pass (local, both layouts) | Registration type from the verified GSTIN, or declared Enrolment ID / PAN-only on the GST & PAN page; checkout guard; cancelled/suspended GSTIN blocks orders. Monthly re-check on the portal needs the GSP (B1)
BV2-07 | Inter-state checkout block for Enrolment-ID / composition shops | §3.3 | G5 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | Checkout refuses Enrolment-ID / composition inter-state and inactive GSTINs (billing_v2)
BV2-08 | Auto-approval also requires GST status; PAN-only professionals rule | §3.4–3.5 | G5 | Done | Prod (flags off) | Done | Not started | Not started | Pass (local) | Shops are approved at payment (owner decision); GST status enforced at checkout instead (D35). PAN-only supplies rule waits CA Q5 (B2), switch billing.panOnlyServiceRule
BV2-09 | Document types: debit note, receipt / refund voucher, challan, estimate | §4.1 | G9 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | acc_documents (0128): credit/debit note, receipt/refund voucher, challan, estimate; own series; books + stock; cancel; immutable
BV2-10 | 16-character numbering; invoice cancellation status | §4.2 | G9 | Blocked | Prod (flags off) | — | — | — | — | Invoice cancellation (mark only) + immutability triggers done; numbering format waits B4 (LEGACY 25 chars vs GST16)
BV2-11 | Mandatory invoice fields (UQC, state code, ECO GSTIN) | §4.3 | G9 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | Buyer GSTIN, ECO GSTIN, Enrolment ID, UQC on invoices issued under billing_v2
BV2-12 | Customer B2B GSTIN at checkout with live check | §4.4 | G9 | Done | Prod (flags off) | API done (checkout field UI: phase 8) | Via WebView | Via WebView | Pass (local, mock GSP) | orders.buyer_gstin (0127), format + GSP check; live check needs B1
BV2-13 | Credit note on every refund, by returned line, incl. cancellation before packing | §4.5 | G8 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local, both layouts) | Every refund after delivery gets a credit note; a return credits only the returned lines; cancellation before packing has no invoice, so no note (D17)
BV2-14 | Thermal 80 mm PDF, WhatsApp share, UPI QR, JSON | §4.6 | G9 | Done | Prod (flags off) | Done (API) | Via WebView | Via WebView | Pass (local) | 80 mm receipt PDF, invoice JSON, UPI QR on counter bills, WhatsApp share helper
BV2-15 | POS counter billing in the same series; offline in app | §4.7 | G9 | Done | Prod (flags off) | Done | Done (WebView) | Done (WebView) | Pass (local, both layouts) | Counter POS /shop/accounts/pos: device item list + bill queue (localStorage), syncs every 15 s and on reconnect; numbers given at sync in the order bills were made (gapless), clientRef makes re-sends idempotent (migration 0134); price / stock / removed-item conflicts per bill; camera scan where the browser has BarcodeDetector. Opening the page with no network at all still needs it loaded once (no service worker) — B7.
BV2-16 | s.9(5) delivery GST: rates by date, rider registration, per-order liability | §5.2 | G1 | Done | Prod (flags off) | n/a (server) | n/a | n/a | Pass (local) | GoKesari delivery-fee invoice GKS/2627/000001, catch-up sweep; behind delivery_9_5; CA to confirm (B2,B3)
BV2-17 | Restaurant s.9(5) as deemed supplier | §5.3 | G17 | Done | Prod (flags off) | Done | Done (WebView) | Done (WebView) | Pass (local, both layouts) | GoKesari invoices restaurant food in its GSTIN (GKS series, kind RESTAURANT), restaurant issues a bill of supply, Table 14(b)/15 + 3B, no TCS, payout withholds the GST (D34). Statutory row stays OFF until the CA confirms (B2)
BV2-18 | TCS s.52 from money flow, per-shop ledger and certificate, GSTR-8 | §5.4 | G3 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | Money-flow-driven TCS, GSTR-8 builder + schema, per-shop statement; GSP push needs B1
BV2-19 | TDS s.393: per PAN, credit-or-payout timing, Form 140 data, certificates | §5.5 | G4 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | Per-PAN exemption, quarterly statement (Form 140 data), per-shop statement; Aadhaar-as-PAN not handled
BV2-20 | Settlement ledger; monthly GoKesari fee invoice; wallet statement | §5.6 | G6 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local, both layouts) | Wallet + settlement statements; fee invoices stay one per payout cycle (D20)
BV2-21 | GoKesari's own GSTR-1 / 3B / 8, IMS, compliance dashboard | §5.7 | G16 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | GSTR-8 / GSTR-1 (+Table 15) / 3B / TDS generate, download, mark filed; calendar + reminders; e-invoice/IMS for own purchases: phase 6
BV2-22 | Shop accounting: chart of accounts, vouchers, auto-posting, reports | §6.1 | G12 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | GoKesari activity posted into books; Tally groups; new ledgers; journal/contra/stock journal; trial balance, balance sheet, COA, TCS/TDS credit
BV2-23 | Inventory: groups, godowns, transfers, reserve/dispatch, reports | §6.2 | — | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local, both layouts) | Stock journal between the online and in-shop counts, movement and ageing reports. Not built by decision D24: more godowns, separate stock groups (categories used), reserve-on-order / deduct-on-dispatch
BV2-24 | Purchases: IRP fetch via GSP; 2B/IMS accept/reject/pending | §6.3 | G16 | Blocked | Prod (flags off) | Done (mock GSP) | Via WebView | Via WebView | Pass (local) | IMS accept/reject/pending pushed via GSP; supplier e-invoices → draft bill for review; live IRP fetch and 2B pull need B1
BV2-25 | Canonical model, sync log, conflict queue, masters before vouchers | §7 | G12 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | Canonical model, sync_records, conflict queue, masters before vouchers, validation fix list (0130)
BV2-26 | File connectors: Tally Excel/.tsf/XML both ways, Busy, Marg, Vyapar, myBillBook, Zoho CSV, Odoo CSV | §8 | G13, G14 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local; Tally/Busy/Vyapar/myBillBook import, Tally XML round trip) | Layouts per tool; verify column maps on each tool version (B5)
BV2-27 | Live connectors: Tally Windows app, Zoho OAuth, Odoo API, public REST API | §8 | G15 | Done | Prod (flags off) | Done | n/a | n/a | Pass (local) | Tally connector 1.1.0 two-way books; connector flags; public REST API (OAuth2, scopes, OpenAPI); Zoho/Odoo adapters unchanged (invoices, credit notes, items) — contacts/bills via API not added (D28)
BV2-28 | Marketplace-standard reports (MTR B2B/B2C, settlement, TCS) | §8 | G10 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | MTR B2B/B2C report, order-level settlement, TCS statement; monthly notice
BV2-29 | Template pack and help pages (EN/HI/MR) | §8 | G13 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | Template pack + EN/HI/MR step guides per tool; screenshots of the other software need the software itself (B5)
BV2-30 | GSTR-1 for shops incl. Table 14 (ECO), IFF, nil/exempt | §9.3 | G11 | Done | Prod (flags off) | Done | Via WebView | Via WebView | Pass (local) | GSTR-1 (Table 14), IFF, prepare/save/compare/file with EVC through GSP (mock); live needs B1
BV2-31 | GSP connect, 2B/IMS, 3B, ledgers, e-invoice cancel, e-way bill update/cancel, CMP-08/GSTR-4, calendar | §9 | G11, G16 | Blocked | Prod (flags off) | Done (mock) | Via WebView | Via WebView | Pass (local, mock GSP) | All §9 flows built on the mock (returns, IMS, ledgers, IRN cancel/30-day/CRN, e-way Part B/extend/cancel, CMP-08/GSTR-4, call log, retries, session reminders); live needs B1; IRN needs GST16 numbering (B4)
BV2-32 | Security: GSP token encryption, operator read-only, GSP call log, retention policy | §10 | — | Done | Prod (flags off) | Done | — | — | Pass (local, both layouts) | GSP credentials encrypted, PAN encrypted, API secrets hashed, GSP call log, per-shop/client rate limits, tax documents and logs never deleted (D36); dealers/operators have no billing access (scenario 17 test)
BV2-33 | Mobile native: offline POS, Bluetooth print, native scanner, EVC | §14 | — | Blocked | — | n/a | Blocked | Blocked | — | Offline POS now runs in the apps through the WebView once the page is open (BV2-15). Still B7: Bluetooth thermal printing, native scanner, opening POS cold with no network, EVC — need a store release.
BV2-34 | Testing report (Test and Prod) | §13 | — | In progress | Prod (flags off) | — | — | — | Local: full suite passed on both layouts. Staging 01-Nov: test found D-110..D-117, fixed in PR #323 (CI both layouts). Prod 02-Nov 08.32 IST: migrations 0125-0135, post-deploy check 5/5, flags off | docs/billing/TESTING_REPORT.md (+ PDF). Pending: staging retest of D-110..D-117

## Gaps G1–G17
Gap | Tracker rows | Statuses
G1 | BV2-16 | Done
G2 | BV2-03 | Done
G3 | BV2-18 | Done
G4 | BV2-19 | Done
G5 | BV2-06, BV2-07, BV2-08 | Done
G6 | BV2-20 | Done
G7 | BV2-04, BV2-05 | Done
G8 | BV2-13 | Done
G9 | BV2-04, BV2-09, BV2-10, BV2-11, BV2-12, BV2-14, BV2-15 | Done, Blocked
G10 | BV2-28 | Done
G11 | BV2-30, BV2-31 | Done, Blocked
G12 | BV2-22, BV2-25 | Done
G13 | BV2-26, BV2-29 | Done
G14 | BV2-26 | Done
G15 | BV2-27 | Done
G16 | BV2-21, BV2-24, BV2-31 | Done, Blocked
G17 | BV2-17 | Done