## Summary
GoKesari feature status - 3 Oct 2026
Checked against code on origin/main @16dff81 and origin/staging @21e9d5a. Baseline: your 28-Sep report (148 rows) and the 2-Oct re-audit committed to the repo (155 rows). Status = DEVELOPMENT status read from code and tests, not QA sign-off.
Automated verification on main @16dff81 (fresh PostgreSQL 16, all migrations applied): fresh install, migrations 0000-0037 applied cleanly, typecheck clean, 885/885 tests passed in 62 files (vitest, 3 Oct 2026)
Headline | 28 Sep | 2 Oct | 3 Oct (now)
Total features tracked | 148 | 155 | 157
COMPLETED | 103 | 125 | 132
IN PROGRESS | 44 | 28 | 23
YET TO START | 0 | 1 | 1
UNCLEAR | 1 | 1 | 1
% complete | 70% | 81% | 84%
Wave | Wave name | Total | Completed | In progress | Yet to start | Unclear
1 | Access & security foundation | 8 | 6 | 1 | 0 | 1
2 | State model extension (map, don't replace) | 6 | 1 | 5 | 0 | 0
3 | Location & serviceability | 4 | 3 | 1 | 0 | 0
4 | Shop onboarding completion | 5 | 3 | 2 | 0 | 0
5 | Discovery & local price comparison | 6 | 4 | 2 | 0 | 0
6 | Checkout & payments | 7 | 1 | 6 | 0 | 0
7 | Shop fulfilment | 4 | 4 | 0 | 0 | 0
8 | Society module | 6 | 6 | 0 | 0 | 0
9 | Delivery & gig assignment | 14 | 12 | 2 | 0 | 0
10 | Notifications | 2 | 1 | 1 | 0 | 0
11 | Support, returns & disputes | 6 | 6 | 0 | 0 | 0
12 | Finance & settlement | 8 | 8 | 0 | 0 | 0
13 | Subscription completion | 1 | 1 | 0 | 0 | 0
14 | Admin & operations console | 6 | 6 | 0 | 0 | 0
15 | Analytics & KPIs | 16 | 16 | 0 | 0 | 0
16 | P1 MVP features | 6 | 5 | 1 | 0 | 0
17 | Phase 2 features | 13 | 11 | 2 | 0 | 0
18 | Completed - preserve & add regression tests | 30 | 30 | 0 | 0 | 0
19 | Delivered after 28-Sep report (new rows) | 9 | 8 | 0 | 1 | 0
| TOTAL | 157 | 132 | 23 | 1 | 1

## MVP flow status
Step | Actor | End-to-end flow | Status (3 Oct) | Feature IDs | What works in code | Gap / caveat
1 | Customer | Login -> Location | READY (caveat) | GS-001, GS-004, GS-070 | Google, email magic link and mobile-number login (code goes to the account EMAIL) all work; location by saved address, device position or PIN. | Mobile number is claimed, not proven - no SMS OTP until an SMS vendor is chosen (D2). Login rebuild + first-time profile sits on staging, not main.
2 | Customer | Discover serviceable shop | READY | GS-019, GS-010, NEW-005 | Shops that deliver to the location, nearest first, radius + extra PIN zones + paused shops honoured. | -
3 | Customer | Search product -> View shop/price | READY | GS-020, GS-021, GS-022 | Product search limited to serviceable shops; every shop selling a product with per-unit / per-pack comparison and Lowest price. | Home-page comparison widgets (NAV-001) and shop-page offers (NAV-002) are enhancements, not blockers.
4 | Customer | Add to cart -> Address -> Slot | PARTIAL | GS-024/025, GS-026, GS-027, NAV-003 | Single + multi-shop cart; cart re-validated against address; checkout hard-blocks non-serviceable shops; EXPRESS_30 / STANDARD_60 / SCHEDULED windows with a feasibility preview. | No slot capacity limits and no real scheduled slot times (GS-027). No order-level coupons (NAV-003).
5 | Payment | Pay -> Payment confirmed | GAP | GS-028, GS-073, SM-005, NEW-007 | Orders can be paid by WALLET (wallet is topped up through Cashfree UPI/card/netbanking) or COD with risk limits. | No direct per-order online payment: orders.payment_method is WALLET ¦ COD only. Design signed off 1 Oct (NEW-007) - no code. Payment state machine (AUTHORIZED/CAPTURED/RECONCILED/CHARGEBACK) not started.
6 | Order | Create parent/child shop orders | PARTIAL | GS-032, GS-033 | Checkout creates one order per shop from a multi-shop cart, each with its own validation and delivery charge. | No master/parent order linking the children - the customer gets N order numbers for one checkout.
7 | Shop | Accept -> Pick -> Pack -> READY | READY | GS-034, GS-035, GS-036, WF-002 | Accept / reject (reject = full refund + restock), per-line picking, substitution with customer approval, pack -> READY. | Accept-timeout auto-cancel not built (designed 1 Oct). SLA reporting not built.
8 | Delivery | Auto assign -> Pickup | READY | GA-006, GS-039, GA-009, GS-041, WF-003 | Rider auto-requested on READY; ranking by distance + reliability + fairness + society preference; offers expire in 2 min with cron retry; pickup code required. | Busy riders are excluded rather than down-ranked; no batching (GA-005). No radius widening. No QR pickup.
9 | Delivery | Out for delivery -> Customer OTP/POD | READY | GS-043, GS-042, WF-005, NEW-004 | Customer delivery OTP (5 attempts), ops override with proof note; arrival checkpoints; live tracking now visible to customer and ops; Google Maps deep link for navigation. | No photo/signature POD (designed 1 Oct). No in-app turn-by-turn.
10 | Completion | DELIVERED -> Order complete | READY | SM-001, NAV-004 | Full order state machine with history and audit (ACCEPTED, ASSIGNED, PICKED_UP, FAILED, RETURNED, DISPUTED); customer can rate, report, return, dispute. | -
11 | Operations | Admin monitors exceptions/refunds | READY | GS-065, GS-066, NAV-015/016/017, GS-057, GS-058 | Live operations dashboard, order monitoring with tracking, ops exceptions queue, returns + return pickups, refunds (wallet), NEW dispute case queue with auto-escalation. | Refunds go to wallet, not back to card/UPI (needs GS-028). Real SMS/WhatsApp alerts not live (D2) - email + in-app only.
12 | Finance | Commission -> Settlement -> Gig earnings | READY | GS-061..064, WF-010, GS-031 | Commission snapshotted per order; weekly shop settlements and rider payouts with full lifecycle; earnings with slots/incentives; reconciliation + exception queue. | Payouts are recorded, not pushed to a bank API (manual transfer).

## Go-live priority status
Priority ID | Development item | Status (3 Oct) | Detail
P0-A | RBAC / permission conflicts | MOSTLY DONE | RBAC-002, RBAC-007, RBAC-010 resolved. RBAC-003 (Operator 'Limited' shop management) still UNCLEAR - needs a business definition.
P0-B | Order/payment state machines | PARTIAL | Order state machine complete. Payment state machine (SM-005) not started - waits on per-order gateway (GS-028).
P0-C | Authentication / consent / audit | MOSTLY DONE | Consent (incl. new ops consent view) and append-only audit logs done. Login works but mobile is not SMS-verified (D2).
P0-D | Location / address / serviceability | DONE | GS-004, GS-010, GS-026 complete.
P0-E | Shop and product discovery | DONE | Search, all-shops-for-product and local comparison complete.
P0-F | Cart / checkout / delivery slot | PARTIAL | Cart + checkout work; slot capacity and coupons missing (GS-027, NAV-003).
P0-G | Payment gateway / payment status | GAP | Cashfree live for wallet top-up only. Per-order online payment not built (GS-028 / NEW-007). Launchable only as wallet + COD.
P0-H | Order creation / shop order split | PARTIAL | Per-shop orders created; no parent order (GS-033).
P0-I | Shop accept/reject / pick / pack | DONE | Complete; accept-timeout escalation not built.
P0-J | Basic gig assignment | DONE | Readiness + distance + availability + fallback all in place.
P0-K | Pickup / delivery OTP-POD / completion | DONE | Pickup code + delivery OTP; photo POD not built.
P0-L | Admin / operator order monitoring | DONE | Order monitoring, live ops, exceptions queue, live tracking for ops.
P0-M | Basic refunds / support / notifications | MOSTLY DONE | Refunds (wallet), returns, grievances, disputes done. Notifications: email + in-app only; SMS/WhatsApp/push blocked on D2.
P0-N | Commission / settlement ledger / gig earnings | DONE | Complete.
P0-O | Gig payout / reconciliation | DONE | Complete (payout execution is manual).
GO-LIVE | Controlled production launch | NOT READY | Blockers: (1) per-order payment decision - build GS-028 or launch wallet+COD only; (2) no functional/browser QA sign-off; (3) migrations up to 0037 to apply in production; (4) main and staging both have a migration 0037 - must be renumbered before staging is merged.
P1-A | Society module | DONE | All 6 society features complete (map pin picker on society form outstanding).
P1-B | Ratings / moderation | DONE | Shop + rider ratings with moderation.
P1-C | Expanded subscriptions | DONE | Weekday schedules, address/society on generated orders. SM-004 extra states outstanding.
P1-D | Core KPI dashboard | DONE | /admin/analytics and /shop/analytics.
P2-A | Advanced gig optimisation | PARTIAL | Reliability + fairness done; load-based ranking / batching (GA-005) and routing ETA (GS-072) not.
P2-B | Segmentation / campaigns / referrals | PARTIAL | Segments + campaigns done; customer referral rewards not built (GS-054).
P2-C | Advanced fraud / risk rules | DONE | 11 risk rules, hourly cron, /admin/risk.
P2-D | E-commerce price benchmarking | BLOCKED | Code complete but hidden from customers until a lawful/licensed source is approved (D7) - one rule flip.
P3-A | Full KPI suite | DONE | KPI-001..015 implemented.

## All features
Seq | Wave | Wave name | ID | Module | Feature / Requirement | Priority | Status (28-Sep) | Status (2-Oct) | Status (3-Oct, now) | Change vs 28-Sep | Change vs 2-Oct | Delivered in | What is built (verified in code) | Remaining scope | Blocked on | Evidence (file) | Where it is
1 | 1 | Access & security foundation | RBAC-002 | Security | Place order (Customer, Admin only) | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Wave 1 | Personal orders for every role; B2B a separate flow (order_type PERSONAL/B2B, buyer_shop_id, ORDER_PLACE_B2B) | - | - | src/server/db/schema.ts (orderTypeEnum); src/server/authz/permissions.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
2 | 1 | Access & security foundation | RBAC-007 | Security | Assign delivery | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Wave 1 + Slices 3-4 + Phase C | Decision taken: shop retry KEPT but bounded and configurable. Assignment is automatic on READY; 'Find rider now' is now a bounded search (rider_searches, dispatch_attempts) with retry interval, attempt cap, total time limit, window expiry and manual cooldown; shop sees status, can retry or stop; every attempt logged; duplicate assignment impossible | - | - | src/server/services/delivery-assignment.ts; src/app/api/orders/[id]/assign/route.ts; drizzle/0027 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
3 | 1 | Access & security foundation | RBAC-003 | Security | Manage own shop (Operator Limited) | n/a | UNCLEAR | UNCLEAR | UNCLEAR | No change | - | - | Nothing built. Only AUDIT_LOG_VIEW_LIMITED exists; no 'Limited' scope for shop management | Define Operator 'Limited' scope, then implement | Decision pending: what 'Limited' means | src/server/authz/permissions.ts:109 (AUDIT_LOG_VIEW_LIMITED only) | Not built
4 | 1 | Access & security foundation | GS-002 | Identity & Access | Role-based access control | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Wave 1 + Phase 2 | SOCIETY_ADMIN role; society roles scoped per membership (ADMIN/OPERATOR/RESIDENT) | - | - | src/server/authz/permissions.ts; src/server/db/schema.ts (userRoleEnum) | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
5 | 1 | Access & security foundation | GS-001 | Identity & Access | Mobile/email/Gmail login | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | Progressed | Progressed | staging 3 Oct (5f64ea2) | Google + email magic link + mobile-number login with a code sent to the account email (main). On STAGING ONLY (5f64ea2): rebuilt single form taking mobile OR email, first-time /onboarding profile (name, gender, mobile, address with map pin), My Profile with verified email change, checkout requires a mobile, admin can release a wrongly-claimed number | SMS delivery of the OTP so a mobile number is proven; promote the staging login rebuild to main | D2 - SMS/OTP vendor (DLT registration) | src/server/otp/*; staging: src/app/signin/page.tsx, src/app/onboarding/page.tsx, drizzle/0037_login_profile.sql | Main: partial. Login rebuild on staging only - not merged to main
6 | 1 | Access & security foundation | GS-070 | Security | Privacy/consent management | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Wave 1 | Marketing consent grant/withdraw with history; profile toggle; /api/consents/marketing | - | - | src/server/services/consents.ts; src/components/marketing-consent-toggle.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
7 | 1 | Access & security foundation | GS-067 | Admin | Audit logs | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Wave 1 | audit_logs append-only, enforced by DB trigger | Dedicated Auditor role (optional) | - | drizzle/0018_audit_logs_append_only.sql; src/server/services/audit.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
8 | 1 | Access & security foundation | RBAC-010 | Security | View orders (role-scoped) | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase 2 + Phase 4 + Phase J | ORDER_VIEW_OWN / _SHOP / _ANY; society dashboard shows society deliveries without customer PII; operator holds ORDER_VIEW_ANY and now has its own order-monitoring screen with status/shop/date filters | - | - | src/server/authz/permissions.ts:284-306; src/app/admin/orders/page.tsx; src/components/order-monitoring-table.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
9 | 2 | State model extension (map, don't replace) | SM-001 | Orders | Order state machine | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | ACCEPTED, ASSIGNED, PICKED_UP, FAILED, RETURNED, DISPUTED added; full transition table + history + audit | - | - | src/server/db/schema.ts:123 (orderStatusEnum) | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
10 | 2 | State model extension (map, don't replace) | SM-005 | Payments | Payment state machine | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | - | Unchanged. payment_status is still CREATED / PENDING / SUCCESS / FAILED / REFUNDED | AUTHORIZED/CAPTURED, RECONCILED, CHARGEBACK | Waits on per-order gateway payments (GS-028) - design signed off 1 Oct, build not started | src/server/db/schema.ts:187 (paymentStatusEnum); docs/gokesari-audit/DESIGN_PAYMENTS_INVOICING_POD_SLA.md | Partial code on `main` @16dff81
11 | 2 | State model extension (map, don't replace) | SM-002 | Shop Onboarding | Shop state machine | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase G | shop_status unchanged (PENDING_APPROVAL/APPROVED/REJECTED/SUSPENDED/INACTIVE), but the suspension half now has a real lifecycle: configurable policy per open-order status, impact preview, per-order decisions, owner notice, reinstatement; plus an orders_paused switch | KYC_PENDING, PAYMENT_PENDING, VERIFIED vs ACTIVE, CLOSED | - | src/server/db/schema.ts:49; src/server/services/shop-suspension.ts; drizzle/0031 | Partial code on `main` @16dff81
12 | 2 | State model extension (map, don't replace) | SM-003 | Delivery | Gig state machine | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase C | delivery_partner_status unchanged (REGISTERED/UNDER_REVIEW/APPROVED/REJECTED/SUSPENDED/DEACTIVATED); the delivery leg gained arrival checkpoints (arrived_at_shop_at, arrived_at_customer_at), which is where DELIVERING-style granularity now lives | KYC_PENDING, BLOCKED, DELIVERING on the partner itself | - | src/server/db/schema.ts:961; drizzle/0027 | Partial code on `main` @16dff81
13 | 2 | State model extension (map, don't replace) | SM-004 | Subscription | Subscription state machine | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase 2 | Final states locked; subscription_events history; resume/cancel notifications. Enum unchanged: ACTIVE/PAUSED/CANCELLED/COMPLETED/PAYMENT_PENDING | DRAFT, RENEWAL_PENDING, ORDER_CREATED/FULFILLED states | - | src/server/db/schema.ts:211 | Partial code on `main` @16dff81
14 | 2 | State model extension (map, don't replace) | SM-006 | Support | Issue state machine | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | Progressed | Progressed | 3 Oct (af2b451) | Tickets linked to orders; returns have a 13-status state machine; NEW: dispute cases carry exactly the missing states (TRIAGED / INVESTIGATING / RESOLUTION_PROPOSED / ESCALATED). Grievance ladder itself still OPEN / IN_PROGRESS / RESOLVED / CLOSED | Either add the four states to grievances, or decide that dispute cases satisfy SM-006 and close it | Decision: does the dispute lifecycle satisfy SM-006? | src/server/db/schema.ts:424 (grievanceStatusEnum); src/lib/dispute-states.ts | Partial code on main @16dff81
15 | 3 | Location & serviceability | GS-004 | Location | PIN / address selection | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 1 + Phase B | 'Deliver to' location: saved address, device position or PIN, remembered in a cookie. Phase B added Maps Places address search, a 'save this place' path, and recipient name / recipient mobile / Home-Work-Other on addresses | - | - | src/lib/geo/provider.ts; src/components/location-bar.tsx; drizzle/0026 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
16 | 3 | Location & serviceability | GS-010 | Shop Onboarding | Service radius / delivery zone | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 1 + Phase B | shops.service_radius_km (1-50 km) editable by the shop; Phase B added extra delivery zones by PIN code (shops.delivery_pincodes), honoured by serviceability, checkout and discovery | - | - | src/server/services/serviceability.ts; src/server/db/schema.ts:691; drizzle/0019, 0026 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
17 | 3 | Location & serviceability | GS-026 | Checkout | Address validation | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 1 + Phase 2 + Phase B | Cart warning, then a checkout hard block when a shop does not deliver to the address. Phase B added a cart-validation service that re-checks every shop in the cart against the chosen location - deliverable, paused, unavailable items, minimum order, delivery charge, closed-now - each with an action, re-running when the address changes | - | - | src/server/services/cart-validation.ts; src/app/api/cart/validate/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
18 | 3 | Location & serviceability | GS-072 | Integration | Maps/navigation | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase C | Google Geocoding (one call per shop, cached), Places address search, haversine distance, turn-by-turn handed off as a Google Maps deep link for riders and return pickups, and a feasibility-based estimated-minutes figure at checkout | Road routing, a real ETA from a routing API, in-app navigation | - | src/server/services/geocoding.ts; src/server/services/delivery-assignment.ts:1282; src/server/services/delivery-feasibility.ts:72 | Partial code on `main` @16dff81
19 | 4 | Shop onboarding completion | GS-007 | Shop Onboarding | Business KYC | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | - | GSTIN, PAN and FSSAI numbers are captured and verified/rejected by operations with their own status enums and encrypted storage; an image store now exists (stored_images, /api/images) that documents could use | Document upload/storage wired to a shop; one tracked KYC status instead of separate GST/PAN states | - | src/app/api/shops/[id]/gst¦pan¦compliance/route.ts; src/server/db/schema.ts:775-781; src/server/services/image-store.ts (unused for KYC) | Partial code on `main` @16dff81
20 | 4 | Shop onboarding completion | GS-008 | Shop Onboarding | Payment reference verification | P0 | IN PROGRESS | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | IN PROGRESS -> COMPLETED | 2 Oct (bbc6140) | approveShop() now refuses unless fee_payment_status = PAID (derived from the shop_payments ledger), naming the amount outstanding; waived fee (zero snapshot) is written PAID at registration; approval queue shows each pending shop's fee state. Gate is on the transition only - shops already APPROVED untouched | - | - | src/server/services/shops.ts (approveShop); src/components/shop-approval-panel.tsx; tests/integration/registration-fees.test.ts | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
21 | 4 | Shop onboarding completion | GS-009 | Shop Onboarding | Shop categories | P0 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Shop-categories release (1 Oct) | Admin-configurable category master: shop_categories + shop_category_mapping (many per shop), seeded from the 44 shop types and backfilled; registration requires at least one category; owners edit their own on /shop; operators/admins manage the list at /admin/shop-categories and assign per shop; uncategorised shops flagged; categories feed search relevance | - | - | src/server/services/shop-categories.ts; src/app/admin/shop-categories/page.tsx; drizzle/0035 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
22 | 4 | Shop onboarding completion | GS-015 | Catalog | MRP / selling price / discount | P0 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase I (1/3) | MRP governance: a selling price above an enforced MRP is refused everywhere a shop price is written (assertPriceWithinMrp on both catalogue write paths); MRP provenance and verification status; MRP drops notify shops without touching prices; shop MRP corrections decided by operations; violations report; MRP shown on the product page | - | - | src/server/services/mrp-governance.ts; src/server/services/catalogue.ts:617,710; src/app/admin/mrp/page.tsx; drizzle/0032 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
23 | 4 | Shop onboarding completion | WF-008 | Shop Onboarding | Shop onboarding | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | Progressed | Progressed | 2 Oct (bbc6140) | Service area complete (radius + extra PIN zones + minimum order + pause switch); categories required at registration; duplicate-registration guard; MRP/price correction queues; registration-fee gate before approval now ENFORCED (GS-008) | KYC document upload wired to a shop (see GS-007) | - | src/components/shop-register-form.tsx; src/server/services/shops.ts | Partial code on main @16dff81
24 | 5 | Discovery & local price comparison | GS-019 | Search | Shop search | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 1 | Shops that deliver to the location, nearest first, with distance | - | - | src/server/services/serviceability.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
25 | 5 | Discovery & local price comparison | GS-020 | Search | Product search | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 1 | Product search limited to serviceable shops, nearest first | - | - | src/app/search/page.tsx; src/server/services/catalogue.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
26 | 5 | Discovery & local price comparison | GS-021 | Search | All shops selling product | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 1 | /products/{id}: every shop selling the product | - | - | src/app/products/[id]/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
27 | 5 | Discovery & local price comparison | GS-022 | Comparison | Local price comparison | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 1 | Per-unit / per-pack comparison, 'Lowest price', delivers-to-you | - | - | src/app/products/[id]/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
28 | 5 | Discovery & local price comparison | NAV-001 | Customer | Customer portal - Home | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Slice 1 + Shop-categories release | Location picker, 'Shops that deliver to you', featured / Kesari / Green shelves, and a product-search-first hero (the category grid was deliberately removed) | Price-comparison widgets on the home page itself | - | src/app/page.tsx | Partial code on `main` @16dff81
29 | 5 | Discovery & local price comparison | NAV-002 | Customer | Customer portal - Shop | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase 2 + Phase B | Shop rating + recent reviews; opening hours with closed-now state; delivery options now shown (fee, free-above threshold, pickup-only, minimum order) | Offers / vouchers on the shop page | Order-level coupons do not exist yet (vouchers are wallet top-up only) | src/app/shops/[slug]/page.tsx:118-133 | Partial code on `main` @16dff81
30 | 6 | Checkout & payments | GS-027 | Checkout | Delivery slot | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | - | EXPRESS_30 / STANDARD_60 / SCHEDULED windows with a feasibility preview that will not promise a window the system cannot back, plus an estimated-minutes figure | Slot capacity rules; real scheduled slot times | - | src/server/services/delivery-feasibility.ts; src/app/api/checkout/delivery-windows/route.ts (no capacity anywhere) | Partial code on `main` @16dff81
31 | 6 | Checkout & payments | GS-028 | Payments | UPI/card/netbanking gateway | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Design only (1 Oct) | Cashfree is live but only for wallet top-up (create-order, server-side verify, HMAC webhook, mock mode). Orders are still WALLET or COD only. A full design for per-order ONLINE payment was signed off on 1 Oct (generalise payments.purpose, orders.payment_method += ONLINE, migration 0036) - no code written | Build per-order gateway payment | D1 taken (pay-per-order via Cashfree); build not scheduled | src/server/services/payments.ts; src/app/api/checkout/route.ts:29 (WALLET¦COD); docs/gokesari-audit/DESIGN_PAYMENTS_INVOICING_POD_SLA.md | Partial code on `main` @16dff81
32 | 6 | Checkout & payments | GS-073 | Integration | Payment gateway | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Design only (1 Oct) | Gateway plumbing exists and is reusable; refunds today are wallet credits through refundDeliveredOrder (journaled, idempotent). Gateway refunds and order payments are designed, not built | Gateway refunds; order payments | Depends on GS-028 | src/server/services/finance.ts (refundDeliveredOrder); docs/gokesari-audit/DESIGN_PAYMENTS_INVOICING_POD_SLA.md | Partial code on `main` @16dff81
33 | 6 | Checkout & payments | GS-033 | Orders | Shop order split | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | - | Checkout already produces one order per shop from a multi-shop cart, with per-shop validation and delivery charges | A master order row linking the child orders (single customer-facing reference) | - | src/server/services/cart.ts:258-295; src/server/services/orders.ts:424 | Partial code on `main` @16dff81
34 | 6 | Checkout & payments | GS-031 | Payments | Payment reconciliation | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | Reconciliation records + exception queue (order/payment/rider/settlement/payout) | - | - | src/app/api/finance/reconciliation/route.ts; src/server/services/finance.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
35 | 6 | Checkout & payments | NAV-003 | Customer | Customer portal - Cart & Checkout | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase B | Cart now re-validates against the chosen location and shows each issue with an action (change address / add items / remove these items); minimum order and paused shops enforced | Order-level coupons; gateway payment | Vouchers are wallet-top-up only; coupons at checkout not built | src/server/services/cart-validation.ts; src/server/services/vouchers.ts (top-up only) | Partial code on `main` @16dff81
36 | 6 | Checkout & payments | WF-001 | Orders | Customer product purchase | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Slice 1 + Slices 3-4 + Phase 2 + Phase B + Oct release | Location, eligible shops, comparison, serviceability block, substitution, minimum order, paused shops, and (1 Oct) ordering from a closed shop behind an explicit customer confirmation with two shop alerts | Direct gateway payment for orders (GS-028) | Depends on GS-028 | src/server/services/orders.ts; src/server/db/schema.ts:1600 (placed_while_closed) | Partial code on `main` @16dff81
37 | 7 | Shop fulfilment | GS-034 | Orders | Shop accept/reject | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | Shop accept / reject (reject = full refund + restock); ops exceptions flag 'Shop not accepting' and 'Shop slow to prepare' | Accept-timeout auto-cancel (designed 1 Oct, not built) | - | src/server/services/fulfilment.ts; src/server/services/ops-exceptions.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
38 | 7 | Shop fulfilment | GS-036 | Orders | Pick and pack | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | Per-line picking, pack -> READY | SLA reporting | - | src/server/services/fulfilment.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
39 | 7 | Shop fulfilment | NAV-006 | Shop | Shop portal - Dashboard | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase J | getShopDashboard(): the operator's day built entirely from live queries - today's orders and money, what needs action, stock alerts, ratings, performance. No sample numbers | - | - | src/server/services/dashboards.ts:63; src/app/shop/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
40 | 7 | Shop fulfilment | WF-002 | Orders | Shop fulfillment | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | Notify -> accept -> stock check -> substitute/remove -> pick -> pack -> READY | - | - | src/server/services/fulfilment.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
41 | 8 | Society module | GS-005 | Location | Society identification | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Society membership; address <-> society link; orders.society_id | - | - | src/server/services/societies.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
42 | 8 | Society module | GS-044 | Society | Society registration | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Registration -> operator verify/reject/suspend/reinstate | Map pin picker on the society form | - | src/app/api/societies/[id]/decision/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
43 | 8 | Society module | GS-045 | Society | Authorized Gig worker whitelist | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Authorised rider list by mobile; add / revoke / preferred; audited | - | - | src/app/api/societies/[id]/riders/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
44 | 8 | Society module | RBAC-009 | Security | Whitelist Gig workers | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Society-scoped roles; SOCIETY_MANAGE_ANY for platform staff | - | - | src/server/authz/permissions.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
45 | 8 | Society module | GS-047 | Society | Delivery instructions | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 + Phase C | Society gate notes + customer landmark/instructions on the rider job; Phase C added a gate entry mode, an optional security-desk contact shared with the rider only if the society enables it, and a customer-at-gate notice | - | - | drizzle/0027; src/server/services/societies.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
46 | 8 | Society module | NAV-014 | Society | Society portal - Dashboard | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | /society/{id} dashboard (rules, residents, riders, shops, deliveries) | - | - | src/app/society/[id]/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
47 | 9 | Delivery & gig assignment | GA-006 | Delivery | Shop readiness | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | Rider requested automatically when the shop marks READY | - | - | src/server/services/delivery-assignment.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
48 | 9 | Delivery & gig assignment | GS-039 | Delivery | Job assignment | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 + Phase C | Auto-trigger on READY; cron retry; no re-offer to decliners; Phase C made the whole search bounded and logged (rider_searches, dispatch_attempts) with admin-tunable retry interval, attempt cap and time limit | - | - | src/server/services/delivery-assignment.ts; drizzle/0027 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
49 | 9 | Delivery & gig assignment | GA-005 | Delivery | Current load | P0 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | - | Unchanged: a rider already on a delivery is EXCLUDED from the candidate pool (row-locked to stop races). Ranking weights are distance + reliability + fairness only - no load term | Lower priority instead of exclusion; multi-order batching | - | src/server/services/delivery-assignment.ts:81-137 (DISPATCH_WEIGHTS has no load term), :5 ('not-already-busy') | Partial code on `main` @16dff81
50 | 9 | Delivery & gig assignment | GA-009 | Delivery | No worker fallback | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 + Phase C | Offers expire after 2 min; auto-retry; shop notified. Phase C added a bounded search with a total time limit, delivery-window expiry, manual cooldown, a stop control and a 'rider assignment failed' notification; 'No rider' is an ops exception | Radius widening | - | src/server/services/delivery-assignment.ts; src/server/notifications/templates.ts (DELIVERY_SEARCH_STOPPED) | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
51 | 9 | Delivery & gig assignment | GA-001 | Delivery | Society authorization | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Exclusive society -> only listed riders offered | - | - | src/server/services/delivery-assignment.ts:97 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
52 | 9 | Delivery & gig assignment | GA-002 | Delivery | Society preferred partner | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Listed / preferred riders ranked first | - | - | src/server/services/delivery-assignment.ts:97-137 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
53 | 9 | Delivery & gig assignment | GS-040 | Delivery | Society priority assignment | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Society preference in dispatch ranking | - | - | src/server/services/delivery-assignment.ts:123 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
54 | 9 | Delivery & gig assignment | WF-003 | Delivery | Gig assignment | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 + Phase 2 + Phase C | Auto-trigger, whitelist filter, priority, reliability, fairness, escalation, bounded retry with a full attempt log | Load batching tracked under GA-005 | - | src/server/services/delivery-assignment.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
55 | 9 | Delivery & gig assignment | WF-004 | Society | Society authorized delivery | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 + Phase C | Identify society -> rider list -> filter/priority -> security alert; Phase C added gate entry mode and the security-desk contact | - | - | src/server/services/delivery-assignment.ts; src/server/services/societies.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
56 | 9 | Delivery & gig assignment | GS-041 | Delivery | Pickup OTP/QR | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | Pickup code issued on accept; rider must enter it | QR variant | - | src/server/services/delivery-assignment.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
57 | 9 | Delivery & gig assignment | GS-043 | Delivery | Delivery OTP/POD | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | Customer delivery OTP (5 attempts); operations override with a proof note; 'Delivery code locked' is an ops exception | Photo / signature proof of delivery (designed 1 Oct, not built) | - | src/server/services/delivery-assignment.ts; docs/gokesari-audit/DESIGN_PAYMENTS_INVOICING_POD_SLA.md | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
58 | 9 | Delivery & gig assignment | GS-042 | Delivery | Live tracking | P0 | IN PROGRESS | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | IN PROGRESS -> COMPLETED | 2 Oct (bbc6140) | Tracking API with role/privacy checks + polling LiveTrackingMap, now MOUNTED: on /orders inside an in-flight order card that has a rider, and on /admin/orders behind a per-row Track toggle. isTrackableOrderStatus() limits polling to orders actually in flight. Rider privacy: area only until pickup, no ETA from a stale fix | - | - | src/app/orders/page.tsx:199; src/components/order-monitoring-table.tsx:171; src/lib/tracking.ts; tests/unit/tracking.test.ts | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
59 | 9 | Delivery & gig assignment | WF-005 | Delivery | Delivery | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Slices 3-4 + Phase 2 + Phase C | Pickup code -> OTP -> delivered; failed -> returned; society access notes; Phase C added 'arrived at shop' / 'arrived at customer' checkpoints with notifications, navigation deep links and rider-side privacy | In-app turn-by-turn navigation (deep link to Google Maps instead) | - | src/server/services/delivery-assignment.ts:599; src/components/delivery-partner-dashboard.tsx:634-667 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
60 | 9 | Delivery & gig assignment | NAV-013 | Gig | Gig portal - Profile | n/a | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | - | The profile page is read-only: vehicle type and registration are displayed, identity and bank details are stored encrypted and deliberately not shown. The only PATCH on a partner is operations' verification actions | Rider self-edit of KYC / vehicle / bank details | - | src/app/gig/profile/page.tsx; src/app/api/delivery-partner/[id]/route.ts:18-25 (admin actions only) | Partial code on `main` @16dff81
61 | 10 | Notifications | GS-055 | Notifications | Order notifications | P0 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase F | Notification framework: in-app + email, queued per channel with retries and backoff, delivery log, dead-letter handling, per-category preferences (security notices always on), read/unread, and templates for every order, return, delivery, shop, wallet, subscription, society and security event. Sent by a one-minute cron | - | - | src/server/notifications/{channels,templates,types}.ts; src/server/services/notifications.ts; src/app/api/cron/notifications/route.ts; drizzle/0030 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
62 | 10 | Notifications | GS-074 | Integration | SMS/WhatsApp/email/push | P1 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase F | Email and in-app are real and live (email needs SMTP in production; without it email is skipped, not failed). SMS, PUSH and WHATSAPP are enum values with a provider seam and one plug-in point | Real SMS / push / WhatsApp providers | D2 - vendor choice (India needs DLT registration) | src/server/notifications/channels.ts:5,57; src/server/db/schema.ts:227 | Partial code on `main` @16dff81
63 | 11 | Support, returns & disputes | GS-056 | Support | Report an issue | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | 'Report a problem' on an order -> linked ticket | - | - | src/app/api/orders/[id]/issue/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
64 | 11 | Support, returns & disputes | GS-057 | Support | Returns/refunds | P0 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Slice 6 (Finance) + Phase E | Full returns workflow: request (reason, condition, quantity, photos, comments) -> automatic policy validation (window, per-reason policy, evidence, quantity held under an order lock) -> approval -> rider pickup (offer / accept / en route / handover code / failure and bounded re-offer) -> goods received -> inspection -> refund through the existing journaled refundDeliveredOrder, idempotent per return, 13 statuses with history. Customer, shop, operations and rider screens; rider pickup fee credited as an earning | Gateway refund (money back to card/UPI rather than wallet) | Depends on GS-028 / GS-073 | src/server/services/returns.ts; src/server/services/return-pickups.ts; src/app/returns, /shop/returns, /admin/returns; drizzle/0029 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
65 | 11 | Support, returns & disputes | GS-058 | Support | Dispute management | P0 | IN PROGRESS | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | IN PROGRESS -> COMPLETED | 3 Oct (af2b451) | Dispute case entity (migration 0037): order, raiser, disputed amount, payment-method snapshot; 8 statuses (OPEN, TRIAGED, INVESTIGATING, RESOLUTION_PROPOSED, ESCALATED, RESOLVED, REJECTED, WITHDRAWN) with a transition table; auto-escalation by amount (default Rs 2,000) and age (default 48 h, hourly cron); escalated cases admin-only; refund resolution goes through refundDeliveredOrder with a double-pay guard; customer sees outcome, not working notes; /admin/disputes queue | Refund to card/UPI (today refunds are wallet credit) - depends on GS-028/GS-073 | - | src/lib/dispute-states.ts; src/server/services/disputes.ts; src/app/admin/disputes/page.tsx; src/app/api/cron/dispute-escalation/route.ts; drizzle/0037_dispute_cases.sql; tests/integration/disputes.test.ts | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
66 | 11 | Support, returns & disputes | RBAC-011 | Security | Refund approval | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | ORDER_REFUND for operator/admin | - | - | src/server/authz/permissions.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
67 | 11 | Support, returns & disputes | WF-007 | Support | Return/refund | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Slice 6 (Finance) + Phase 2 + Phase E | Report -> return request -> validation -> approval -> rider pickup -> inspection -> refund, end to end, with who bears the cost configurable per reason | Replacement instead of refund | - | src/server/services/returns.ts; src/server/services/return-pickups.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
68 | 11 | Support, returns & disputes | NAV-004 | Customer | Customer portal - Orders | n/a | IN PROGRESS | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | IN PROGRESS -> COMPLETED | 2-3 Oct (bbc6140, af2b451) | Rate an order, report a problem, request a return (/orders/{id}/return, /returns), live tracking panel on in-flight orders, and raise / follow a dispute case | - | - | src/app/orders/page.tsx | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
69 | 12 | Finance & settlement | GS-061 | Finance | Shop commission | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | Commission by default / shop type / shop, snapshotted per order | - | - | src/server/services/finance.ts:216 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
70 | 12 | Finance & settlement | GS-062 | Finance | Shop settlement | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | Weekly shop settlements DRAFT -> APPROVED -> PAID, full lifecycle | - | - | src/app/api/finance/settlements/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
72 | 12 | Finance & settlement | GS-064 | Finance | Gig payout | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | Weekly rider payouts, full lifecycle | - | - | src/app/api/finance/rider-payouts/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
73 | 12 | Finance & settlement | WF-010 | Finance | Settlement | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | GMV -> commission -> refunds -> adjustments -> settlement -> payout -> reconciliation | - | - | src/server/services/finance.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
74 | 12 | Finance & settlement | RBAC-012 | Security | Settlement visibility | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | Settlement visibility per role; operator exceptions-only view | - | - | src/server/authz/permissions.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
75 | 12 | Finance & settlement | NAV-010 | Shop | Shop portal - Finance | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | /shop/finance | - | - | src/app/shop/finance/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
76 | 12 | Finance & settlement | NAV-012 | Gig | Gig portal - Earnings | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Slice 6 (Finance) | Rider earnings with status + payouts list, now with a per-earning breakdown | - | - | src/app/gig/orders/page.tsx; src/app/api/delivery-partner/earnings/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
71 | 12 | Finance & settlement | GS-063 | Finance | Gig earnings | P0 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Slice 6 (Finance) + Phase D | Configurable time slots (including overnight, weekdays, validity, priority) each with their own base, per-km, minimum, order component and peak bonus; incentives by order count, daily/weekly target, distance, peak hour and campaign; every earning stores its full breakdown plus append-only ledger lines and idempotent award rows; with no slots configured the result is exactly the old base + per-km; admin screen with a 'try a delivery' calculator. 12 unit tests on the calculation engine | - | - | src/server/services/delivery-earnings.ts; src/app/admin/rider-earnings/page.tsx; drizzle/0028; tests/unit/earnings-calc.test.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
77 | 13 | Subscription completion | WF-006 | Subscription | Subscription | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Subscription orders carry address/society -> fulfilment -> dispatch -> settlement | - | - | src/server/services/subscriptions.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
78 | 14 | Admin & operations console | GS-065 | Admin | Global dashboard | P0 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase 4 + Phase J | getAdminDashboard() + /admin/dashboard: the marketplace's operational picture from live queries - in-flight orders by status, today's money, KPI cards, open risk flags, shops by status. No sample numbers | - | - | src/server/services/dashboards.ts:207; src/app/admin/dashboard/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
79 | 14 | Admin & operations console | GS-066 | Admin | Operator console | P0 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Slice 6 (Finance) + Phase 4 | Two exception queues: finance exceptions at /admin/finance/exceptions, and a general operations queue at /admin/exceptions with 12 categories (shop not accepting, shop slow, awaiting substitution, no rider, self-delivery overdue, rider not picked up, stuck after pickup, delivery code locked, failed delivery, returned-no-decision, disputed, past promised time), elapsed-time thresholds, severity and precedence | - | - | src/server/services/ops-exceptions.ts; src/app/admin/exceptions/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
80 | 14 | Admin & operations console | NAV-015 | Operator | Operator portal - Operations | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Slice 6 (Finance) + Phase 4 | /admin/finance/exceptions and the non-finance /admin/exceptions queue with per-row actions | - | - | src/app/admin/exceptions/page.tsx; src/components/ops-exception-actions.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
81 | 14 | Admin & operations console | NAV-016 | Operator | Operator portal - Orders | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase 4 | /admin/orders order-monitoring screen with status, shop and date-range filters, gated on ORDER_VIEW_ANY | - | - | src/app/admin/orders/page.tsx; src/components/order-monitoring-table.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
82 | 14 | Admin & operations console | NAV-017 | Admin | Admin portal - Control Tower | n/a | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase 4 + Phase J | /admin/dashboard: live operations, in-flight orders, KPIs, risk flags, shop approvals, with links into orders, finance and exceptions | - | - | src/app/admin/dashboard/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
83 | 14 | Admin & operations console | NAV-019 | Admin | Admin portal - Security | n/a | IN PROGRESS | IN PROGRESS | COMPLETED | IN PROGRESS -> COMPLETED | IN PROGRESS -> COMPLETED | 3 Oct (ef25ca0) | Fraud side: /admin/risk over 11 risk rules. NEW consent side: /admin/consents behind CONSENT_VIEW (operator + admin) - per-type consent standing vs live policy version, recent grant/withdrawal trail, per-person audited lookup; stored IP never returned | - | - | src/app/admin/consents/page.tsx; src/server/authz/permissions.ts (CONSENT_VIEW); tests/integration/consents.test.ts | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
84 | 15 | Analytics & KPIs | GS-069 | Analytics | Marketplace KPI dashboard | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | /admin/analytics (marketplace) and /shop/analytics (own shop) | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
85 | 15 | Analytics & KPIs | KPI-001 | Analytics | GMV | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | GMV plus a daily GMV trend | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
86 | 15 | Analytics & KPIs | KPI-002 | Analytics | Order fill rate | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | delivered / placed in window | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
87 | 15 | Analytics & KPIs | KPI-003 | Analytics | Shop acceptance time | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | duration from placed to accepted | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
88 | 15 | Analytics & KPIs | KPI-004 | Analytics | Pick-pack time | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | duration from accepted to READY | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
89 | 15 | Analytics & KPIs | KPI-005 | Analytics | Assignment time | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | duration from READY to rider accepted | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
90 | 15 | Analytics & KPIs | KPI-006 | Analytics | Delivery time | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | duration from pickup to delivered | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
91 | 15 | Analytics & KPIs | KPI-007 | Analytics | On-time delivery rate | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | delivered within the promised window | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
92 | 15 | Analytics & KPIs | KPI-008 | Analytics | Cancellation rate | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | cancelled / placed | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
93 | 15 | Analytics & KPIs | KPI-009 | Analytics | Refund rate | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | refund rate by count and by value | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
94 | 15 | Analytics & KPIs | KPI-010 | Analytics | Customer repeat rate | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | ordering vs repeat vs returning customers | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
95 | 15 | Analytics & KPIs | KPI-011 | Analytics | Subscription retention | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | retained subscriptions period over period | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
96 | 15 | Analytics & KPIs | KPI-012 | Analytics | Gig acceptance rate | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | offers accepted / offers made | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
97 | 15 | Analytics & KPIs | KPI-013 | Analytics | Gig utilization | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | active delivery time against availability | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
98 | 15 | Analytics & KPIs | KPI-014 | Analytics | Shop retention | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | shops active last period still active | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
99 | 15 | Analytics & KPIs | NAV-018 | Analytics | Admin portal - Analytics | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | /admin/analytics and /shop/analytics | - | - | src/server/services/analytics.ts; src/app/admin/analytics/page.tsx; src/app/api/analytics/kpis/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
100 | 16 | P1 MVP features | GS-014 | Catalog | Product images/specifications | P1 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase E + Phase I (3/3) | Image store (stored_images, /api/images) with validation, browser-side shrink and a safe fallback; several images per product or per listing, primary image, reorder, replace, delete, alt text. products.specifications exists | Image moderation (the product-approval queue does not review images) | - | src/server/services/product-images.ts; src/server/services/image-store.ts; src/app/shop/products/[id]/images/page.tsx; drizzle/0034 | Partial code on `main` @16dff81
101 | 16 | P1 MVP features | GS-035 | Orders | Substitution approval | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Slices 3-4 | Shop proposes a substitute; customer approves/rejects; price difference refunded | - | - | src/app/api/orders/[id]/items/[itemId]/substitution/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
102 | 16 | P1 MVP features | GS-059 | Ratings | Shop rating | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Eligibility, one per order, average, anonymous reviews, moderation | - | - | src/server/services/ratings.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
103 | 16 | P1 MVP features | GS-060 | Ratings | Gig rating | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Rider rating: average visible to rider and operations | - | - | src/server/services/ratings.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
104 | 16 | P1 MVP features | GA-007 | Delivery | Reliability | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Reliability score (30-day completions vs failures/declines) in ranking | - | - | src/server/services/delivery-assignment.ts:126 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
105 | 16 | P1 MVP features | GA-008 | Delivery | Fairness | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Fairness penalty per offer received today | - | - | src/server/services/delivery-assignment.ts:85 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
106 | 17 | Phase 2 features | GS-003 | Identity & Access | Multi-role user account | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | user_role_grants; active role switcher in the header; /api/me/roles; admin revoke; shop/rider/society flows grant roles; staff roles exclusive | - | - | src/server/services/roles.ts; src/app/api/me/roles/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
107 | 17 | Phase 2 features | GS-018 | Inventory | Reorder level / quantity | P1 | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS -> COMPLETED | - | Phase I (2/3) | Low-stock threshold, reorder level and reorder quantity resolved at listing -> product -> shop level with an explicit opt-out and the source reported; reserved / available / on-hand; one notification per new alert; hand-edited stock now writes the ledger and re-checks alerts | Analytics-driven replenishment suggestions (enhancement) | - | src/server/services/inventory-alerts.ts; src/app/shop/inventory/page.tsx; drizzle/0033 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
108 | 17 | Phase 2 features | GS-023 | Comparison | E-commerce price benchmark | P1 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | Phase I (1/3) | External reference prices with source, time, location, URL and verification plus an audit history, kept strictly separate from MRP and selling price and never written into either. Visibility is a rule: shops and operations see them, customers do not | Turn on the customer display (code is in place, the rule is off) | D7 - licensed/lawful source for customer-visible reference prices. Flip externalPrices.showToCustomers; no code change | src/server/services/price-references.ts:271; src/server/config/rules.ts:187-196; src/app/admin/price-references/page.tsx | Partial code on `main` @16dff81
109 | 17 | Phase 2 features | GS-030 | Payments | COD | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | COD at checkout with risk limits; shop opt-in; rider/operator cash confirmation; collection nets into finance batches; deposits at /admin/cod; COD refunds as wallet credit | - | - | src/server/services/cod.ts; src/app/admin/cod/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
110 | 17 | Phase 2 features | GS-046 | Society | Security notification | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Society security alert on rider acceptance (opt-in) | - | - | src/server/services/societies.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
112 | 17 | Phase 2 features | GS-052 | Marketing | Customer segmentation | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | Segments by PIN, society, delivered orders, recency, lapse, spend; consent required; counts only | - | - | src/server/services/marketing.ts:89 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
113 | 17 | Phase 2 features | GS-053 | Marketing | Shop promotional campaigns | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | Shop campaigns with budget, shop rate limit and customer frequency caps | - | - | src/server/services/marketing.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
115 | 17 | Phase 2 features | WF-009 | Marketing | Marketing campaign | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | Audience -> consent -> budget -> operations approval -> send -> tracking (opened, converted, revenue) | - | - | src/app/api/admin/campaigns/route.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
116 | 17 | Phase 2 features | NAV-009 | Shop | Shop portal - Marketing | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | /shop/marketing (customers, segments, campaigns, COD setting) | - | - | src/app/shop/marketing/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
117 | 17 | Phase 2 features | KPI-015 | Analytics | Marketing conversion | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | Campaign conversion within the attribution window | - | - | src/server/services/analytics.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
118 | 17 | Phase 2 features | GS-068 | Admin | Fraud/risk rules | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 3 | 11 risk rules (customer, rider, shop), hourly cron, review queue /admin/risk; a HIGH customer flag pauses COD | - | - | src/server/services/risk.ts; src/app/admin/risk/page.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
111 | 17 | Phase 2 features | GS-049 | Subscription | Recurring vegetables/daily goods | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Phase 2 | Weekday schedules; generated orders carry address/society | - | - | src/server/services/subscriptions.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
114 | 17 | Phase 2 features | GS-054 | Marketing | Referral program | P1 | IN PROGRESS | IN PROGRESS | IN PROGRESS | No change | - | - | What exists is SHOP referral attribution: referral codes, usable-code resolution, attributing a registering shop to a code, performance report. There is no customer referral | Customer referral rewards and the fraud checks that go with them | - | src/server/services/referrals.ts (attributeShopToCode, no customer path) | Partial code on `main` @16dff81
119 | 18 | Completed - preserve & add regression tests | GS-006 | Shop Onboarding | Shop registration | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
120 | 18 | Completed - preserve & add regression tests | GS-011 | Catalog | Product master | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
121 | 18 | Completed - preserve & add regression tests | GS-012 | Catalog | Shop catalog mapping | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
122 | 18 | Completed - preserve & add regression tests | GS-013 | Catalog | Bulk product upload | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
123 | 18 | Completed - preserve & add regression tests | GS-016 | Inventory | Stock quantity | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
124 | 18 | Completed - preserve & add regression tests | GS-017 | Inventory | Low-stock threshold | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | Extended by GS-018 (three-level thresholds, Phase I) | - | - | - | Live (pre-existing)
125 | 18 | Completed - preserve & add regression tests | GS-024 | Cart | Single-shop cart | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
126 | 18 | Completed - preserve & add regression tests | GS-025 | Cart | Multi-shop cart | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
127 | 18 | Completed - preserve & add regression tests | GS-029 | Payments | Wallet | P1 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
128 | 18 | Completed - preserve & add regression tests | GS-032 | Orders | Order creation | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
129 | 18 | Completed - preserve & add regression tests | GS-037 | Delivery | Gig worker onboarding | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
130 | 18 | Completed - preserve & add regression tests | GS-038 | Delivery | Online/offline status | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
131 | 18 | Completed - preserve & add regression tests | GS-048 | Subscription | Daily milk subscription | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
132 | 18 | Completed - preserve & add regression tests | GS-050 | Subscription | Subscription payment | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
133 | 18 | Completed - preserve & add regression tests | GS-051 | Subscription | Skip/pause/resume/cancel | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
134 | 18 | Completed - preserve & add regression tests | GS-071 | Security | Data access controls | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
135 | 18 | Completed - preserve & add regression tests | RBAC-001 | Security | Browse/search | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
136 | 18 | Completed - preserve & add regression tests | RBAC-004 | Security | Manage catalog | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
137 | 18 | Completed - preserve & add regression tests | RBAC-005 | Security | Upload product lists | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
138 | 18 | Completed - preserve & add regression tests | RBAC-006 | Security | Verify shop | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
139 | 18 | Completed - preserve & add regression tests | RBAC-008 | Security | Manage own availability | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
140 | 18 | Completed - preserve & add regression tests | RBAC-013 | Security | Manage users/roles | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
141 | 18 | Completed - preserve & add regression tests | RBAC-014 | Security | System configuration | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | Extended by NEW-001 (business-rules console, Phase A-J) | - | - | - | Live (pre-existing)
142 | 18 | Completed - preserve & add regression tests | RBAC-015 | Security | Audit logs | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
143 | 18 | Completed - preserve & add regression tests | GA-003 | Delivery | Distance | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
144 | 18 | Completed - preserve & add regression tests | GA-004 | Delivery | Availability | P0 | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
145 | 18 | Completed - preserve & add regression tests | NAV-005 | Customer | Customer portal - Subscriptions | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
146 | 18 | Completed - preserve & add regression tests | NAV-007 | Shop | Shop portal - Catalog | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
147 | 18 | Completed - preserve & add regression tests | NAV-008 | Shop | Shop portal - Orders | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
148 | 18 | Completed - preserve & add regression tests | NAV-011 | Gig | Gig portal - Jobs | n/a | COMPLETED | COMPLETED | COMPLETED | No change | - | Pre-existing | - | - | - | - | Live (pre-existing)
149 | 19 | Delivered after 28-Sep report (new rows) | NEW-001 | Admin | Business-rules console (admin-tunable thresholds) | n/a | - | COMPLETED | COMPLETED | New | - | Phase A-J | platform_settings + /admin/settings: nine rule groups (otp, dispatch, riderEarnings, returns, images, notifications, suspension, mrp, externalPrices) with code defaults, server-side validation and an audit trail. This is what makes 'configurable' true across the other features | Per-field forms instead of JSON editing | - | src/server/config/rules.ts; src/server/services/settings.ts; src/app/admin/settings/page.tsx; drizzle/0025 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
150 | 19 | Delivered after 28-Sep report (new rows) | NEW-002 | Shop Onboarding | Shop suspension policy, impact preview & review | n/a | - | COMPLETED | COMPLETED | New | - | Phase G | Configurable policy per open-order status (cancel & refund / continue / hold for review); impact preview before suspending and an impact list with per-order decisions after; the owner is told reason, time, expected action and impact; new orders stop at once; held orders are neither advanced by the shop nor dispatched; reinstatement. Review queue at /admin/suspensions | - | - | src/server/services/shop-suspension.ts; src/server/services/shop-suspension-guard.ts; src/app/admin/suspensions/page.tsx; drizzle/0031 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
151 | 19 | Delivered after 28-Sep report (new rows) | NEW-003 | Orders | Order placed while the shop is closed | n/a | - | COMPLETED | COMPLETED | New | - | 1 Oct release | A customer can choose to order from a closed shop after an explicit confirmation; the order is flagged placed_while_closed, the shop gets an alert at once and a second one when it opens, and the customer is told the shop is closed and told again when it opens. Opening hours are evaluated in IST | - | - | src/server/db/schema.ts:1600,1653; src/server/services/shop-opening.ts; src/server/notifications/templates.ts | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
152 | 19 | Delivered after 28-Sep report (new rows) | NEW-004 | Delivery | Rider arrival checkpoints & customer notices | n/a | - | COMPLETED | COMPLETED | New | - | Phase C | 'Arrived at shop' and 'arrived at customer' checkpoints on the delivery, each with a notification; rider-side privacy (area only until pickup, never the customer's name, phone or handover codes) | - | - | drizzle/0027; src/server/services/delivery-assignment.ts:597-612; src/components/delivery-partner-dashboard.tsx | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
153 | 19 | Delivered after 28-Sep report (new rows) | NEW-005 | Shop Onboarding | Minimum order value, pause new orders, extra delivery PIN zones | n/a | - | COMPLETED | COMPLETED | New | - | Phase B | Per-shop minimum order value (CHECK-constrained), a 'pause new orders' switch and extra delivery PIN codes beyond the radius; serviceability, discovery, cart validation and checkout all honour them | - | - | src/server/db/schema.ts:691-702,875; drizzle/0026 | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
154 | 19 | Delivered after 28-Sep report (new rows) | NEW-006 | Orders | D10 cancellation & refund policy (verified) | n/a | - | COMPLETED | COMPLETED | New | - | Phase H | Cancellation policy verified against code, history and tests at every stage (CONFIRMED / ACCEPTED / PREPARING / READY / ASSIGNED / PICKED_UP / OUT_FOR_DELIVERY) for customer and shop; two real gaps fixed; retained delivery fee journaled; 13 characterization tests | Confirm the ACCEPTED/ASSIGNED and PICKED_UP treatments with the business owner | D10 - confirm the three extension statuses | tests/integration/d10-cancellation-policy.test.ts; docs/gokesari-audit/D10_VERIFICATION.md | Merged to `main` @16dff81 — needs migrations up to 0037 + QA; not QA-signed
155 | 19 | Delivered after 28-Sep report (new rows) | NEW-007 | Payments | Direct per-order payments, tax invoicing, photo POD, accept timeout | n/a | - | YET TO START | YET TO START | New | - | Design signed off 1 Oct | Design only - no code, no migrations. Covers ONLINE payment method via Cashfree hosted checkout per order, shop invoices goods while the platform invoices its own fees, photo proof of delivery on the existing handover, and auto-cancel with full refund when a shop does not accept in time | The whole build | Awaiting go-ahead after design review; decisions D1 and D6 already taken | docs/gokesari-audit/DESIGN_PAYMENTS_INVOICING_POD_SLA.md | Design document on `main` @16dff81 - nothing implemented
156 | 19 | Delivered after 28-Sep report (new rows) | NEW-008 | Catalog | Product category master & shop product-category visibility | n/a | - | - | COMPLETED | New | New row | staging 3 Oct (74fda32, 7d13b7b, bf5a81a) | product_categories as a master (unique names, permanent General category guarded by trigger); shop_product_categories decides which products a shop sees; removing a category moves products to General; removing it from a shop pauses its listings; screens /product-categories, /product-categories/products, /shop/product-categories, /admin/shops/[id]/product-categories; one-time categorisation script with dry run / apply / restore | Merge to main (migration renumbering needed - see Risks) | - | staging: drizzle/0038_product_category_management.sql; src/server/services/product-categories.ts; scripts/categorise-products.ts; tests/integration/product-categories.test.ts | Staging only - not merged to main
157 | 19 | Delivered after 28-Sep report (new rows) | NEW-009 | Admin | Explicit Save flow on admin screens (categories, privileges, user profiles) | n/a | - | - | COMPLETED | New | New row | 2 Oct (dbbcc88) | Draft + Save Changes bar with dirty tracking, confirm step, unsaved-changes guard; privileges saved in one transaction (no half-applied role changes, last-admin protection, self-change blocked); profile edits limited to name/phone/status; every save audited. Editing moved to /admin/users/[id] and /admin/users/[id]/privileges | - | - | src/components/save-changes-bar.tsx; src/components/admin-privileges-form.tsx; tests/integration/admin-save-flows.test.ts | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed

## Open items
Status | ID | Wave name | Feature | What is built | Remaining scope | Blocked on
UNCLEAR | RBAC-003 | Access & security foundation | Manage own shop (Operator Limited) | Nothing built. Only AUDIT_LOG_VIEW_LIMITED exists; no 'Limited' scope for shop management | Define Operator 'Limited' scope, then implement | Decision pending: what 'Limited' means
YET TO START | NEW-007 | Delivered after 28-Sep report (new rows) | Direct per-order payments, tax invoicing, photo POD, accept timeout | Design only - no code, no migrations. Covers ONLINE payment method via Cashfree hosted checkout per order, shop invoices goods while the platform invoices its own fees, photo proof of delivery on the existing handover, and auto-cancel with full refund when a shop does not accept in time | The whole build | Awaiting go-ahead after design review; decisions D1 and D6 already taken
IN PROGRESS | GS-001 | Access & security foundation | Mobile/email/Gmail login | Google + email magic link + mobile-number login with a code sent to the account email (main). On STAGING ONLY (5f64ea2): rebuilt single form taking mobile OR email, first-time /onboarding profile (name, gender, mobile, address with map pin), My Profile with verified email change, checkout requires a mobile, admin can release a wrongly-claimed number | SMS delivery of the OTP so a mobile number is proven; promote the staging login rebuild to main | D2 - SMS/OTP vendor (DLT registration)
IN PROGRESS | SM-005 | State model extension (map, don't replace) | Payment state machine | Unchanged. payment_status is still CREATED / PENDING / SUCCESS / FAILED / REFUNDED | AUTHORIZED/CAPTURED, RECONCILED, CHARGEBACK | Waits on per-order gateway payments (GS-028) - design signed off 1 Oct, build not started
IN PROGRESS | SM-002 | State model extension (map, don't replace) | Shop state machine | shop_status unchanged (PENDING_APPROVAL/APPROVED/REJECTED/SUSPENDED/INACTIVE), but the suspension half now has a real lifecycle: configurable policy per open-order status, impact preview, per-order decisions, owner notice, reinstatement; plus an orders_paused switch | KYC_PENDING, PAYMENT_PENDING, VERIFIED vs ACTIVE, CLOSED | -
IN PROGRESS | SM-003 | State model extension (map, don't replace) | Gig state machine | delivery_partner_status unchanged (REGISTERED/UNDER_REVIEW/APPROVED/REJECTED/SUSPENDED/DEACTIVATED); the delivery leg gained arrival checkpoints (arrived_at_shop_at, arrived_at_customer_at), which is where DELIVERING-style granularity now lives | KYC_PENDING, BLOCKED, DELIVERING on the partner itself | -
IN PROGRESS | SM-004 | State model extension (map, don't replace) | Subscription state machine | Final states locked; subscription_events history; resume/cancel notifications. Enum unchanged: ACTIVE/PAUSED/CANCELLED/COMPLETED/PAYMENT_PENDING | DRAFT, RENEWAL_PENDING, ORDER_CREATED/FULFILLED states | -
IN PROGRESS | SM-006 | State model extension (map, don't replace) | Issue state machine | Tickets linked to orders; returns have a 13-status state machine; NEW: dispute cases carry exactly the missing states (TRIAGED / INVESTIGATING / RESOLUTION_PROPOSED / ESCALATED). Grievance ladder itself still OPEN / IN_PROGRESS / RESOLVED / CLOSED | Either add the four states to grievances, or decide that dispute cases satisfy SM-006 and close it | Decision: does the dispute lifecycle satisfy SM-006?
IN PROGRESS | GS-072 | Location & serviceability | Maps/navigation | Google Geocoding (one call per shop, cached), Places address search, haversine distance, turn-by-turn handed off as a Google Maps deep link for riders and return pickups, and a feasibility-based estimated-minutes figure at checkout | Road routing, a real ETA from a routing API, in-app navigation | -
IN PROGRESS | GS-007 | Shop onboarding completion | Business KYC | GSTIN, PAN and FSSAI numbers are captured and verified/rejected by operations with their own status enums and encrypted storage; an image store now exists (stored_images, /api/images) that documents could use | Document upload/storage wired to a shop; one tracked KYC status instead of separate GST/PAN states | -
IN PROGRESS | WF-008 | Shop onboarding completion | Shop onboarding | Service area complete (radius + extra PIN zones + minimum order + pause switch); categories required at registration; duplicate-registration guard; MRP/price correction queues; registration-fee gate before approval now ENFORCED (GS-008) | KYC document upload wired to a shop (see GS-007) | -
IN PROGRESS | NAV-001 | Discovery & local price comparison | Customer portal - Home | Location picker, 'Shops that deliver to you', featured / Kesari / Green shelves, and a product-search-first hero (the category grid was deliberately removed) | Price-comparison widgets on the home page itself | -
IN PROGRESS | NAV-002 | Discovery & local price comparison | Customer portal - Shop | Shop rating + recent reviews; opening hours with closed-now state; delivery options now shown (fee, free-above threshold, pickup-only, minimum order) | Offers / vouchers on the shop page | Order-level coupons do not exist yet (vouchers are wallet top-up only)
IN PROGRESS | GS-027 | Checkout & payments | Delivery slot | EXPRESS_30 / STANDARD_60 / SCHEDULED windows with a feasibility preview that will not promise a window the system cannot back, plus an estimated-minutes figure | Slot capacity rules; real scheduled slot times | -
IN PROGRESS | GS-028 | Checkout & payments | UPI/card/netbanking gateway | Cashfree is live but only for wallet top-up (create-order, server-side verify, HMAC webhook, mock mode). Orders are still WALLET or COD only. A full design for per-order ONLINE payment was signed off on 1 Oct (generalise payments.purpose, orders.payment_method += ONLINE, migration 0036) - no code written | Build per-order gateway payment | D1 taken (pay-per-order via Cashfree); build not scheduled
IN PROGRESS | GS-073 | Checkout & payments | Payment gateway | Gateway plumbing exists and is reusable; refunds today are wallet credits through refundDeliveredOrder (journaled, idempotent). Gateway refunds and order payments are designed, not built | Gateway refunds; order payments | Depends on GS-028
IN PROGRESS | GS-033 | Checkout & payments | Shop order split | Checkout already produces one order per shop from a multi-shop cart, with per-shop validation and delivery charges | A master order row linking the child orders (single customer-facing reference) | -
IN PROGRESS | NAV-003 | Checkout & payments | Customer portal - Cart & Checkout | Cart now re-validates against the chosen location and shows each issue with an action (change address / add items / remove these items); minimum order and paused shops enforced | Order-level coupons; gateway payment | Vouchers are wallet-top-up only; coupons at checkout not built
IN PROGRESS | WF-001 | Checkout & payments | Customer product purchase | Location, eligible shops, comparison, serviceability block, substitution, minimum order, paused shops, and (1 Oct) ordering from a closed shop behind an explicit customer confirmation with two shop alerts | Direct gateway payment for orders (GS-028) | Depends on GS-028
IN PROGRESS | GA-005 | Delivery & gig assignment | Current load | Unchanged: a rider already on a delivery is EXCLUDED from the candidate pool (row-locked to stop races). Ranking weights are distance + reliability + fairness only - no load term | Lower priority instead of exclusion; multi-order batching | -
IN PROGRESS | NAV-013 | Delivery & gig assignment | Gig portal - Profile | The profile page is read-only: vehicle type and registration are displayed, identity and bank details are stored encrypted and deliberately not shown. The only PATCH on a partner is operations' verification actions | Rider self-edit of KYC / vehicle / bank details | -
IN PROGRESS | GS-074 | Notifications | SMS/WhatsApp/email/push | Email and in-app are real and live (email needs SMTP in production; without it email is skipped, not failed). SMS, PUSH and WHATSAPP are enum values with a provider seam and one plug-in point | Real SMS / push / WhatsApp providers | D2 - vendor choice (India needs DLT registration)
IN PROGRESS | GS-014 | P1 MVP features | Product images/specifications | Image store (stored_images, /api/images) with validation, browser-side shrink and a safe fallback; several images per product or per listing, primary image, reorder, replace, delete, alt text. products.specifications exists | Image moderation (the product-approval queue does not review images) | -
IN PROGRESS | GS-023 | Phase 2 features | E-commerce price benchmark | External reference prices with source, time, location, URL and verification plus an audit history, kept strictly separate from MRP and selling price and never written into either. Visibility is a rule: shops and operations see them, customers do not | Turn on the customer display (code is in place, the rule is off) | D7 - licensed/lawful source for customer-visible reference prices. Flip externalPrices.showToCustomers; no code change
IN PROGRESS | GS-054 | Phase 2 features | Referral program | What exists is SHOP referral attribution: referral codes, usable-code resolution, attributing a registering shop to a code, performance report. There is no customer referral | Customer referral rewards and the fraud checks that go with them | -

## Changed since 2-Oct
ID | Feature | Change | Delivered in | What changed | Where it is
GS-001 | Mobile/email/Gmail login | Progressed | staging 3 Oct (5f64ea2) | Google + email magic link + mobile-number login with a code sent to the account email (main). On STAGING ONLY (5f64ea2): rebuilt single form taking mobile OR email, first-time /onboarding profile (name, gender, mobile, address with map pin), My Profile with verified email change, checkout requires a mobile, admin can release a wrongly-claimed number | Main: partial. Login rebuild on staging only - not merged to main
SM-006 | Issue state machine | Progressed | 3 Oct (af2b451) | Tickets linked to orders; returns have a 13-status state machine; NEW: dispute cases carry exactly the missing states (TRIAGED / INVESTIGATING / RESOLUTION_PROPOSED / ESCALATED). Grievance ladder itself still OPEN / IN_PROGRESS / RESOLVED / CLOSED | Partial code on main @16dff81
GS-008 | Payment reference verification | IN PROGRESS -> COMPLETED | 2 Oct (bbc6140) | approveShop() now refuses unless fee_payment_status = PAID (derived from the shop_payments ledger), naming the amount outstanding; waived fee (zero snapshot) is written PAID at registration; approval queue shows each pending shop's fee state. Gate is on the transition only - shops already APPROVED untouched | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
WF-008 | Shop onboarding | Progressed | 2 Oct (bbc6140) | Service area complete (radius + extra PIN zones + minimum order + pause switch); categories required at registration; duplicate-registration guard; MRP/price correction queues; registration-fee gate before approval now ENFORCED (GS-008) | Partial code on main @16dff81
GS-042 | Live tracking | IN PROGRESS -> COMPLETED | 2 Oct (bbc6140) | Tracking API with role/privacy checks + polling LiveTrackingMap, now MOUNTED: on /orders inside an in-flight order card that has a rider, and on /admin/orders behind a per-row Track toggle. isTrackableOrderStatus() limits polling to orders actually in flight. Rider privacy: area only until pickup, no ETA from a stale fix | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
GS-058 | Dispute management | IN PROGRESS -> COMPLETED | 3 Oct (af2b451) | Dispute case entity (migration 0037): order, raiser, disputed amount, payment-method snapshot; 8 statuses (OPEN, TRIAGED, INVESTIGATING, RESOLUTION_PROPOSED, ESCALATED, RESOLVED, REJECTED, WITHDRAWN) with a transition table; auto-escalation by amount (default Rs 2,000) and age (default 48 h, hourly cron); escalated cases admin-only; refund resolution goes through refundDeliveredOrder with a double-pay guard; customer sees outcome, not working notes; /admin/disputes queue | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
NAV-004 | Customer portal - Orders | IN PROGRESS -> COMPLETED | 2-3 Oct (bbc6140, af2b451) | Rate an order, report a problem, request a return (/orders/{id}/return, /returns), live tracking panel on in-flight orders, and raise / follow a dispute case | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
NAV-019 | Admin portal - Security | IN PROGRESS -> COMPLETED | 3 Oct (ef25ca0) | Fraud side: /admin/risk over 11 risk rules. NEW consent side: /admin/consents behind CONSENT_VIEW (operator + admin) - per-type consent standing vs live policy version, recent grant/withdrawal trail, per-person audited lookup; stored IP never returned | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed
NEW-008 | Product category master & shop product-category visibility | New row | staging 3 Oct (74fda32, 7d13b7b, bf5a81a) | product_categories as a master (unique names, permanent General category guarded by trigger); shop_product_categories decides which products a shop sees; removing a category moves products to General; removing it from a shop pauses its listings; screens /product-categories, /product-categories/products, /shop/product-categories, /admin/shops/[id]/product-categories; one-time categorisation script with dry run / apply / restore | Staging only - not merged to main
NEW-009 | Explicit Save flow on admin screens (categories, privileges, user profiles) | New row | 2 Oct (dbbcc88) | Draft + Save Changes bar with dirty tracking, confirm step, unsaved-changes guard; privileges saved in one transaction (no half-applied role changes, last-admin protection, self-change blocked); profile edits limited to name/phone/status; every save audited. Editing moved to /admin/users/[id] and /admin/users/[id]/privileges | Merged to main @16dff81 - needs migrations up to 0037 + QA; not QA-signed

## Decisions & risks
Type | Item | What is needed | Blocks
Decision | Per-order payment (GS-028 / NEW-007) | Approve the build of per-order online payment, OR consciously launch with wallet + COD only. | GS-028, GS-073, SM-005, gateway refunds, GO-LIVE
Decision | D2 - SMS / OTP vendor | Pick a DLT-registered SMS provider. | GS-001 (proven mobile), GS-074 (SMS/WhatsApp/push)
Decision | D7 - external price source | Approve a lawful/licensed source for customer-visible reference prices. | GS-023 (one rule flip)
Decision | D10 - cancellation policy | Confirm ACCEPTED/ASSIGNED (customer blocked) and PICKED_UP (goods-only refund) treatments. | NEW-006 sign-off
Decision | RBAC-003 - Operator 'Limited' | Define what an operator may change on a shop. | RBAC-003
Decision | SM-006 scope | Does the new dispute lifecycle satisfy the issue state machine, or must grievances get the same states? | SM-006
Risk - HIGH | Migration number collision | main has drizzle/0037_dispute_cases.sql; staging has 0037_login_profile.sql + 0038_product_category_management.sql. A trial merge of staging into main conflicts in drizzle/meta/_journal.json and 0037_snapshot.json. Staging's migrations must be renumbered (0038, 0039) and snapshots regenerated before merge, or a database that ran one 0037 will skip the other. | Promoting login rebuild (GS-001) and category master (NEW-008) to main
Risk - HIGH | No QA sign-off | Nothing since Phase 1 has been signed off in a browser; status here is code + automated tests only. | GO-LIVE
Risk - MEDIUM | Production migrations | Production must apply migrations through 0037 (main) before Phase A-J, consent view and dispute features work. Dispute escalation needs its own cron (see DEPLOY_RUNBOOK.md). | Deployment
Risk - LOW | Unmerged branches | claude/awesome-dijkstra-fmccpl (20 commits: Product Master on MySQL), claude/tender-cannon-vmecpj (7), claude/amazing-cannon-5n3fro (1 docs commit) are not in main or staging. | Housekeeping