## Feature status
Shop registration — single flow, document window, pin after payment (owner brief 30 Oct 2026)
As of 31 Oct 2026, 00:30 IST. PR #298 merged into staging (685e1f2f) and live on test.gokesari.com since 30 Oct 18:37 UTC; follow-up fixes in a second PR. Not on gokesari.com. Design: docs/shop-onboarding-wizard-2026-10/FLOW_2026-10-30-b.md.
# | Fix | Status | Where it runs | Notes | Files
1 | Single registration process | Done | test.gokesari.com (#298) | One card on /sell and Seller Central → /shop/register. /shop/join forwards with ?code=/?ref=. /shop/join/{token} status pages unchanged. | register-options.tsx; app/shop/join/page.tsx; app/shop/register/page.tsx; app/sell/page.tsx; app/shop/page.tsx
2 | Screen 2: one checklist, Enter / Request Referral Code, documents list | Done | test.gokesari.com (#298) | Tile board is the only checklist. | onboarding-wizard.tsx (ReferralStep, RequiredDocuments)
3 | Yes / No control | Done | test.gokesari.com (#298) | "Do you have your documents now?" Yes / No. | onboarding-wizard.tsx (DocumentsReadyStep)
4 | Document window: GSTN, PAN, Shop Act, FSSAI (optional) [+ Udyam optional] | Done | test.gokesari.com (#298) | Udyam kept as a 5th optional line (owner: keep both). | onboarding-wizard.tsx (IdentityStep)
5 | Validate button per number | Done | test.gokesari.com (#298) | Each line calls the existing government-check route; Verified / Our team will check / Not verified / inline format error. | onboarding-wizard.tsx
6 | Auto-fill shop and owner name from GST / PAN | Done | test.gokesari.com (#298) | Existing server code. A company's GST record has no single owner: shown as 'Not in the record'. | shop-registration-wizard.ts (unchanged), PrefillSummary
7 | Page 3: confirm retrieved details | Done | test.gokesari.com (#298) | Step 5 shows shop name and owner name, editable. | onboarding-wizard.tsx (DetailsStep)
8 | Page 4: payment | Done | test.gokesari.com (#298) | Checkout unchanged. Local: sandbox payment passed. Staging: goes to HDFC Bank UAT gateway — not completed. | -
9 | Page 5: address and location after payment | In Progress | test.gokesari.com (#298) | Owner chose 'pin after pay': address given before payment (shop needs one), corrected with the map pin after payment. Verified locally; not reached on staging because staging's fee payment now goes to HDFC UAT. | shop-registration-wizard.ts (step order); onboarding-wizard.tsx (ShopLocationStep)
10 | Google Maps fix | Done | test.gokesari.com and gokesari.com | Cause: staging was built with a different browser key that Google refused (RefererNotAllowedMapError). Owner set the production key on staging in hPanel; the #298 build carries it and the map loads (verified 30 Oct). Code fallback for a refused key added. | lib/geo/provider.ts; map-picker.tsx; nearby-map.tsx
11 | Android and iOS apps | Done | WebView — no build needed | Both apps show the website; changes arrive with the web deploy. No platform differences in this flow. | mobile/README.md
12 | Testing on Test (test.gokesari.com) | In Progress | After merge of PR #298 | Steps 1–6 pass on staging. Payment and address/location step blocked: staging uses PAYMENT_GATEWAY=HDFC (UAT), not SANDBOX. | -
13 | Testing on Prod (gokesari.com) | Blocked | Owner-approved release window | Owner chose 'staging now, Prod later'. Read-only smoke checks after release; no payment on production. | -

## Test results
Test results
Local = Postgres 18 on the developer Mac, mock KYC, sandbox payment. Split = core + seller databases (postgres_fdw). Staging / production rows are filled after release.
ID | Case | Layer / site | Status | Evidence
UT-1 | shop-registration-flow + onboarding-wizard-step1/2 (59 cases) | Local, single DB | Pass | 59 / 59
UT-2 | Same 59 cases | Local, split layout | Pass | 59 / 59
UT-3 | 25 registration / referral / approval / location files | Local, split layout | Pass | 333 / 333 (dealer-step4 re-run alone after the local server ran out of lock memory)
UT-4 | Whole suite | Local, single DB | Pass | 3016 / 3020; the 4 failures are known and unrelated (3 product-import / pmd; migrate-on-build clean-up hook timeout, 7 / 7 tests pass alone)
UI-1 | One registration card on /sell; button → /shop/register | Local browser | Pass | No register-option-join card
UI-2 | /shop/join?code=ab12cd34 → /shop/register?ref=AB12CD34 | Local | Pass | redirect checked
UI-3 | Screen 2: tiles, Enter / Request Referral Code, 6 documents | Local browser | Pass | -
UI-4 | Yes / No step | Local browser | Pass | -
GOV-GST | GSTIN validate (mock provider) | Local | Pass | Verified; PAN filled from GST record; shop name filled
GOV-PAN | PAN from GST record | Local | Pass | PAN line shows Verified (from GST)
GOV-SHOPACT | Shop Act validate | Local | Pass | 'Our team will check' (online check not available in that state) — expected outcome
GOV-FSSAI | FSSAI: bad number then valid number | Local | Pass | Inline '14 digits' error; then Verified, valid until 2028-10-29
UI-5 | Food shop sent back to FSSAI (Required, Continue locked) | Local browser | Pass | -
UI-6 | Confirm page shows retrieved names; review → pay (sandbox) | Local browser | Pass | Pay ₹1,178.82 on the sandbox page
UI-7 | Page 5 after payment: address pre-filled, coordinates saved with address | Local browser + DB | Pass | shops row: area, lat 18.5308, lng 73.8475
MAP-1 | Maps on gokesari.com | Production (read-only) | Pass | Script + Places load, no auth error
REG-1 | Regression: whole suite | Local | Pass | see UT-4
PRD-1 | Smoke on gokesari.com | Production | Not run | after an owner-approved release
MAP-2 | Maps on test.gokesari.com before the fix | Staging | Fail | RefererNotAllowedMapError with the old staging key
MAP-3 | Maps on test.gokesari.com after the owner's key change | Staging | Pass | Production key (…UffY) built in; map and Places load
ST-1 | /sell one card → /shop/register | Staging | Pass | -
ST-2 | /shop/join?code → /shop/register?ref | Staging | Pass | -
ST-3 | Seller Central with no shop: one card | Staging | Pass | -
ST-4 | Screen 2: tiles, Enter / Request Referral Code, 6 documents | Staging | Pass | Code required on staging; test code T47BC8PU
ST-5 | Referral → email → Yes / No | Staging | Pass | -
ST-6 | Document window, 5 lines with Validate | Staging | Pass | Staging provider: all 'Our team will check' for test numbers
ST-7 | Confirm details → review (no map before payment) → shop created | Staging | Pass | QA Staging Stores 298
ST-8 | Payment | Staging | Not run | Goes to HDFC UAT gateway; card details not entered by Claude
ST-9 | Address and location after payment | Staging | Not run | Needs ST-8
GOV-STG | GSTIN / Shop Act / FSSAI / Udyam on the staging provider | Staging | Pass | Clear 'Our team will check' states; a real GSTIN is needed to see Verified

## Open items
Open items and decisions
Who acts on each.
# | Item | Who | Status | Notes
4 | Production release window | Owner | Open | One release at a time (DEPLOYMENT.md §3)
5 | A paid shop waiting for admin approval gets the map step only after approval | Decision | Open | Could be asked right after payment instead
6 | Lawyer / CA sign-off for selling before documents are verified (D-F05) | Owner | Open | Carried from 30 Oct flow
7 | Staging fee payment goes to HDFC UAT — switch back to SANDBOX or pay with HDFC's test card | Owner | Open | Blocks ST-8 / ST-9
8 | Dealer-role account sees the wizard but step 1 says 'no permission' | Decision | Open | Existing; could tell dealers to switch to their customer account
9 | Staging test data: shop 'QA Staging Stores 298' (unpaid) and referral code T47BC8PU | Owner / QA | Open | Delete or keep for the next run