## Summary
GoKesari - features and products status (19 Oct 2026)
Source: docs/gokesari-audit/GOKESARI_FEATURE_STATUS_REPORT_2026-10-19.xlsx (267 features). Production = main @418392d (gokesari.com, migrations to 0084; build & integrate batch live since release #194 on 18 Oct, new features OFF until switched on). Test site = staging, same code. Status = development status from code, PRs, docs and recorded test runs - not QA sign-off. Replaces the 3 Oct version of this file.
Item | Count | Note
Total features tracked | 267 | Feature Register, 18 Oct report
Completed | 247 | 93% - built, merged and live on gokesari.com (incl. built but switched off by default)
In progress | 1 | Mobile apps - Android builds done, store publishing on hold
Blocked | 7 | Waiting on an owner decision, vendor, account or CA / legal check
Yet to start | 11 | Known gaps with no code yet (incl. signature capture, deferred to Phase 2)
Dropped | 1 | Online reference prices (GS-023) - dropped by owner decision
Completed but switched off in production | 34 | Built and released; waiting for owner keys / a switch (see Go-live blockers)
Products / modules tracked | 14 | See the "Products" sheet (incl. Inventory & Accounting and Bulk product upload)
Decisions / vendor choices pending | 15 | See "Decisions pending"
Go-live blockers and owner inputs open | 20 | See "Go-live blockers" (keys, accounts, security actions, inputs)
Change since 18 Oct | +20 completed | 18 Oct: 227 of 267 (85 %); 19 Oct: 247 of 267 (92.5 %) - batch #190 released by #194; 23 features changed status
Change since 3 Oct | +115 completed | 3 Oct: 132 of 157 complete (84 %) - 110 features added to the register since 3 Oct

## Products
Product / module | What it covers | Status | Features | Completed | of which switched off in prod | In progress | Yet to start | Blocked | Dropped | % complete | Open feature IDs
Customer shopping (web + app) | Find shops that deliver to you, compare, cart, checkout, orders, returns, support | LIVE - work open | 57 | 48 | 7 | 0 | 7 | 1 | 1 | 84% | GS-023, GAP-008, GAP-011, GAP-012, GAP-013, GAP-014, GAP-015, GAP-018, GAP-019
Seller Central (shop owner portal) | Shop registration, KYC, listings, prices, media, orders, shop switcher | LIVE | 39 | 39 | 4 | 0 | 0 | 0 | 0 | 100% | -
Inventory & Accounting (NEW-067) | Stock ledger, purchases, GST, supplier bills, reports for shop owners (sub-features) | LIVE - work open | 56 | 49 | - | 1 | 0 | 6 | 0 | 88% | IA-022, IA-031, IA-032, IA-034, IA-039, IA-049, IA-056
Bulk product upload (GS-013) | Excel / CSV product import with stock update, web + app (sub-features) | LIVE - work open | 17 | 15 | - | 1 | 0 | 1 | 0 | 88% | BPU-10, BPU-11
Product Master Data Platform | Master product catalogue, feeds, loader, quality scores | LIVE | 7 | 7 | 1 | 0 | 0 | 0 | 0 | 100% | -
Delivery & riders (gig) | Rider onboarding, assignment, pickup / delivery codes, proof of delivery | LIVE - work open | 30 | 29 | 5 | 0 | 1 | 0 | 0 | 97% | GAP-003
Payments, wallet & finance | Customer / shop wallets, Cashfree top-up, COD, refunds, invoices, settlements | LIVE - work open | 19 | 18 | 10 | 0 | 0 | 1 | 0 | 95% | NEW-027
Subscriptions | Recurring orders (milk, daily needs) | LIVE | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 100% | -
Societies (housing) | Society membership, society admin, society orders | LIVE | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 100% | -
Admin & operator console | Approvals, settings, analytics / KPIs, operator tools | LIVE | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 100% | -
Identity, access & security | Sign-in (Google, email, mobile), roles, RBAC, data protection | LIVE | 26 | 26 | 1 | 0 | 0 | 0 | 0 | 100% | -
Notifications, integrations & marketing | Email / in-app / push / SMS, event layer, third-party integrations, referrals | LIVE - work open | 13 | 12 | 5 | 0 | 1 | 0 | 0 | 92% | GAP-009
Mobile apps (Android / iPhone) | Native shell around gokesari.com | IN PROGRESS | 4 | 2 | 0 | 1 | 0 | 1 | 0 | 50% | NEW-043, PLT-017
Platform, performance & QA | Hosting, database, CI / deploy, performance, test runs, branding | LIVE - work open | 31 | 25 | 1 | 0 | 2 | 4 | 0 | 81% | PLT-015, QA-003, QA-009, GAP-010, GAP-016, GAP-017

## Switched off in prod
# | ID | Feature | Product / module | Switch / what it needs | Remaining / owner input | Blocked on / next step
1 | GS-014 | Product images/specifications | Seller Central (shop owner portal) | Off by default - switch on in Admin > Business rules (rule: imageModeration.enabled) | - | -
2 | GS-027 | Delivery slot | Customer shopping (web + app) | Off by default - switch on in Admin > Business rules (rules: scheduledSlots.enabled, deliverySlots.enabled) | - | -
3 | GS-028 | UPI/card/netbanking gateway | Payments, wallet & finance | Off until live gateway keys (onlinePayments); sandbox on test | Live Cashfree / Razorpay / PhonePe keys and webhook secrets | Owner inputs §1-2
4 | GS-033 | Shop order split | Customer shopping (web + app) | Off by default - switch on in Admin > Business rules (rule: parentOrders.enabled) | - | -
5 | GS-054 | Referral program | Notifications, integrations & marketing | Off by default - switch on in Admin > Business rules (rule: customerReferrals.enabled; rewards Rs 50 / Rs 50) | - | -
6 | GS-072 | Maps/navigation | Notifications, integrations & marketing | Off by default - switch on in Admin > Business rules (rule: routing.enabled) | In-app turn-by-turn navigation not built (Google Maps deep link used instead). | -
7 | GS-073 | Payment gateway | Notifications, integrations & marketing | Off until live gateway keys | Live keys and webhook secrets | Owner inputs §1-2
8 | GS-074 | SMS/WhatsApp/email/push | Notifications, integrations & marketing | Email + in-app live; Expo push on mock until EAS / FCM / APNs keys; SMS / WhatsApp stubs | Real push keys; SMS / WhatsApp vendor if wanted | Owner inputs §11 (push)
9 | WF-001 | Customer product purchase | Customer shopping (web + app) | Online payment at checkout built (sandbox); live keys needed | Live gateway keys | Owner inputs §1-2
10 | RBAC-003 | Manage own shop | Identity, access & security | OPERATOR_LIMITED role live on test; production by role grant | - | -
11 | SM-005 | Payment state machine | Payments, wallet & finance | Off until live gateway keys | RECONCILED / CHARGEBACK states not added | Owner inputs §1-2
12 | GA-005 | Current load | Delivery & riders (gig) | Off by default - switch on in Admin > Business rules (rule: batching.enabled; F3 busy-rider fallback: dispatch.busyRidersAsFallback) | - | -
13 | NAV-001 | Customer portal - Home | Customer shopping (web + app) | Off by default - switch on in Admin > Business rules (rule: homePriceComparison.enabled) | The category grid was deliberately removed in favour of search-first; categories are reachable from shops and search. | -
14 | NAV-002 | Customer portal - Shop | Customer shopping (web + app) | Off by default - switch on in Admin > Business rules (rule: shopOffers.enabled) | - | -
15 | NAV-003 | Customer portal - Cart & Checkout | Customer shopping (web + app) | Online payment at checkout built (sandbox); coupons rule unchanged | Live gateway keys | Owner inputs §1-2
16 | NEW-007 | Direct per-order payments, tax invoicing, photo POD, accept timeout | Payments, wallet & finance | All four parts built; per-order online payment off until live keys | Live gateway keys; CA to confirm invoice rates / HSN (NEW-027) | Owner inputs §1-2
17 | NEW-020 | Cancellation before packing - full refund; optional customer cancel until packing (item A) | Customer shopping (web + app) | Off by default - rule cancellation.customerMayCancelUntil = CONFIRMED (the original behaviour); PREPARING turns it on | - | Choose whether to switch PREPARING on
18 | NEW-033 | Shop prepaid wallet | Payments, wallet & finance | Off by default - rule shopWallet.enabled = false (on for the test site only) | Production release | Legal review of holding shops' prepaid money (Blockers #17) before switching it on
19 | NEW-034 | Shop wallet: Rs 5/km delivery charge, no checkout below minimum, commission back on refunds | Payments, wallet & finance | Off by default - rule shopWallet.enabled = false (on for the test site only) | Production release | Legal review of holding shops' prepaid money (Blockers #17) before switching it on
20 | NEW-038 | Shop self-registration with auto-approval (Module 3) | Seller Central (shop owner portal) | Off by default - rule selfRegistration.enabled = false; refused on gokesari.com until a real SMS/WhatsApp provider is set | Merge #92; real SMS / WhatsApp provider for production (refused on gokesari.com until set); fee amounts; FSSAI rule for self-registered food shops | Owner inputs P2, P4, P5 (Blockers #18) before switching it on
21 | NEW-039 | Delivery options and scheduling: pickup, shop's own delivery, GoKesari partner | Delivery & riders (gig) | Off by default - rule fulfilmentOptions.enabled = false (on for the test site only) | Production release (migrations 0056-0064); owner decision F1-8 - refund the customer's delivery fee automatically when the shop chooses pickup? | Switch on in Admin > Business rules when ready
22 | NEW-040 | Mandatory legal documents by shop type (FSSAI, drug licence, medical registration) | Seller Central (shop owner portal) | Off by default - rule legalDocuments.enabled = false (on for the test site only) | Production release; tell shop owners about the 15-day grace first; decision - also hide shops past their grace period from customers? | Tell shop owners about the 15-day grace, then switch on (Blockers #28)
23 | NEW-041 | Bank account details with Rs 1 verification (shops for payouts, customers for refunds) | Payments, wallet & finance | Off by default - rule bankAccounts.enabled = false (on for the test site only) | Production release; Cashfree live keys with the Refunds API; payout gate not run on test (covered by integration tests); decisions - buy Cashfree Verification Suite for the bank's name? offer refunds to bank at all? | Cashfree live keys with the Refunds API (Blockers #24), then switch on
24 | NEW-042 | Mandatory referral code at shop registration + 'Request a referral code' | Seller Central (shop owner portal) | Admin > Referral settings: referral_required_shop = OPTIONAL on production (checked 14 Oct) | Production release; create referral codes before switching it on (or registrations stop); confirm who owns referrals@gokesari.com and that mail arrives there | Create referral codes and the referrals@ mailbox (Blockers #26), then switch on
25 | NEW-048 | Mandatory customer referral code at sign-up, with 'ask us for a code' | Notifications, integrations & marketing | Admin > Referral settings: referral_required_customer = OPTIONAL on production (checked 14 Oct) | - | Set requiredFrom and switch on when codes can be issued
26 | NEW-049 | Refunds to the customer's verified bank account | Payments, wallet & finance | Off by default - rule bankRefunds.enabled = false | - | Switch on with bank accounts (NEW-041)
27 | NEW-050 | Bank account checked with the bank (Cashfree Verification Suite) instead of the Rs 1 payment | Payments, wallet & finance | Off by default - rule bankAccountCheck.enabled = false | Test site showed 'Keys not found' before #117 | Verification Suite keys on production, then switch on
28 | PMD-002 | GS1 India and manufacturer-catalogue feeds | Product Master Data Platform | Manufacturer portal on; GS1 DataKart (mock) and Open Food Facts off (Admin > Settings) | GS1 India Solution Provider agreement and keys for live GS1 data | Owner inputs §8
29 | PLT-013 | Opt-in prepared statements (DATABASE_PREPARED_STATEMENTS=on) | Platform, performance & QA | Off - environment variable not set on either site | Turn on for test.gokesari.com, check Neon's pooled host accepts prepared statements, then gokesari.com | Owner: environment setting (Blockers #36)
30 | GAP-001 | Pickup QR code | Delivery & riders (gig) | Off - rule pickupQr.enabled; set PICKUP_QR_SECRET first | - | Owner: switch on
31 | GAP-002 | In-app turn-by-turn navigation | Delivery & riders (gig) | Off - rule riderNavigation.enabled; Google Routes / OSRM provider (mock on test) | Routes API on the Maps server key, or an OSRM server | Owner: provider + switch on
32 | GAP-004 | Broadcast job offers / radius widening | Delivery & riders (gig) | Off - rule dispatchBroadcast.enabled (radius 2 > 4 > 6 km) | - | Owner: switch on (needs the timeout-sweep cron)
33 | GAP-005 | Automated bank transfer for settlements and rider payouts | Payments, wallet & finance | Off - PayoutProvider on sandbox | RazorpayX / Cashfree payout keys | Owner inputs §3
34 | GAP-006 | Platform tax invoice for GoKesari's own fees (D6) | Payments, wallet & finance | Off until GoKesari GSTIN, legal details and invoice prefix | CA to confirm TCS / TDS / SAC rates | Owner inputs §4-6

## Open features
# | ID | Feature | Product / module | Priority | Status | Where it runs | Remaining scope | Blocked on / next step
1 | GAP-008 | Map 'Confirm location' answers 500 on test.gokesari.com | Customer shopping (web + app) | - | BLOCKED | Test site only (test.gokesari.com) | Cause found (N-1): the test server key GOOGLE_MAPS_SERVER_API_KEY is restricted by HTTP referrer, so Google refuses server calls. Switch it to an IP restriction; check production's key too | Owner: change the Maps server key restriction
2 | PLT-017 | 'iPhone app' workflow - EAS build and TestFlight upload | Mobile apps (Android / iPhone) | - | BLOCKED | GitHub Actions (runs from main) | Link the project to Expo and commit the project id; secrets EXPO_TOKEN, ASC_API_KEY_P8, ASC_KEY_ID, ASC_ISSUER_ID, APPLE_TEAM_ID; App Store Connect app record for com.gokesari.app | On hold (owner decision on store publishing); then EXPO_TOKEN + Expo project id
3 | NEW-027 | GST rates / HSN codes report for the CA; cron map (item D) | Payments, wallet & finance | - | BLOCKED | Production (gokesari.com) | CA to verify HSN codes, GST rates, bill-of-supply wording and invoice numbering before invoicing is used for filing | CA verification
4 | GAP-010 | Slow signed-in pages and cold first visits (database far from the web server) | Platform, performance & QA | - | BLOCKED | Not started | Database and web server in the same region and a longer idle timeout; then prepared statements (PLT-013) | Owner: hosting decision (Blockers #35)
5 | PLT-015 | Seller / customer database split (tooling and 'Database split' workflow) | Platform, performance & QA | - | BLOCKED | GitHub Actions (runs from main) | Cut-over (DB_SPLIT_MODE) not performed | Owner: go-ahead and window for the cut-over + Neon logical replication (Owner inputs §13)
6 | QA-003 | Execute the 791 test cases and sign off in a browser on test.gokesari.com | Platform, performance & QA | - | BLOCKED | Not started | Manual 791-case browser plan still not run; production order-lifecycle subset not run | Owner inputs §14 (production shop, rider, payment choice)
7 | QA-009 | Order-lifecycle run on production (gokesari.com) with a real payment | Platform, performance & QA | - | BLOCKED | Not started | Needs the owner's production shop and owner email, an approved rider, Cashfree live keys confirmed, and the owner to pay the top-up | Owner inputs §14
8 | NEW-043 | Android and iPhone app (mobile/) - native shell around gokesari.com | Mobile apps (Android / iPhone) | - | IN PROGRESS | Mobile app - Android test builds only (not in stores) | Store publishing on hold (owner decision) | Owner: decide when to publish (Play / App Store)
9 | GAP-011 | Search shows '0 shops' for products that nearby shops sell | Customer shopping (web + app) | - | YET TO START | Not started | Fix shop matching in search (back-end) | -
10 | GAP-012 | Admin dispute resolution gives no visible confirmation | Customer shopping (web + app) | - | YET TO START | Not started | Busy state and success message on the resolve form | -
11 | GAP-013 | Approved return waiting for a rider cannot be completed by staff | Customer shopping (web + app) | - | YET TO START | Not started | Decide whether staff may complete a pickup without a rider | Owner: business rule
12 | GAP-014 | /orders?tab=returns shows the Active list | Customer shopping (web + app) | - | YET TO START | Not started | Map tab=returns to /returns | -
13 | GAP-015 | Hindi / Marathi for the body of inner pages | Customer shopping (web + app) | - | YET TO START | Not started | Translate the remaining strings with a native-speaker review | Owner: decision (Blockers #38)
14 | GAP-018 | My Orders card wording after an order is switched to pickup | Customer shopping (web + app) | - | YET TO START | Not started | Hide the rider line once the order is not a GoKesari delivery; label the delivery-fee refund correctly | -
15 | GAP-019 | Wallet checkout takes 30-38 s on the test site | Customer shopping (web + app) | - | YET TO START | Not started | Profile checkout on test; likely the far database (GAP-010) | -
16 | GAP-003 | Signature capture at delivery | Delivery & riders (gig) | - | YET TO START | Not started | Deferred to Phase 2 (owner decision) | Phase 2
17 | GAP-009 | Email sending capacity (mail host hourly limit) | Notifications, integrations & marketing | - | YET TO START | Not started | Raise the limit with the host or send through a transactional email service; check SPF/DKIM | Owner: email provider choice
18 | GAP-016 | Same Drizzle bare-id subquery bug in rider reliability and the integrations 'listed' flag | Platform, performance & QA | - | YET TO START | Not started | Apply the #138 fix pattern and add regression tests | -
19 | GAP-017 | React error #418 (hydration) on /wallet and /admin/orders | Platform, performance & QA | - | YET TO START | Not started | Find the server / client difference and fix | -
20 | GS-023 | E-commerce price benchmark | Customer shopping (web + app) | P1 | DROPPED | Dropped (code constant) | - | -

## All features
# | ID | Feature | Product / module | Module / area | Priority | Status | Where it runs | Switched on? | Released in PR(s)
1 | GS-001 | Mobile/email/Gmail login | Identity, access & security | Identity & Access | P0 | COMPLETED | Production (gokesari.com) | Live (email OTP); SMS OTP only via the Phase-2 SMS stub | #14; #23; #43; #81; #123; #194
2 | GS-002 | Role-based access control | Identity, access & security | Identity & Access | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #19
3 | GS-003 | Multi-role user account | Identity, access & security | Identity & Access | P1 | COMPLETED | Production (gokesari.com) | Live | #19
4 | GS-004 | PIN / address selection | Customer shopping (web + app) | Location | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #23; #84
5 | GS-005 | Society identification | Customer shopping (web + app) | Location | P0 | COMPLETED | Production (gokesari.com) | Live | #19
6 | GS-006 | Shop registration | Seller Central (shop owner portal) | Shop Onboarding | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #47; #54
7 | GS-007 | Business KYC | Seller Central (shop owner portal) | Shop Onboarding | P0 | COMPLETED | Production (gokesari.com) | Live; vendor checks run on the MOCK vendor until Gridlines keys are set (KYC_PROVIDER) | Baseline; #54
8 | GS-008 | Payment reference verification | Seller Central (shop owner portal) | Shop Onboarding | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #29
9 | GS-009 | Shop categories | Seller Central (shop owner portal) | Shop Onboarding | P0 | COMPLETED | Production (gokesari.com) | Live | #23; #32
10 | GS-010 | Service radius / delivery zone | Seller Central (shop owner portal) | Shop Onboarding | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #23
11 | GS-011 | Product master | Seller Central (shop owner portal) | Catalog | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #8; #43
12 | GS-012 | Shop catalog mapping | Seller Central (shop owner portal) | Catalog | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #43; #47
13 | GS-013 | Bulk product upload | Seller Central (shop owner portal) | Catalog | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #43
14 | GS-014 | Product images/specifications | Seller Central (shop owner portal) | Catalog | P1 | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rule: imageModeration.enabled) | #23; #57; #82
15 | GS-015 | MRP / selling price / discount | Seller Central (shop owner portal) | Catalog | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #23; #47
16 | GS-016 | Stock quantity | Seller Central (shop owner portal) | Inventory | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline
17 | GS-017 | Low-stock threshold | Seller Central (shop owner portal) | Inventory | P1 | COMPLETED | Production (gokesari.com) | Live | Baseline; #23
18 | GS-018 | Reorder level / quantity | Seller Central (shop owner portal) | Inventory | P1 | COMPLETED | Production (gokesari.com) | Live | Baseline; #23
19 | GS-019 | Shop search | Customer shopping (web + app) | Search | P0 | COMPLETED | Production (gokesari.com) | Live | #14; #84
20 | GS-020 | Product search | Customer shopping (web + app) | Search | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #71; #84
21 | GS-021 | All shops selling product | Customer shopping (web + app) | Search | P0 | COMPLETED | Production (gokesari.com) | Live | #14
22 | GS-022 | Local price comparison | Customer shopping (web + app) | Comparison | P0 | COMPLETED | Production (gokesari.com) | Live | #14; #57; #73
23 | GS-023 | E-commerce price benchmark | Customer shopping (web + app) | Comparison | P1 | DROPPED | Dropped (code constant) | Off permanently (code constant, not a setting) | #23; #194
24 | GS-024 | Single-shop cart | Customer shopping (web + app) | Cart | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #71; #73
25 | GS-025 | Multi-shop cart | Customer shopping (web + app) | Cart | P1 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14
26 | GS-026 | Address validation | Customer shopping (web + app) | Checkout | P0 | COMPLETED | Production (gokesari.com) | Live | #19; #23; #43
27 | GS-027 | Delivery slot | Customer shopping (web + app) | Checkout | P0 | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rules: scheduledSlots.enabled, deliverySlots.enabled) | Baseline; #57; #65
28 | GS-028 | UPI/card/netbanking gateway | Payments, wallet & finance | Payments | P0 | COMPLETED | Production - built, switched off by default | Off until live gateway keys (onlinePayments); sandbox on test | Baseline; #194
29 | GS-029 | Wallet | Payments, wallet & finance | Payments | P1 | COMPLETED | Production (gokesari.com) | Live | Baseline
30 | GS-030 | COD | Payments, wallet & finance | Payments | P1 | COMPLETED | Production (gokesari.com) | Live | #19
31 | GS-031 | Payment reconciliation | Payments, wallet & finance | Payments | P0 | COMPLETED | Production (gokesari.com) | Live | #14
32 | GS-032 | Order creation | Customer shopping (web + app) | Orders | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14
33 | GS-033 | Shop order split | Customer shopping (web + app) | Orders | P0 | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rule: parentOrders.enabled) | Baseline; #57
34 | GS-034 | Shop accept/reject | Customer shopping (web + app) | Orders | P0 | COMPLETED | Production (gokesari.com) | Live | #14; #19; #65
35 | GS-035 | Substitution approval | Customer shopping (web + app) | Orders | P1 | COMPLETED | Production (gokesari.com) | Live | #14
36 | GS-036 | Pick and pack | Customer shopping (web + app) | Orders | P0 | COMPLETED | Production (gokesari.com) | Live | #14
37 | GS-037 | Gig worker onboarding | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline
38 | GS-038 | Online/offline status | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #19
39 | GS-039 | Job assignment | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #23
40 | GS-040 | Society priority assignment | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | #19
41 | GS-041 | Pickup OTP/QR | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | #14
42 | GS-042 | Live tracking | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #29
43 | GS-043 | Delivery OTP/POD | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | #14; #23; #65
44 | GS-044 | Society registration | Societies (housing) | Society | P1 | COMPLETED | Production (gokesari.com) | Live | #19
45 | GS-045 | Authorized Gig worker whitelist | Societies (housing) | Society | P0 | COMPLETED | Production (gokesari.com) | Live | #19
46 | GS-046 | Security notification | Societies (housing) | Society | P1 | COMPLETED | Production (gokesari.com) | Live | #19
47 | GS-047 | Delivery instructions | Societies (housing) | Society | P1 | COMPLETED | Production (gokesari.com) | Live | #19; #23
48 | GS-048 | Daily milk subscription | Subscriptions | Subscription | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline
49 | GS-049 | Recurring vegetables/daily goods | Subscriptions | Subscription | P1 | COMPLETED | Production (gokesari.com) | Live | Baseline; #19
50 | GS-050 | Subscription payment | Subscriptions | Subscription | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline
51 | GS-051 | Skip/pause/resume/cancel | Subscriptions | Subscription | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #65; #84
52 | GS-052 | Customer segmentation | Notifications, integrations & marketing | Marketing | P1 | COMPLETED | Production (gokesari.com) | Live | #19
53 | GS-053 | Shop promotional campaigns | Notifications, integrations & marketing | Marketing | P1 | COMPLETED | Production (gokesari.com) | Live | #19
54 | GS-054 | Referral program | Notifications, integrations & marketing | Marketing | P1 | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rule: customerReferrals.enabled; rewards Rs 50 / Rs 50) | Baseline; #57
55 | GS-055 | Order notifications | Notifications, integrations & marketing | Notifications | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #23
56 | GS-056 | Report an issue | Customer shopping (web + app) | Support | P0 | COMPLETED | Production (gokesari.com) | Live | #19
57 | GS-057 | Returns/refunds | Customer shopping (web + app) | Support | P0 | COMPLETED | Production (gokesari.com) | Live | #14; #23
58 | GS-058 | Dispute management | Customer shopping (web + app) | Support | P0 | COMPLETED | Production (gokesari.com) | Live | #40; #194
59 | GS-059 | Shop rating | Customer shopping (web + app) | Ratings | P1 | COMPLETED | Production (gokesari.com) | Live | #19
60 | GS-060 | Gig rating | Customer shopping (web + app) | Ratings | P1 | COMPLETED | Production (gokesari.com) | Live | #19
61 | GS-061 | Shop commission | Payments, wallet & finance | Finance | P0 | COMPLETED | Production (gokesari.com) | Live | #14
62 | GS-062 | Shop settlement | Payments, wallet & finance | Finance | P0 | COMPLETED | Production (gokesari.com) | Live | #14
63 | GS-063 | Gig earnings | Payments, wallet & finance | Finance | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #23
64 | GS-064 | Gig payout | Payments, wallet & finance | Finance | P0 | COMPLETED | Production (gokesari.com) | Live | #14
65 | GS-065 | Global dashboard | Admin & operator console | Admin | P0 | COMPLETED | Production (gokesari.com) | Live | #19; #23
66 | GS-066 | Operator console | Admin & operator console | Admin | P0 | COMPLETED | Production (gokesari.com) | Live | #19
67 | GS-067 | Audit logs | Admin & operator console | Admin | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14
68 | GS-068 | Fraud/risk rules | Admin & operator console | Admin | P1 | COMPLETED | Production (gokesari.com) | Live | #19
69 | GS-069 | Marketplace KPI dashboard | Admin & operator console | Analytics | P0 | COMPLETED | Production (gokesari.com) | Live | #19
70 | GS-070 | Privacy/consent management | Identity, access & security | Security | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #34; #78
71 | GS-071 | Data access controls | Identity, access & security | Security | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #73
72 | GS-072 | Maps/navigation | Notifications, integrations & marketing | Integration | P0 | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rule: routing.enabled) | Baseline; #23; #57
73 | GS-073 | Payment gateway | Notifications, integrations & marketing | Integration | P0 | COMPLETED | Production - built, switched off by default | Off until live gateway keys | Baseline; #194
74 | GS-074 | SMS/WhatsApp/email/push | Notifications, integrations & marketing | Integration | P1 | COMPLETED | Production - built, switched off by default | Email + in-app live; Expo push on mock until EAS / FCM / APNs keys; SMS / WhatsApp stubs | #23; #194
75 | WF-001 | Customer product purchase | Customer shopping (web + app) | Customer | - | COMPLETED | Production - built, switched off by default | Online payment at checkout built (sandbox); live keys needed | Baseline; #14; #19; #23; #24; #43; #57; #194
76 | WF-002 | Shop fulfillment | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live | #14; #24; #65
77 | WF-003 | Gig assignment | Platform, performance & QA | System | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #19; #23; #57; #65
78 | WF-004 | Society authorized delivery | Societies (housing) | System/Society | - | COMPLETED | Production (gokesari.com) | Live | #19
79 | WF-005 | Delivery | Delivery & riders (gig) | Gig | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #23; #29
80 | WF-006 | Subscription | Customer shopping (web + app) | Customer/System | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #65
81 | WF-007 | Return/refund | Customer shopping (web + app) | Customer/Operator | - | COMPLETED | Production (gokesari.com) | Live | #14; #23
82 | WF-008 | Shop onboarding | Seller Central (shop owner portal) | Shop/Operator | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #29; #47; #54; #65
83 | WF-009 | Marketing campaign | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live | #19
84 | WF-010 | Settlement | Payments, wallet & finance | System/Finance | - | COMPLETED | Production (gokesari.com) | Live | #14
85 | RBAC-001 | Browse/search | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline
86 | RBAC-002 | Place order | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #14
87 | RBAC-003 | Manage own shop | Identity, access & security | Security | - | COMPLETED | Production - built, switched off by default | OPERATOR_LIMITED role live on test; production by role grant | Baseline; #194
88 | RBAC-004 | Manage catalog | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #43
89 | RBAC-005 | Upload product lists | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline
90 | RBAC-006 | Verify shop | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline
91 | RBAC-007 | Assign delivery | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #23
92 | RBAC-008 | Manage own availability | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline
93 | RBAC-009 | Whitelist Gig workers | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | #19
94 | RBAC-010 | View all orders | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #19
95 | RBAC-011 | Refund approval | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | #14
96 | RBAC-012 | Settlement | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | #14
97 | RBAC-013 | Manage users/roles | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #32
98 | RBAC-014 | System configuration | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | #23
99 | RBAC-015 | Audit logs | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | #14
100 | SM-001 | Order state machine | Customer shopping (web + app) | Order | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #14
101 | SM-002 | Shop state machine | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live since release #65 (migration 0051); the approval gate follows statusModels.enforceTransitions (true) | #23; #57; #65
102 | SM-003 | Gig state machine | Delivery & riders (gig) | Gig | - | COMPLETED | Production (gokesari.com) | Live since release #57 (migration 0042) (statusModels.enforceTransitions = true) | #23; #57
103 | SM-004 | Subscription state machine | Subscriptions | Subscription | - | COMPLETED | Production (gokesari.com) | Live since release #65 (migration 0052) (renewal rule subscriptionRenewal on: 3 days' notice before the end date, 1 day of payment cover) | #19; #57; #65
104 | SM-005 | Payment state machine | Payments, wallet & finance | Payment | - | COMPLETED | Production - built, switched off by default | Off until live gateway keys | Baseline; #194
105 | SM-006 | Issue state machine | Customer shopping (web + app) | Issue | - | COMPLETED | Production (gokesari.com) | Live (help desk + grievance portal) | #19; #40; #194
106 | GA-001 | Society authorization | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | #19
107 | GA-002 | Society preferred partner | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | #19
108 | GA-003 | Distance | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline
109 | GA-004 | Availability | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline
110 | GA-005 | Current load | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rule: batching.enabled; F3 busy-rider fallback: dispatch.busyRidersAsFallback) | Baseline; #57; #65
111 | GA-006 | Shop readiness | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | #14
112 | GA-007 | Reliability | Delivery & riders (gig) | Delivery | P1 | COMPLETED | Production (gokesari.com) | Live | #19
113 | GA-008 | Fairness | Delivery & riders (gig) | Delivery | P1 | COMPLETED | Production (gokesari.com) | Live | #19
114 | GA-009 | No worker | Delivery & riders (gig) | Delivery | P0 | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #23
115 | NAV-001 | Customer portal - Home | Customer shopping (web + app) | Customer | - | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rule: homePriceComparison.enabled) | Baseline; #23; #57; #65; #69; #84; #123; #129; #131
116 | NAV-002 | Customer portal - Shop | Customer shopping (web + app) | Customer | - | COMPLETED | Production - built, switched off by default | Off by default - switch on in Admin > Business rules (rule: shopOffers.enabled) | Baseline; #19; #24; #57; #123; #126
117 | NAV-003 | Customer portal - Cart & Checkout | Customer shopping (web + app) | Customer | - | COMPLETED | Production - built, switched off by default | Online payment at checkout built (sandbox); coupons rule unchanged | Baseline; #23; #43; #71; #57; #194
118 | NAV-004 | Customer portal - Orders | Customer shopping (web + app) | Customer | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #29; #123
119 | NAV-005 | Customer portal - Subscriptions | Customer shopping (web + app) | Customer | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #65; #84; #123
120 | NAV-006 | Shop portal - Dashboard | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #23; #47; #123; #126
121 | NAV-007 | Shop portal - Catalog | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #43; #47; #82; #123; #126
122 | NAV-008 | Shop portal - Orders | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #14; #123
123 | NAV-009 | Shop portal - Marketing | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live | #19; #57
124 | NAV-010 | Shop portal - Finance | Seller Central (shop owner portal) | Shop | - | COMPLETED | Production (gokesari.com) | Live | #14; #65
125 | NAV-011 | Gig portal - Jobs | Delivery & riders (gig) | Gig | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #65
126 | NAV-012 | Gig portal - Earnings | Delivery & riders (gig) | Gig | - | COMPLETED | Production (gokesari.com) | Live | Baseline; #19; #23
127 | NAV-013 | Gig portal - Profile | Delivery & riders (gig) | Gig | - | COMPLETED | Production (gokesari.com) | Live | #19; #57
128 | NAV-014 | Society portal - Dashboard | Societies (housing) | Society | - | COMPLETED | Production (gokesari.com) | Live | #19
129 | NAV-015 | Operator portal - Operations | Admin & operator console | Operator | - | COMPLETED | Production (gokesari.com) | Live | #19; #73
130 | NAV-016 | Operator portal - Orders | Admin & operator console | Operator | - | COMPLETED | Production (gokesari.com) | Live | #19; #29; #73
131 | NAV-017 | Admin portal - Control Tower | Admin & operator console | Admin | - | COMPLETED | Production (gokesari.com) | Live | #19; #23; #73; #123; #126
132 | NAV-018 | Admin portal - Analytics | Admin & operator console | Admin | - | COMPLETED | Production (gokesari.com) | Live | #19
133 | NAV-019 | Admin portal - Security | Admin & operator console | Admin | - | COMPLETED | Production (gokesari.com) | Live | #19; #34
134 | KPI-001 | GMV | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
135 | KPI-002 | Order fill rate | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
136 | KPI-003 | Shop acceptance time | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
137 | KPI-004 | Pick-pack time | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
138 | KPI-005 | Assignment time | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
139 | KPI-006 | Delivery time | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
140 | KPI-007 | On-time delivery rate | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
141 | KPI-008 | Cancellation rate | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
142 | KPI-009 | Refund rate | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
143 | KPI-010 | Customer repeat rate | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
144 | KPI-011 | Subscription retention | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
145 | KPI-012 | Gig acceptance rate | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
146 | KPI-013 | Gig utilization | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
147 | KPI-014 | Shop retention | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
148 | KPI-015 | Marketing conversion | Admin & operator console | Analytics | - | COMPLETED | Production (gokesari.com) | Live | #19
149 | NEW-001 | Business-rules console (admin-tunable thresholds) | Admin & operator console | Admin | - | COMPLETED | Production (gokesari.com) | Live | #23
150 | NEW-002 | Shop suspension policy, impact preview & review | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live | #23
151 | NEW-003 | Order placed while the shop is closed | Customer shopping (web + app) | Orders | - | COMPLETED | Production (gokesari.com) | Live | #24
152 | NEW-004 | Rider arrival checkpoints & customer notices | Delivery & riders (gig) | Delivery | - | COMPLETED | Production (gokesari.com) | Live | #23
153 | NEW-005 | Minimum order value, pause new orders, extra delivery PIN zones | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live | #23
154 | NEW-006 | D10 cancellation & refund policy (verified) | Customer shopping (web + app) | Orders | - | COMPLETED | Production (gokesari.com) | Live | #14; #23; #194
155 | NEW-007 | Direct per-order payments, tax invoicing, photo POD, accept timeout | Payments, wallet & finance | Payments | - | COMPLETED | Production - built, switched off by default | All four parts built; per-order online payment off until live keys | #23; #65; #194
156 | NEW-008 | Product category master & shop product-category visibility | Seller Central (shop owner portal) | Catalog | - | COMPLETED | Production (gokesari.com) | Live | #43
157 | NEW-009 | Explicit Save flow on admin screens (categories, privileges, user profiles) | Admin & operator console | Admin | - | COMPLETED | Production (gokesari.com) | Live | #32
158 | NEW-010 | Shop inventory fill when a category is added; per-shop prices | Seller Central (shop owner portal) | Catalog | - | COMPLETED | Production (gokesari.com) | Live | #47
159 | NEW-011 | GoKesari logo mark, name, tagline and favicon | Platform, performance & QA | Branding | - | COMPLETED | Production (gokesari.com) | Live | #60; #62
160 | NEW-012 | Product card quantity controls; search bar row; cart state after reload | Customer shopping (web + app) | Cart | - | COMPLETED | Production (gokesari.com) | Live | #71; #73
161 | NEW-013 | Home page speed, accessibility and error boundary | Customer shopping (web + app) | Home | - | COMPLETED | Production (gokesari.com) | Live | #65; #69
162 | NEW-014 | Data-exposure hardening (only screen fields reach browsers) | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | #65; #73
163 | NEW-015 | Header role menus link operations and rider pages | Customer shopping (web + app) | Navigation | - | COMPLETED | Production (gokesari.com) | Live | #73
164 | NEW-016 | Notification settings and marketing-consent switch | Notifications, integrations & marketing | Notifications | - | COMPLETED | Production (gokesari.com) | Live | #76; #78
165 | NEW-017 | Shop photo catalogue (/shop/catalogue) | Seller Central (shop owner portal) | Catalog | - | COMPLETED | Production (gokesari.com) | Live | #82; #84
166 | NEW-018 | OTP request privacy - same reply for every request | Identity, access & security | Identity & Access | - | COMPLETED | Production (gokesari.com) | Live | #81
167 | NEW-019 | Home and Shops redesign; Tomorrow's delivery card | Customer shopping (web + app) | Home | - | COMPLETED | Production (gokesari.com) | Live | #84
168 | NEW-020 | Cancellation before packing - full refund; optional customer cancel until packing (item A) | Customer shopping (web + app) | Orders | - | COMPLETED | Production - built, switched off by default | Off by default - rule cancellation.customerMayCancelUntil = CONFIRMED (the original behaviour); PREPARING turns it on | #86 (reverted by #87); #120; #194
169 | NEW-021 | Business limits editable at /admin/settings (item B) | Admin & operator console | Admin | - | COMPLETED | Production (gokesari.com) | Live (defaults identical to the old fixed values) | #86 (reverted by #87); #120; #126
170 | NEW-022 | Shop's own customer contact phone / WhatsApp (item C1) | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live (rule shopContact = SHOP_CONTACT) | #86 (reverted by #87); #120
171 | NEW-023 | Only verified societies can add or prefer riders (item C2) | Societies (housing) | Society | - | COMPLETED | Production (gokesari.com) | Live (rule societyRiders.requireVerifiedSociety = true) | #86 (reverted by #87); #120
172 | NEW-024 | Open-order prompt before paying (item C3) | Customer shopping (web + app) | Cart | - | COMPLETED | Production (gokesari.com) | Live (rule openOrderCheck on, ANY_SHOP) | #86 (reverted by #87); #120
173 | NEW-025 | Voucher codes visible to operators and admins (item C4) | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | Behaviour already live; tests released with the next production release
174 | NEW-026 | Rider files: access-checked photos, KYC documents, rider ID card (item C5) | Delivery & riders (gig) | Delivery | - | COMPLETED | Production (gokesari.com) | Live (rule riderFiles: protected photos, KYC documents, ID card) | #86 (reverted by #87); #120
175 | NEW-027 | GST rates / HSN codes report for the CA; cron map (item D) | Payments, wallet & finance | Finance | - | BLOCKED | Production (gokesari.com) | - | #120
176 | NEW-028 | Event layer: real-time workflows, cron only as a safety net | Notifications, integrations & marketing | Event layer | - | COMPLETED | Production (gokesari.com) | Live (rule defaults; no off switch) | #120
177 | NEW-029 | Live delivery tracking v2 (5-second polling) | Delivery & riders (gig) | Delivery | - | COMPLETED | Production (gokesari.com) | Live (rule defaults; no off switch) | #120
178 | NEW-030 | Seller verification events, 'more info' and optional auto-approval | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live (rule defaults; no off switch) | #120
179 | NEW-031 | Dispute conversation, attachments and 24 h SLA escalation | Customer shopping (web + app) | Support | - | COMPLETED | Production (gokesari.com) | Live (rule defaults; no off switch) | #120
180 | NEW-032 | Per-order risk rules at placement and on failed payment | Admin & operator console | Admin | - | COMPLETED | Production (gokesari.com) | Live (rule defaults; no off switch) | #120
181 | NEW-033 | Shop prepaid wallet | Payments, wallet & finance | Finance | - | COMPLETED | Production - built, switched off by default | Off by default - rule shopWallet.enabled = false (on for the test site only) | #120
182 | NEW-034 | Shop wallet: Rs 5/km delivery charge, no checkout below minimum, commission back on refunds | Payments, wallet & finance | Finance | - | COMPLETED | Production - built, switched off by default | Off by default - rule shopWallet.enabled = false (on for the test site only) | #120
183 | NEW-035 | OTP-confirmed delivery hardening | Delivery & riders (gig) | Delivery | - | COMPLETED | Production (gokesari.com) | Live (code emailed; SMS needs D2) | #120
184 | NEW-036 | Shop product media - photos and descriptions (Module 1) | Seller Central (shop owner portal) | Catalog | - | COMPLETED | Production (gokesari.com) | Live | #120
185 | NEW-037 | Accounting / inventory integration and GST (Module 2) | Notifications, integrations & marketing | Integration | - | COMPLETED | Production (gokesari.com) | GST invoice per order live; inventory sync descoped (rule inventorySync OFF) | #120; #194
186 | NEW-038 | Shop self-registration with auto-approval (Module 3) | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production - built, switched off by default | Off by default - rule selfRegistration.enabled = false; refused on gokesari.com until a real SMS/WhatsApp provider is set | #120
187 | NEW-039 | Delivery options and scheduling: pickup, shop's own delivery, GoKesari partner | Delivery & riders (gig) | Delivery | - | COMPLETED | Production - built, switched off by default | Off by default - rule fulfilmentOptions.enabled = false (on for the test site only) | #120
188 | NEW-040 | Mandatory legal documents by shop type (FSSAI, drug licence, medical registration) | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production - built, switched off by default | Off by default - rule legalDocuments.enabled = false (on for the test site only) | #120
189 | NEW-041 | Bank account details with Rs 1 verification (shops for payouts, customers for refunds) | Payments, wallet & finance | Payments | - | COMPLETED | Production - built, switched off by default | Off by default - rule bankAccounts.enabled = false (on for the test site only) | #120
190 | NEW-042 | Mandatory referral code at shop registration + 'Request a referral code' | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production - built, switched off by default | Admin > Referral settings: referral_required_shop = OPTIONAL on production (checked 14 Oct) | #120
191 | NEW-043 | Android and iPhone app (mobile/) - native shell around gokesari.com | Mobile apps (Android / iPhone) | Mobile App | - | IN PROGRESS | Mobile app - Android test builds only (not in stores) | Android APK from the 'Android APK' workflow (test signing key); not on Google Play or the App Store | #100 (code on main; no store release)
192 | NEW-044 | Website support for the app: Google sign-in hand-off and deep-link files | Mobile apps (Android / iPhone) | Mobile App | - | COMPLETED | Production (gokesari.com) | Sign-in hand-off live; deep links off until MOBILE_* env vars are set (after the first store build) - assetlinks.json answers 404 today | #100
193 | NEW-045 | iPhone home-screen app (web app manifest, full-screen, Back button) | Mobile apps (Android / iPhone) | Mobile App | - | COMPLETED | Production (gokesari.com) | Live | #100
194 | NEW-046 | Tile Board home screens (approved 'Theme 1 Tile Board') for customer, shop owner, admin and operator | Customer shopping (web + app) | Navigation / UX | - | COMPLETED | Production (gokesari.com) | Live | #120; #123; #126; #129; #131
195 | NEW-047 | Language switch EN / Hindi / Marathi (boards, header and menus on every page) | Customer shopping (web + app) | Navigation / UX | - | COMPLETED | Production (gokesari.com) | Live | #120; #123
196 | NEW-048 | Mandatory customer referral code at sign-up, with 'ask us for a code' | Notifications, integrations & marketing | Marketing | - | COMPLETED | Production - built, switched off by default | Admin > Referral settings: referral_required_customer = OPTIONAL on production (checked 14 Oct) | #120
197 | NEW-049 | Refunds to the customer's verified bank account | Payments, wallet & finance | Payments | - | COMPLETED | Production - built, switched off by default | Off by default - rule bankRefunds.enabled = false | #120
198 | NEW-050 | Bank account checked with the bank (Cashfree Verification Suite) instead of the Rs 1 payment | Payments, wallet & finance | Payments | - | COMPLETED | Production - built, switched off by default | Off by default - rule bankAccountCheck.enabled = false | #120
199 | NEW-051 | Tile Board everywhere: one path to every function | Customer shopping (web + app) | Navigation / UX | - | COMPLETED | Production (gokesari.com) | Live | #123
200 | NEW-052 | Status tabs and paging on lists; one screen per view on the longest pages | Customer shopping (web + app) | Navigation / UX | - | COMPLETED | Production (gokesari.com) | Live | #123; #126
201 | NEW-053 | Error, not-found and offline screens; progress bar; confirm before destructive actions | Customer shopping (web + app) | Navigation / UX | - | COMPLETED | Production (gokesari.com) | Live | #123
202 | NEW-054 | Accessibility pass: touch targets, text size, contrast | Customer shopping (web + app) | Navigation / UX | - | COMPLETED | Production (gokesari.com) | Live | #123; #126
203 | NEW-055 | Product cards and shop page for phones | Customer shopping (web + app) | Catalogue / UX | - | COMPLETED | Production (gokesari.com) | Live | #123
204 | NEW-056 | Sign-in: one Terms & Privacy box instead of three | Identity, access & security | Identity & Access | - | COMPLETED | Production (gokesari.com) | Live | #123
205 | NEW-057 | Nearby shops from the real location (/shops/nearby) | Customer shopping (web + app) | Location | - | COMPLETED | Production (gokesari.com) | Live (no rule; needs the Maps keys) | #135
206 | NEW-058 | Referral code Mandatory / Optional set by admin (customers and shops) | Identity, access & security | Identity & Access | - | COMPLETED | Production (gokesari.com) | Live - both OPTIONAL on production (checked 14 Oct: /api/referral-settings) | #135
207 | NEW-059 | Admin 'Shops without location' list and coordinates backfill | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live | #135
208 | NEW-060 | GoKesari Seller Central (shop owner workspace) and the 'Sell on GoKesari' page (/sell) | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live | #143
209 | NEW-062 | Document upload with auto-read (file or camera), review and Verify & Approve | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live - rule documentUpload.enabled = on; photos read in the owner's browser (DOCUMENT_OCR_BROWSER on by default; 'off' = server only) | #149; #175 (#169 cherry-picked); #177 (same commit, no change)
210 | NEW-063 | FSSAI licence mandatory for food shops | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live - rule documentUpload.fssaiMandatoryForFood = on | #149
211 | NEW-064 | Compact footer and saffron GoKesari wordmark (site, Seller Central, sign-in, emails) | Platform, performance & QA | Branding | - | COMPLETED | Production (gokesari.com) | Live | #149; #151; #157
212 | NEW-065 | Fix: Admin > Referral codes showed 0 shops (Societies showed 0 members) | Notifications, integrations & marketing | Marketing | - | COMPLETED | Production (gokesari.com) | Live | #139
213 | NEW-066 | Seller Central shop switcher for owners with several shops | Seller Central (shop owner portal) | Shop Onboarding | - | COMPLETED | Production (gokesari.com) | Live (no rule) | #175 (15 Oct, live 14:43 UTC)
214 | NEW-067 | Inventory & Accounting for shop owners (/shop/accounts): stock ledger, books, GST returns, supplier bill capture | Seller Central (shop owner portal) | Inventory | - | COMPLETED | Production (gokesari.com) | Live (shop owners: Inventory -> Bills & GST); GST portal link off on production (file upload), AI bill reading off | #179 (release, acfaa6a; migrations 0076-0078)
215 | PMD-001 | Product Master Data Platform (pmd schema, pipeline, matching, review queue) | Product Master Data Platform | Product Master | - | COMPLETED | Production (gokesari.com) | Live (operators/admins) | #8; #50; #131
216 | PMD-002 | GS1 India and manufacturer-catalogue feeds | Product Master Data Platform | Product Master | - | COMPLETED | Production - built, switched off by default | Manufacturer portal on; GS1 DataKart (mock) and Open Food Facts off (Admin > Settings) | #8; #194
217 | PMD-003 | Loader rework for scale (bulk path, workers) | Product Master Data Platform | Product Master | - | COMPLETED | Production (gokesari.com) | Live (CLI) | #8; #185 (#184 race fix)
218 | PMD-004 | Promote master products into the shop catalogue | Product Master Data Platform | Product Master | - | COMPLETED | Production (gokesari.com) | Live (CLI) | #8
219 | PMD-005 | Apply duplicate-review decisions in bulk | Product Master Data Platform | Product Master | - | COMPLETED | Production (gokesari.com) | Live (CLI) | #12
220 | PMD-006 | Large-scale ingestion (pilot step 9) | Product Master Data Platform | Product Master | - | COMPLETED | Production (gokesari.com) | Live (admin) | #194
221 | PMD-007 | Product browser / edit screens, promote button, scheduler and alerting | Product Master Data Platform | Product Master | - | COMPLETED | Production (gokesari.com) | Live (admin product browser) | #194
222 | PLT-001 | Hostinger build and dev server (webpack, @/ alias) | Platform, performance & QA | Platform | - | COMPLETED | Production (gokesari.com) | Live | #19; #35
223 | PLT-002 | Root-cause logging for failed database queries | Platform, performance & QA | Platform | - | COMPLETED | Production (gokesari.com) | Live | #19
224 | PLT-003 | CI pipeline (typecheck, lint, tests on PostgreSQL, build) | Platform, performance & QA | Platform | - | COMPLETED | Production (gokesari.com) | Live | #8
225 | PLT-004 | Dependency security patches | Identity, access & security | Security | - | COMPLETED | Production (gokesari.com) | Live | #19; #65
226 | PLT-005 | GoKesari domain and repository hygiene | Platform, performance & QA | Platform | - | COMPLETED | Production (gokesari.com) | Live | #32; #36; #43
227 | PLT-006 | Deployment runbooks | Platform, performance & QA | Platform | - | COMPLETED | Production (gokesari.com) | Live | #37; #88
228 | PLT-007 | Opt-in automatic migration during the build (MIGRATE_ON_BUILD) | Platform, performance & QA | Platform | - | COMPLETED | Production (gokesari.com) | On for gokesari.com and test.gokesari.com (MIGRATE_ON_BUILD=true) | #120
229 | PLT-008 | 'Test database' workflow (backup, migrate, settings, verify) | Platform, performance & QA | Platform | - | COMPLETED | GitHub Actions (runs from staging) | Live for the test database | Not needed (test only)
230 | PLT-009 | 'Production database' workflow (verify / migrate with typed confirmation) | Platform, performance & QA | Platform | - | COMPLETED | GitHub Actions (runs from main) | Live | #118; #194
231 | PLT-010 | 'Android APK' workflow - installable test builds without any accounts | Platform, performance & QA | Platform | - | COMPLETED | GitHub Actions (runs from main) | Live | #100
232 | PLT-011 | 'Sandbox payment' workflow - pay Cashfree sandbox checkouts for E2E tests | Platform, performance & QA | Platform | - | COMPLETED | GitHub Actions (runs from staging) | Live for the test site | Not needed (test only)
233 | PLT-012 | One database read per fact per page render | Platform, performance & QA | Performance | - | COMPLETED | Production (gokesari.com) | Live | #126
234 | PLT-013 | Opt-in prepared statements (DATABASE_PREPARED_STATEMENTS=on) | Platform, performance & QA | Performance | - | COMPLETED | Production - built, switched off by default | Off - environment variable not set on either site | #126
235 | PLT-014 | Board figures: shared cache and 8 s allowance | Platform, performance & QA | Performance | - | COMPLETED | Production (gokesari.com) | Live | #129; #131
236 | PLT-015 | Seller / customer database split (tooling and 'Database split' workflow) | Platform, performance & QA | Platform | - | BLOCKED | GitHub Actions (runs from main) | Site still reads one database (DB_SPLIT_MODE = single); the split databases are copies only | #149; #157; #159; #161; #163
237 | PLT-016 | CI scope job: skip runs that cannot find anything new | Platform, performance & QA | Platform | - | COMPLETED | GitHub Actions (runs from main) | Live | #135
238 | PLT-017 | 'iPhone app' workflow - EAS build and TestFlight upload | Mobile apps (Android / iPhone) | Mobile App | - | BLOCKED | GitHub Actions (runs from main) | Not run yet | #157
239 | PLT-018 | 'Copy shops to production' workflow (plan / copy / sql modes) | Platform, performance & QA | Platform | - | COMPLETED | GitHub Actions (runs from main) | Used once (sql mode, 12-13 Oct) | #141; #145; #157
240 | QA-001 | Automated test suites (unit, integration, E2E) | Platform, performance & QA | QA | - | COMPLETED | Production (gokesari.com) | Live in CI | #54 (via staging); #70
241 | QA-002 | Test execution framework for 791 test cases | Platform, performance & QA | QA | - | COMPLETED | Production (gokesari.com) | Live | #70
242 | QA-003 | Execute the 791 test cases and sign off in a browser on test.gokesari.com | Platform, performance & QA | QA | - | BLOCKED | Not started | - | #194
243 | QA-004 | Four-features browser test run on test.gokesari.com (all roles, phone + desktop) | Platform, performance & QA | QA | - | COMPLETED | Test site only (test.gokesari.com) | - | Not needed (test only)
244 | QA-005 | Tile Board UI pass test run on test.gokesari.com (all roles, phone, app size, slow 4G, Lighthouse) | Platform, performance & QA | QA | - | COMPLETED | Test site only (test.gokesari.com) | - | Not needed (test only)
245 | QA-006 | Nearby shops + referral settings test run (test site, Android / iPhone / desktop; production checks) | Platform, performance & QA | QA | - | COMPLETED | Test site only (test.gokesari.com) | - | Not needed (test only)
246 | QA-007 | 13 Oct release test run (document upload, FSSAI, footer, branding, DB split) | Platform, performance & QA | QA | - | COMPLETED | Test site only (test.gokesari.com) | - | Not needed (test only)
247 | QA-008 | Order-lifecycle run on staging (sign-up -> order -> delivery code -> done) | Platform, performance & QA | QA | - | COMPLETED | Test site only (test.gokesari.com) | - | Not needed (test only)
248 | QA-009 | Order-lifecycle run on production (gokesari.com) with a real payment | Platform, performance & QA | QA | - | BLOCKED | Not started | - | -
249 | GAP-001 | Pickup QR code | Delivery & riders (gig) | Delivery | - | COMPLETED | Production - built, switched off by default | Off - rule pickupQr.enabled; set PICKUP_QR_SECRET first | #194
250 | GAP-002 | In-app turn-by-turn navigation | Delivery & riders (gig) | Delivery | - | COMPLETED | Production - built, switched off by default | Off - rule riderNavigation.enabled; Google Routes / OSRM provider (mock on test) | #194
251 | GAP-003 | Signature capture at delivery | Delivery & riders (gig) | Delivery | - | YET TO START | Not started | - | -
252 | GAP-004 | Broadcast job offers / radius widening | Delivery & riders (gig) | Delivery | - | COMPLETED | Production - built, switched off by default | Off - rule dispatchBroadcast.enabled (radius 2 > 4 > 6 km) | #194
253 | GAP-005 | Automated bank transfer for settlements and rider payouts | Payments, wallet & finance | Finance | - | COMPLETED | Production - built, switched off by default | Off - PayoutProvider on sandbox | #194
254 | GAP-006 | Platform tax invoice for GoKesari's own fees (D6) | Payments, wallet & finance | Finance | - | COMPLETED | Production - built, switched off by default | Off until GoKesari GSTIN, legal details and invoice prefix | #194
255 | GAP-007 | Customer Cancel button on My Orders | Customer shopping (web + app) | Orders | - | COMPLETED | Production (gokesari.com) | Live - follows rule cancellation (CONFIRMED orders by default; until packing when customerMayCancelUntil = PREPARING) | #123
256 | GAP-008 | Map 'Confirm location' answers 500 on test.gokesari.com | Customer shopping (web + app) | Location | - | BLOCKED | Test site only (test.gokesari.com) | - | -
257 | GAP-009 | Email sending capacity (mail host hourly limit) | Notifications, integrations & marketing | Notifications | - | YET TO START | Not started | - | -
258 | GAP-010 | Slow signed-in pages and cold first visits (database far from the web server) | Platform, performance & QA | Performance | - | BLOCKED | Not started | - | -
259 | GAP-011 | Search shows '0 shops' for products that nearby shops sell | Customer shopping (web + app) | Search | - | YET TO START | Not started | - | -
260 | GAP-012 | Admin dispute resolution gives no visible confirmation | Customer shopping (web + app) | Disputes | - | YET TO START | Not started | - | -
261 | GAP-013 | Approved return waiting for a rider cannot be completed by staff | Customer shopping (web + app) | Returns | - | YET TO START | Not started | - | -
262 | GAP-014 | /orders?tab=returns shows the Active list | Customer shopping (web + app) | Orders | - | YET TO START | Not started | - | -
263 | GAP-015 | Hindi / Marathi for the body of inner pages | Customer shopping (web + app) | Navigation / UX | - | YET TO START | Not started | - | -
264 | GAP-016 | Same Drizzle bare-id subquery bug in rider reliability and the integrations 'listed' flag | Platform, performance & QA | Platform | - | YET TO START | Not started | - | -
265 | GAP-017 | React error #418 (hydration) on /wallet and /admin/orders | Platform, performance & QA | Platform | - | YET TO START | Not started | - | -
266 | GAP-018 | My Orders card wording after an order is switched to pickup | Customer shopping (web + app) | Orders | - | YET TO START | Not started | - | -
267 | GAP-019 | Wallet checkout takes 30-38 s on the test site | Customer shopping (web + app) | Checkout | - | YET TO START | Not started | - | -

## Decisions pending
# | Type | Decision / input | What is needed | Unblocks | Who | Status
12 | Decision | Which off-by-default features to switch on in production | Choose which of the now-released off-by-default features to switch on in production: F3-F11 and #58 rules, plus fulfilmentOptions, legalDocuments, bankAccounts, bankRefunds, bankAccountCheck, shopReferral, customerSignupReferral, shopWallet, selfRegistration, cancellation PREPARING (all off on gokesari.com after #120). | GS-014, GS-027, GS-033, GS-054, GS-072, GA-005, NAV-001, NAV-002, NAV-003, NEW-007 | Owner | PENDING
13 | Decision | Event-layer decisions to confirm | Dispatch starts at READY; customer not told when a rider declines; shops propose resolutions only after triage; auto-approved shops classified GREEN; 'support' = operators + admins. | NEW-028, NEW-030, NEW-031 | Owner | PENDING CONFIRMATION
14 | Vendor | Gridlines live keys (seller verification) | Sandbox then live keys; confirm FSSAI / GSTIN fields, Shop Act coverage, IP whitelist, retention and DPA. Production shows verification as paused until then. | GS-007 automatic checks | Owner | PENDING
15 | Legal / CA | CA check of GST rates, HSN codes and invoice wording | Run scripts/gst-hsn-report.sql and have a CA confirm rates, HSN codes, bill-of-supply wording and numbering before invoicing is used for filing. Update 15 Oct: also covers the GST liability, set-off and invoice figures in Inventory & Accounting (NEW-067, on test). | NEW-007 (invoicing), NEW-027 | Owner / CA | PENDING
16 | Legal | Seller-verification retention and Shop Act needs | Lawyer/CA to confirm the retention period after closure (default 1,095 days) and Shop Act needs for non-MH / home sellers. | GS-007 compliance | Owner / lawyer | PENDING
17 | Legal | Holding shops' prepaid money | Legal review of the shop prepaid wallet; at least a seller-terms clause. | NEW-033, NEW-034 | Owner / lawyer | PENDING
19 | Agreement | GS1 India and brand permissions | Agreement / written permission and a real sample file for each source; then go-ahead for large-scale ingestion. | PMD-002, PMD-006 | Owner | PENDING
24 | Vendor | Cashfree live keys and Refunds API | Set CASHFREE_APP_ID / CASHFREE_SECRET_KEY / CASHFREE_ENV=production and confirm the Refunds API is enabled - the Rs 1 bank-account check refunds every payment. | NEW-041 | Owner | PENDING
34 | Decision | Tile Board: build the four entries that have no feature behind them? | Customer Favourites, App theme, Call rider (rider number is not shown to customers today); shop owner Theme. The board shows the nearest real page in their place. | NEW-046 | Owner | PENDING
38 | Decision | Translate the body of inner pages into Hindi / Marathi? | Boards, header, menus, tabs and error screens are translated; forms, tables and policy pages are English. Thousands of strings; needs a native-speaker review. | GAP-015; NEW-047 | Owner | PENDING
52 | Decision / vendor | Inventory & Accounting: licensed GSP for GST returns | Choose and contract a GSP (Masters India, ClearTax, IRIS, Tally GSP, Vayana) for live GSTR-2B/2A/1 pull; until then owners upload the file from gst.gov.in (works on production). | IA-022, IA-023 | Owner | OPEN
53 | Decision | Inventory & Accounting: AI reading of supplier bills | Allow bills to be read by Claude (ANTHROPIC_API_KEY + INVOICE_EXTRACTION_PROVIDER=claude): needed for photos, handwriting, Hindi and Marathi. Without it: e-invoice, Excel, PDF text and typing. | IA-034, IA-039 | Owner | OPEN
55 | Vendor | Inventory & Accounting: bill forwarding by email and S3 bucket | Inbound mail provider (INBOUND_EMAIL_SECRET / _DOMAIN) for forwarding; S3-compatible bucket credentials (ACCOUNTS_S3_*) - bills stay in the database until then. | IA-032, IA-049 | Owner | OPEN
60 | Legal / CA | CA confirmation of TCS / TDS / SAC rates | Rates looked up 18 Oct; CA must confirm before production use | GAP-005, GAP-006 | Owner / CA | PENDING
64 | Owner choice | Switch on the new batch features in production | Every batch feature is OFF on gokesari.com: online payments, broadcast offers, pickup QR (needs PICKUP_QR_SECRET), rider navigation, payouts, fee invoices, push | GAP-001, GAP-002, GAP-004, GAP-005, GAP-006, GS-028 | Owner | PENDING

## Go-live blockers
# | Type | Blocker | Detail | Unblocks | Who | Status
3 | Go-live blocker | No recorded browser / QA sign-off | Execute the 791-case plan (smoke, P0, P1, P2) on test.gokesari.com and record results. Progress 9 Oct: the first recorded browser run (four features + regression, 8-9 Oct, TEST_RESULTS.md) - the 791-case plan itself is still not run. 10 Oct: second recorded run - Tile Board UI pass, 1,026 of 1,038 checks PASS (QA-005). | QA-003; QA-005; go-live | QA / owner | OPEN
4 | Go-live blocker | Production cron jobs | Schedule seller-verification, dispute-escalation, shop-acceptance, delivery-dispatch and notifications on gokesari.com; add timeout-sweep and notification-retry when the event layer ships. Not confirmed since 6 Oct. The daily seller-verification job now also starts legal-document grace periods and sends expiry reminders (NEW-040). | GS-007, GS-058, NEW-007, NEW-028 | Owner | OPEN
18 | Owner inputs | Inputs for PR #92 modules 2 and 3 | Modules 2 and 3 are on gokesari.com since #120 (module 2 on mock providers, module 3 switched off). Inputs P1-P6 are needed before using them for real. | NEW-037, NEW-038 | Owner | PENDING
25 | Go-live blocker | Email sending capacity | The test site hit the mail host's hourly cap (451). Raise the limit or use a transactional email service before go-live; check SPF/DKIM for gokesari.com. | GAP-009, GS-055, NEW-039-042 | Owner | OPEN
26 | Owner inputs | referrals@gokesari.com and referral codes | Create the mailbox and confirm mail arrives (not readable from the test run); decide who else gets requests (shopReferral.notifyEmails); create referral codes before switching shopReferral.required on. | NEW-042 | Owner | PENDING
29 | Accounts | App store publishing | Expo account + EAS project id in mobile/app.config.ts; Google Play Console ($25) with the first .aab uploaded by hand; Apple Developer Program ($99/yr); store listings (privacy policy URL, Data safety form, screenshots). Then set MOBILE_* env vars for deep links. Update 14 Oct: the 'iPhone app' workflow (#153) is ready; it needs EXPO_TOKEN, ASC_API_KEY_P8, ASC_KEY_ID, ASC_ISSUER_ID, APPLE_TEAM_ID, the Expo project id and the App Store Connect app record. 18 Oct: store publishing ON HOLD by owner decision. | NEW-043, NEW-044 | Owner | ON HOLD
33 | Security | Rotate database passwords before go-live | Urgent: the production Neon neondb_owner password was posted in a chat on 12 Oct - reset it now and update DATABASE_URL in hPanel (and the GitHub secrets). Rotate the other database passwords before go-live as planned. | Go-live | Owner | OPEN
39 | Security | Delete the downloaded copy-shops SQL files | copy-shops-1-PREVIEW.sql / copy-shops-2-APPLY.sql hold the 5 owners' contact details - delete every downloaded copy. | PLT-018 | Owner | OPEN
40 | Owner inputs | Copied shops: sign-in, legal documents, two shops without location | The 5 copied owners sign in on gokesari.com and upload their legal documents; add map locations for the 2 original production shops (Asmy super market x2) so Nearby can list them. | PLT-018, NEW-057, NEW-040 | Owner | PENDING
44 | Owner inputs | Production order-lifecycle run (real payment) | For QA-009: a production shop with delivery on and its owner's sign-in email; an approved rider (or permission to register one for approval); confirmation that the Cashfree live keys are set; the owner pays the small real top-up. No test data or sandbox keys on gokesari.com. Listed again in Owner inputs §14 (18 Oct). | QA-009 | Owner | PENDING
50 | Go-live blocker | Bulk upload: mobile store builds | EAS / Expo account and Apple Developer account for the AAB and the iPhone build | BPU-10, BPU-11 | Owner | OPEN
51 | Owner action | Inventory & Accounting: INTEGRATION_ENCRYPTION_KEY value | The variable is set on test and production but is not base64 of 32 bytes (test reports encryption not configured; GST link answers 500). Set `openssl rand -base64 32` (a different value per site) in Hostinger and redeploy. | IA-056, IA-020, IA-048, NEW-037 | Owner | OPEN
54 | Owner action | Inventory & Accounting: crons | Schedule POST /api/cron/gst-reminders daily and /api/cron/bill-captures every 10 min (Bearer CRON_SECRET) on both sites. | IA-027, IA-050 | Owner | OPEN
57 | Owner inputs | Payment gateway live keys and webhook secrets | PAYMENT_GATEWAY + Cashfree (or Razorpay / PhonePe) live keys; payment and payout webhook secrets | GS-028, GS-073, SM-005, WF-001, NAV-003, NEW-007, GS-058 | Owner | PENDING
58 | Owner inputs | Payout account and keys | RazorpayX / Cashfree payout account and keys for the 5-day shop payouts | GAP-005 | Owner | PENDING
59 | Owner inputs | GoKesari GSTIN, legal details and invoice prefix | For GoKesari fee invoices (F10.2.5) | GAP-006 | Owner | PENDING
61 | Owner inputs | Grievance Officer details | Name, contact and address to publish on the grievance portal (consumer protection rules) | SM-006 | Owner | PENDING
62 | Owner inputs | Deep links: Android signing fingerprint and Apple Team ID | MOBILE_* values so gokesari.com links open the app | NEW-044 | Owner | PENDING
63 | Owner inputs | Mobile push keys | EAS project + FCM / APNs keys for real push notifications (app 1.2.0) | GS-074, NEW-043 | Owner | PENDING
65 | Owner inputs | Batch cron jobs on both sites | payments-reconcile (5 min), auth-housekeeping, timeout-sweep, payouts and the other entries in crontab.txt | GS-028, GAP-004, GAP-005 | Owner | PENDING