## Dealer programme
ID | Module | What it does | Priority | Build step | Migration | Commit(s) | Built | Local + CI tests | Staging (test.gokesari.com) | Production
FLAGS | Feature flags & geo areas | Four flags, per district; Maharashtra districts, Pune talukas / localities, PIN prefixes; DEALER role | P0 | 1 | 0101, 0102, 0103 | bc3f93a | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
FEE-SLABS | Registration fee slabs | Admin-defined fee slabs by declared turnover (up to 20) | P0 | 1 | — | 973d520 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-DR-001 | Dealer registration | Application by type, mobile OTP, e-mail, documents per type, ₹1 bank check, agreement | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-DR-002 | Dealer documents & approval | Configurable document requirements; admin approval queue; suspend / reject / terminate | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-DR-003 | Dealer codes, link & QR | GKS-MH-<district>-code, share link /shop/register?ref=, QR, suspend / replace | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-DR-004 | Employees | Salespeople with optional Employee ID; legacy distributors migrated as dealers | P0 | 2 | 0104 | 3d92aaf | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-SH-001 | Self-registration attribution | Code typed or from ?ref=, optional Employee ID field | P0 | 3 | 0105 | 611f979 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-SH-002 | Dealer-assisted registration | Dealer registers with the owner; owner confirms with a code | P0 | 3 | 0105 | 611f979 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-SH-003 | Duplicates | Phone / GSTIN / name within 150 m flagged; no commission | P0 | 3 | 0105 | 611f979 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-RA-001 | Attribution & claims | 30-day leads (cap 200), attribution priority, dealer claims decided by staff | P0 | 3 | 0105 | 611f979 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-SH-004 | Instant approval on GST/PAN + payment | Government check + gateway fee → approved; ready-for-upload e-mail; evidence log; retry when source down | P0 | 4 | 0106 | 4500808, 6db91cd | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-CM-001 | Commission rules | Fixed / % / both, per shop type, district, milestone, versioned, admin only | P0 | 5 | 0107 | 22a74db | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-CM-002 | Ledger & payouts | Earned → approved → paid; cap with override; reversals; payouts with bank reference; CSV statement; hold for shops approved without documents | P0 | 5 | 0107 | 22a74db, 9e3e1b7 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-CM-003 | Rating & bonus | Rating 0–10 by live shops (slabs), start rating, downgrade, bonus | P0 | 5 | 0107 | 22a74db | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-DB-001 | Dealer dashboard | Tiles, pending, performance by day / week / month, employees, areas; admin dealer list | P0 | 6 | — | 89f66b9, c9ea939 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-SP-001 | Support services | General (free), product upload, price update; admin charges; wallet / online pay; tickets; refunds | P0 | 7 | 0108 | c70e869 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-GEO-001 | Coverage map & targets | Areas with dealers, shops, operational, target vs registered, gaps; drawn map | P1 | 8 | 0110 | bf53b23 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-AN-001 | Performance score | Weighted score (admin weights), ranked within district | P1 | 8 | — | bf53b23 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-AN-002 | Activation & 30-day activity | Per dealer and employee | P1 | 8 | — | bf53b23 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
APP | Mobile app parity | Website in the app shell; app links; downloads and print through the bridge | P0 | 9 | — | c89cf0b | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
DOCS | Guides & report | Admin guide, dealer onboarding guide, testing report | P0 | 10 | — | c9ea939 | Done | PASS | PASS | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-IN-001 | All-India states & districts | 28 states + 8 UTs with PIN prefixes; districts added by admin with generated short codes | P0 | 11 | 0114 | a8258f1, 5f134ad | Done | PASS | PASS (29 Oct; D-4 fixed) | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-IN-002 | Add dealer (admin) | Any state / district (or a new one); approved at once; code GKS-<state>-<district>-XXXXXX or GKS-<state>-XXXXXX | P0 | 11 | 0114 | a8258f1 | Done | PASS | PASS (29 Oct) | Steps 1–10 released 28 Oct (flags off); all-India not released yet
GKS-IN-003 | Flags & commission by state | Flags on for whole states or districts; commission rules for India / state / district (most specific wins) | P0 | 11 | — | a8258f1 | Done | PASS | PASS (29 Oct) | Steps 1–10 released 28 Oct (flags off); all-India not released yet
VER-FIX | PAN / GST / Udyam verification fixes | PAN vs GSTIN's PAN in either order; reviewer approval survives re-check; reviewer row lock; state from any PIN; licence re-runs approval | P0 | 11 | — | faac963 | Done | PASS | Tests only (local + CI); not run on staging | Steps 1–10 released 28 Oct (flags off); all-India not released yet

## Feature flags
Flag | Switches on | Staging | Production
dealer_programme_enabled | Dealer application and portal, codes, attribution, commission, analytics | On (dealer_programme: KA + MH-PUN; others MH-PUN) | Off
gov_verification_auto_approval_enabled | Instant approval on GST/PAN + gateway fee | On (dealer_programme: KA + MH-PUN; others MH-PUN) | Off
dealer_rating_bonus_enabled | Rating bonus on commission | On (dealer_programme: KA + MH-PUN; others MH-PUN) | Off
paid_support_services_enabled | Paid Support services page | On (dealer_programme: KA + MH-PUN; others MH-PUN) | Off