## Summary
GoKesari - staging vs main, defects and open work (26 Oct 2026, 04:30 UTC)
Compares test.gokesari.com (branch staging) with gokesari.com (branch main): pull requests, migrations, defects (docs/testing/qa-defects.json on staging), features in progress or blocked and open blockers. Sources: git history, GitHub, the 25 Oct status workbook and gap analysis, Hostinger build logs. GoKesari only.
Headline
- gokesari.com is up and runs the 24 Oct release (#249). The 25 Oct release (#261 = #254) was rolled back (#262) during a 4 h 15 min outage (E-03).
- staging is ahead of main by 10 merged PRs: 5 with code (#250, #251, #254, #257, #259), 1 process/workflow (#260) and 4 docs. main has nothing staging lacks.
- Migrations: staging 0096; the production database 0094 (0092-0094 stayed after the rollback; additive). 0095-0096 (loose stock in decimals) are not on production.
- Defects: 107 logged - 74 fixed and re-tested, 30 fixed and waiting for a re-test (9 of them only on staging), 1 by design, 1 not a defect, 2 open incidents (E-02, E-03).
- Features: of 277 in the 25 Oct register, 259 are completed and 1 dropped. Still open on production: 3 in progress (mobile app, QA sign-off, checkout speed), 4 blocked (iPhone workflow, production order run, GST/HSN CA check, slow pages) and 3 yet to start (signature capture, email capacity, Hindi/Marathi). Built but waiting for release on staging: GAP-011-019, D-95, the 25 Oct D-items, India-time dates.
Recommended order
1. Hosting first (owner): find why gokesari.com kept restarting on 25 Oct - account resource use, the six other Node apps on the account, Hostinger support - and add uptime monitoring.
2. Re-test on test.gokesari.com: the 9 staging-only fixes (D-23, D-25, D-57, D-69, D-91, D-96, D-103, D-95, D-105), GAP-011-019 and TC-SPI-025.
3. One release PR staging -> main covering #250, #251, #254, #257, #259 and #260 (and the docs), in an agreed window; one deploy at a time; check the site after the deploy (the #260 check).
4. Re-test the 21 production fixes still marked 're-test pending' on gokesari.com.
5. Owner inputs that block features: live payment and payout keys, CA check of GST/HSN, email provider, hosting region, app-store accounts (sheet 'Blockers').
Note: Hostinger preview builds of PRs run the build's migrations against the target site's database before merge (blocker #71); that is how 0092-0094 reached production at the #261 release.
Counts
PRs on staging not on main (code): 5
PRs on staging not on main (process / docs): 5
Open PRs: 1
Defects waiting for a re-test: 30
- of which only on staging: 9
Open incidents: 2
Features in progress: 3
Features blocked: 4
Features yet to start: 3
Open blockers / decisions: 45

## Environments
Environments
Which code and database each site runs.
Site | Branch | Head | Code | Database migrations | Status | Check
gokesari.com (production) | main | 76b9d34 (#262) | Same code as 4a32386 (#249, 24 Oct release) | 0094 recorded (0092-0094 applied by the #261 release / preview build) | Up | Up since 25 Oct 14:15 UTC; 26 Oct 04:25 UTC: / 200 (11.7 s cold), /shops 200 (1.4 s)
test.gokesari.com (staging) | staging | 59a6163 (#260) | Everything below plus all of main | 0096 | Up | 26 Oct 04:25 UTC: /shops 200 (6.1 s)

## Staging vs main
Staging vs main
Merged into staging and not (or no longer) on main, in merge order, plus the open PR. main has nothing staging lacks.
PR | Title | Type | staging | main (gokesari.com) | Migrations | Next step / note
#250 | Fix the seven open bugs from the 21 Oct report (GAP-011, 012, 014, 016, 017, 018, 019) | Code | Merged 25 Oct 02:09 UTC | Staging only | None | Re-test on test.gokesari.com, then release
#252 | QA: staging re-tests of the cart and checkout races passed (D-102, #243) | Docs | Merged 25 Oct 02:18 UTC | Docs only | None | Goes with the next release
#253 | QA 25 Oct: production retest after #248; incident note E-02 (two overlapping deploys) | Docs | Merged 25 Oct 03:27 UTC | Docs only | None | Goes with the next release
#254 | Owner decisions of 25 Oct: D-103, D-57, D-91, D-25, D-96, D-23, D-69 | Code + migrations | Merged 25 Oct 03:58 UTC | Rolled back | 0092 (core), 0093 (core), 0094 (seller) | Released by #261 (25 Oct 09:55 UTC), rolled back by #262 (12:57 UTC) during the 25 Oct outage (E-03). Migrations 0092-0094 stay applied on the production database (additive).
#251 | Dates in India time everywhere (React #418, UTC on server pages) + voucher upload refuses a past end date (TC-FLD-114, D-105) | Code | Merged 25 Oct 04:27 UTC | Staging only | None | Re-test dates on order, wallet and admin pages and TC-FLD-114 (draft PR #263 records the TC-FLD-114 pass on test)
#256 | Report 25 Oct: detailed gap analysis (sessions, all defects, PR gaps) | Docs | Merged 25 Oct 05:07 UTC | Docs only | None | -
#258 | Status report 25 Oct: GAP-008 resolved (Maps server key restriction) | Docs | Merged 25 Oct 05:56 UTC | Docs only | None | -
#257 | Loose stock records decimals (D-95, TC-SPI-025) | Code + migrations | Merged 25 Oct 06:58 UTC | Staging only | 0095 loose_stock_decimals (seller), 0096 cart_loose_quantity | Re-test TC-SPI-025 and stock flows on test; largest change still waiting (36 files)
#259 | GAP-013 rider returns wait for goods at the shop; GAP-019 faster checkout | Code | Merged 25 Oct 09:10 UTC | Staging only | None | Re-test returns completed by staff and re-time wallet checkout
#260 | Release steps: one production release at a time, and a post-deploy check (E-02) | Process + workflow | Merged 25 Oct 12:22 UTC | Staging only | None | The post-deploy workflow runs on pushes to main, so it is not active until released
#263 | QA: D-101 voucher dates re-tested on test.gokesari.com (TC-FLD-114 pass) | Docs | Open PR (draft) | - | None | Open draft into staging (another session)

## Defects open
Defects open
Every defect not closed in docs/testing/qa-defects.json (staging), with where its fix is. 'Both (production)': the fix is on gokesari.com and test.gokesari.com; 'Staging only': not on gokesari.com yet.
ID | Severity | Defect | Status | Fix is on | PR | Next step | Fix (from the log)
D-07 | Medium | A deleted address can still be used at checkout | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Checkout reads only live addresses (loadAddressSnapshot filters deleted_at); a deleted address is refused.
D-08 | Medium | The rider never sees address line 2 (flat, floor) | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | The rider's drop address and navigation label include address line 2.
D-11 | Low | Order notes never reach the shop | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Optional note on the cart (sent with checkout); 'Note from the customer' on the shop's order card.
D-15 | Low | The shop page does not show the minimum order | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | The shop page shows the minimum order with the delivery terms.
D-16 | Low | A broken product photo stays broken (no placeholder) | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | SafeImage notices an image that failed before hydration and shows the placeholder.
D-20 | Medium | A rider who signs out stays online and gets offers | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Sign out sets an online rider offline (a rider mid-delivery keeps the job).
D-23 | Low | After a session expires, sign-in does not return to the page asked for | Fixed - awaiting retest | Staging only | #254 | Re-test on test.gokesari.com; then release again (rolled back from production 25 Oct) | Owner decision 25 Oct: return to the same page if signed in again within 24 h. src/proxy.ts remembers the page opened (httpOnly cookie gk_return_to, 24 h; page navigations only); every sign-in lands on /onboarding, which now sends a complete profile there (same-site paths only, src/lib/return-to.ts). Checked locally: expired session on /wallet → /signin → signed in → /wallet.
D-25 | Medium | A rewarded referral found fraudulent cannot be reversed | Fixed - awaiting retest | Staging only | #254 | Re-test on test.gokesari.com; then release again (rolled back from production 25 Oct) | Owner decision 25 Oct: yes. Admin → Customer referrals → 'Reverse reward' (WALLET_ADJUST, reason required) takes both rewards back as wallet REVERSAL entries pointing at the original credit (reversal_of_id), never below zero (the shortfall is recorded), marks the referral REVERSED, tells both customers and audits it; the friend's mobile can't earn again (migration 0093). Not done: TC-MKT-017 also
D-29 | High | Reconciliation reports books that agree as UNMATCHED | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Every correlated subquery of runReconciliation names its outer column; online payments (captured less refunds) count; refund-pending orders expect 0.
D-30 | High | A shop cannot remove an unavailable line from an online-paid order | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Removing a line or a cheaper substitute refunds the way the order was paid (refundOrderPart: wallet, the original online payment after commit, nothing for COD).
D-32 | High | Wallet 'Add money' is off-screen on a phone | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Wallet grid columns minmax(0,1fr) with min-w-0, so nothing widens the page on a phone.
D-36 | Medium | A negative rider payout is not flagged | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | A negative payout cannot be approved, processed or paid (409) and negative payouts and settlements are listed in the exceptions.
D-40 | Low | Verifying an unpaid top-up gives 500 when the gateway is unreachable | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | No gateway call for a mock payment or without keys; an unreachable gateway gives 400 'try again' and the payment is not failed.
D-46 | Medium | No 'Cancel order' button after pickup | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | One shared rule (src/lib/order-cancellation.ts) for the server, the cancellation quote and both My Orders pages.
D-48 | Medium | 1.5 of a per-piece item can be returned | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Lines sold by count are returned in whole pieces (the full remaining quantity always allowed); the form checks the same.
D-53 | Low | The remove-line reason accepts anything | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | The remove-line reason is one of the shop page's list ('Out of stock', 'Unavailable'; none = Unavailable).
D-54 | Low | The failed-delivery reason accepts anything | Not changed (by design) | Both | - | Product decision only if the owner wants a list of reasons | The rider screen asks for a free-text reason, so any text within the length rules is valid. Turning it into a list is a product decision.
D-56 | Low | Admin refund form rounds 10.555 instead of refusing it | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | src/lib/rupee-input.ts refuses more than 2 decimals on the refund and adjustment forms.
D-57 | Medium | Riders can be approved with no identity documents | Fixed - awaiting retest | Staging only | #254 | Re-test on test.gokesari.com; then release again (rolled back from production 25 Oct) | Owner decision 25 Oct: riders can't be approved without identity documents. Approval refuses (409) unless an Aadhaar, PAN, driving licence or other identity document is on file and not rejected; a vehicle RC alone does not count (delivery-partners.ts approve guard, RIDER_IDENTITY_DOC_TYPES). Test: tests/integration/owner-decisions-2026-10-25.test.ts.
D-69 | Medium | An owner cannot close their shop | Fixed - awaiting retest | Staging only | #254 | Re-test on test.gokesari.com; then release again (rolled back from production 25 Oct) | Owner decision 25 Oct. /shop/manage/hours 'Shop status': 'Close shop for now' / 'Open shop' (orders_paused); 'Close shop permanently' with a reason and the shop name typed (POST /api/shops/[id]/close) — refused while an order is open; the shop becomes INACTIVE (lifecycle CLOSED), leaves search and the storefront, live subscriptions are cancelled; only operations reopen it (approval). Membership (r
D-70 | Low | Product card shows no MRP strike-through or discount | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Product cards show the MRP struck through and 'x% off' (rounded down, from 1 %).
D-75 | Low | No upper limit on minimum order, delivery fee or free-delivery threshold | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Minimum order and free-delivery threshold up to ₹1 lakh, delivery fee up to ₹5,000.
D-78 | Low | A 'javascript:' logo URL is accepted; no logo upload | Fixed in part (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Logo and photo addresses must be https or the site's own image path (javascript:, data:, http: → 422). Open (feature gap): there is no logo upload control.
D-91 | Medium | Order lines record no MRP | Fixed - awaiting retest | Staging only | #254 | Re-test on test.gokesari.com; then release again (rolled back from production 25 Oct) | Owner decision 25 Oct: if a product has an MRP, show it. order_items.mrp_paise (and substitute_mrp_paise) record the MRP at the time of the order (migration 0092); the order page, the tax invoice snapshot, the invoice page and its text copy show it. A later master MRP change does not alter old orders.
D-92 | Low | Order pages lack unit price and payment method | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | Unit price per line and the payment method on the customer's order page and the shop's order card.
D-95 | Medium | Loose stock cannot hold decimals | Fixed (re-test pending) | Staging only | #257 | Re-test on test.gokesari.com; then release | Owner decision 25 Oct: loose stock records decimals. Migration 0095 (seller): shop_products.online_stock / offline_stock, inventory_movements.delta/previous/new_units and stock_alerts.stock_at_alert become numeric(14,3); the ledger triggers convert exactly (round(x * 1000)). Migration 0096 (core): cart_items.quantity numeric(10,3). Rules in src/lib/stock-quantity.ts: a LOOSE product keeps up to 3
D-96 | Low | Inventory page has no filters or sort | Fixed - awaiting retest | Staging only | #254 | Re-test on test.gokesari.com; then release again (rolled back from production 25 Oct) | Search (name or code), category, 'Low stock' and 'Out of stock' filters and a sort (name, available stock, price, status) on /shop/inventory, next to 'Needs a price'.
D-100 | High | On two databases, promoting a product-master record into the catalogue fails (duplicate product code) | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | src/server/pmd/db.ts catalogueProductCode(): on the split layout the code is drawn from the core's product_code_seq and inserted explicitly (src/server/pmd/services/catalogue-bridge.ts); on one database the column default applies as before. Test: tests/integration/pmd-review-bridge.test.ts (fails on the split layout without the fix: P00001 instead of P00016).
D-103 | Medium | Signed-in desktop header: the search box collapses to 0 px and 'Search by voice' covers the Shops link | Fixed - awaiting retest | Staging only | #254 | Re-test on test.gokesari.com; then release again (rolled back from production 25 Oct) | Orders and Subscriptions moved into the account menu for signed-in customers (the nav keeps Shops), the wordmark text hides when signed in, and the search box has a minimum width (md:min-w-44). At 1280 px signed in: search box 354 px, input 260 px, 'Shops' receives its own click (src/components/site-header.tsx).
D-104 | Low | Shop owner menu links to the public page of a shop that is not approved yet | Fixed (re-test pending) | Both (production) | released | Re-test on test.gokesari.com and gokesari.com | src/app/shop/page.tsx passes the slug to the menus only when the shop is APPROVED (the entries are then hidden); src/app/shop/manage/[section]/page.tsx shows 'View public page →' only for an approved shop. Unit test in tests/unit/tile-board.test.ts.
E-02 | High | gokesari.com stopped answering for about 14 minutes after two overlapping deploys | Open (owner decision) | Process | #253, #260 | Owner: confirm the release process; release #260 so the post-deploy check runs on main | Recovered by restarting the Node.js app through the Hostinger API at 02:09:45 UTC (no rebuild). Prevention: one release at a time, a site check (and restart) after every production deploy, an external uptime monitor; ask Hostinger whether overlapping builds can be queued. See docs/gokesari-audit/INCIDENT_2026-10-25_production_hang.md.
D-105 | Medium | Voucher Excel upload accepted an end date that has already passed (also yesterday, from 00:00 to 05:30 IST) | Fixed (re-test pending) | Staging only | #251 | Re-test on test.gokesari.com; then release | parseVoucherWorkbook marks a row INVALID ('End Date has already passed') when End Date < today in APP_TIMEZONE; applyVoucherUpload re-checks each row and skips (marks INVALID) one whose end date passed since. The template's example runs from today for 30 days. Tests with Date pinned to 15 Jan 2030 00:30 IST: create, edit, upload and late apply; the template uploads as it is. Older upload tests mov
E-03 | High | gokesari.com did not answer for about 4 h 15 min after the #261 release (25 Oct 09:59-14:15 UTC) | Open | Production (hosting) | #261, #262 | Owner: check the Hostinger account's resource use (it also runs six Bkesari / Ladwani Node apps created that day); ask Hostinger support; add uptime monitoring before the next release | Build and publish succeeded; the app restarted every few seconds with no error. API restart (12:38) did not help; rollback #262 to the 24 Oct code (deployed 13:02) did not help either; the site answered again at 14:15 UTC without a further change from our side. test.gokesari.com ran the same release throughout. Cause not proven: most likely the account's process / memory limits.

## Features open
Features open
Features and gaps not completed on production, from the 25 Oct feature register brought up to date with PRs #250-#260.
ID | Feature | Status | Where | What is left | Blocked on / next step
GAP-011, 012, 014, 016, 017, 018 | Search '0 shops'; dispute confirmation; returns tab; integrations 'listed'; React #418; pickup wording | Awaiting release | Staging (#250) | Fixed; not on gokesari.com | Re-test on test, then release
GAP-013 | Approved return waiting for a rider can be completed by staff | Awaiting release | Staging (#259) | Fixed; not on gokesari.com | Re-test, release
GAP-019 | Wallet checkout 30-38 s on the test site | IN PROGRESS | Staging (#250, #259) | Fewer and parallel queries; the rest is database distance (GAP-010) | Re-time on test; GAP-010 hosting decision
D-items 25 Oct | Owner decisions: header search (D-103), rider ID documents (D-57), MRP on order lines (D-91), referral reversal (D-25), inventory filters (D-96), sign-in return (D-23), shop closing and membership (D-69) | Rolled back | Staging (#254) | Released 25 Oct and rolled back the same day during E-03 | Re-test on test; release again once production is stable
D-95 | Loose stock in decimals | Awaiting release | Staging (#257) | Built with migrations 0095-0096 | Re-test, release (migrations on production)
D-105 / IST | Dates in India time everywhere; voucher upload refuses a past end date | Awaiting release | Staging (#251) | Built; TC-FLD-114 passed on test (#263) | Release
E-02 process | One release at a time; post-deploy check workflow | Awaiting release | Staging (#260) | Workflow runs from main only | Release
NEW-043 | Android and iPhone app | IN PROGRESS | Android test builds only | Store publishing on hold | Owner: decide when to publish
PLT-017 | 'iPhone app' workflow (EAS build, TestFlight) | BLOCKED | GitHub Actions | Expo project id, EXPO_TOKEN, Apple keys | Owner: store publishing decision, then secrets
QA-003 | Run the 791 test cases and sign off | IN PROGRESS | Test site and production (guest tier) | Signed-tier and staging failures to work through; 30 defects await re-test | Re-run after the next staging build
QA-009 | Order-lifecycle run on production with a real payment | BLOCKED | Not started | Needs a production shop, an approved rider and live Cashfree keys | Owner inputs
NEW-027 | GST rates / HSN codes report for the CA | BLOCKED | Production | CA has to confirm rates, HSN codes and invoice wording | CA verification
GAP-003 | Signature capture at delivery | YET TO START | - | Deferred to Phase 2 | Phase 2 (owner decision)
GAP-009 | Email sending capacity (mail host hourly limit) | YET TO START | - | Higher limit or a transactional email service; SPF/DKIM | Owner: email provider
GAP-010 | Slow signed-in pages and cold first visits | BLOCKED | - | Database far from the web server (11.7 s cold home page on 26 Oct) | Owner: hosting / database region
GAP-015 | Hindi / Marathi for inner page bodies | YET TO START | - | Forms, tables and policy pages are English | Owner: translate? (native review)
NEW-070 | www.gokesari.com redirects to gokesari.com | Live | Production | Observed 308 from www on 25 Oct | Register still says open PR: update it
GAP-008 | Map 'Confirm location' 500 | Done | Production | Resolved: Maps server key restriction (#258) | -

## Blockers
Blockers
Open blockers and decisions (25 Oct workbook, not resolved), plus two new ones. The 25 Oct decisions on D-25 / D-57 / D-69 (row 70) were taken and are left out.
# | Type | Item | What is needed | Who | Status
3 | Go-live blocker | No recorded browser / QA sign-off | Execute the 791-case plan and record results. 24 Oct: automated (QA-010) and run on local, staging and production (guest); register in docs/testing/GOKESARI_MASTER_TEST_REGISTER.xlsx. Remaining: 8 open defects and the test-side follow-ups. | QA / owner | In progress
4 | Go-live blocker | Production cron jobs | Schedule seller-verification, dispute-escalation, shop-acceptance, delivery-dispatch and notifications on gokesari.com; add timeout-sweep and notification-retry when the event layer ships. Not confirmed since 6 Oct. The daily seller-verification job now also starts legal-document grace periods and sends expiry reminders (NEW-040). | Owner | Open
12 | Decision | Which off-by-default features to switch on in production | Choose which of the now-released off-by-default features to switch on in production: F3-F11 and #58 rules, plus fulfilmentOptions, legalDocuments, bankAccounts, bankRefunds, bankAccountCheck, shopReferral, customerSignupReferral, shopWallet, selfRegistration, cancellation PREPARING (all off on gokesari.com after #120). | Owner | Pending
13 | Decision | Event-layer decisions to confirm | Dispatch starts at READY; customer not told when a rider declines; shops propose resolutions only after triage; auto-approved shops classified GREEN; 'support' = operators + admins. | Owner | Pending confirmation
14 | Vendor | Gridlines live keys (seller verification) | Sandbox then live keys; confirm FSSAI / GSTIN fields, Shop Act coverage, IP whitelist, retention and DPA. Production shows verification as paused until then. | Owner | Pending
15 | Legal / CA | CA check of GST rates, HSN codes and invoice wording | Run scripts/gst-hsn-report.sql and have a CA confirm rates, HSN codes, bill-of-supply wording and numbering before invoicing is used for filing. Update 15 Oct: also covers the GST liability, set-off and invoice figures in Inventory & Accounting (NEW-067, on test). Since 19 Oct the rates can be entered in the app (/admin/product-gst, NEW-068). | Owner / CA | Pending
16 | Legal | Seller-verification retention and Shop Act needs | Lawyer/CA to confirm the retention period after closure (default 1,095 days) and Shop Act needs for non-MH / home sellers. | Owner / lawyer | Pending
17 | Legal | Holding shops' prepaid money | Legal review of the shop prepaid wallet; at least a seller-terms clause. | Owner / lawyer | Pending
18 | Owner inputs | Inputs for PR #92 modules 2 and 3 | Modules 2 and 3 are on gokesari.com since #120 (module 2 on mock providers, module 3 switched off). Inputs P1-P6 are needed before using them for real. | Owner | Pending
19 | Agreement | GS1 India and brand permissions | Agreement / written permission and a real sample file for each source; then go-ahead for large-scale ingestion. | Owner | Pending
22 | Release step | Purge CDN cache for /api/images/* after releasing C5 | Release #120 is out: purge the CDN cache for /api/images/* now (rider photos used to be cached publicly). | Owner | At release
24 | Vendor | Cashfree live keys and Refunds API | Set CASHFREE_APP_ID / CASHFREE_SECRET_KEY / CASHFREE_ENV=production and confirm the Refunds API is enabled - the Rs 1 bank-account check refunds every payment. | Owner | Pending
25 | Go-live blocker | Email sending capacity | The test site hit the mail host's hourly cap (451). Raise the limit or use a transactional email service before go-live; check SPF/DKIM for gokesari.com. | Owner | Open
26 | Owner inputs | referrals@gokesari.com and referral codes | Create the mailbox and confirm mail arrives (not readable from the test run); decide who else gets requests (shopReferral.notifyEmails); create referral codes before switching shopReferral.required on. | Owner | Pending
28 | Release step | Tell shop owners before switching legalDocuments on | Shops without the required licence get 15 days; announce it before switching the rule on in production. | Owner | At release
29 | Accounts | App store publishing | Expo account + EAS project id in mobile/app.config.ts; Google Play Console ($25) with the first .aab uploaded by hand; Apple Developer Program ($99/yr); store listings (privacy policy URL, Data safety form, screenshots). Then set MOBILE_* env vars for deep links. Update 14 Oct: the 'iPhone app' workflow (#153) is ready; it needs EXPO_TOKEN, ASC_API_KEY_P8, ASC_KEY_ID, ASC_ISSUER_ID, APPLE_TEAM_ID, the Expo project id and the App Store Connect app record. 18 Oct: store publishing ON HOLD by owner decision. | Owner | On hold
33 | Security | Rotate database passwords before go-live | Urgent: the production Neon neondb_owner password was posted in a chat on 12 Oct - reset it now and update DATABASE_URL in hPanel (and the GitHub secrets). Rotate the other database passwords before go-live as planned. | Owner | Open
34 | Decision | Tile Board: build the four entries that have no feature behind them? | Customer Favourites, App theme, Call rider (rider number is not shown to customers today); shop owner Theme. The board shows the nearest real page in their place. | Owner | Pending
35 | Performance / hosting | Slow signed-in pages and cold first visits | Put the database and the web server in the same region, or keep database connections open longer than 20 s. Signed-in pages take 3.4-5.1 s of server time on the test site; the gokesari.com home waited ~4 s after a quiet spell (the board part is fixed by #127 / #130). | Owner | Open
36 | Release step | Turn on prepared statements (DATABASE_PREPARED_STATEMENTS=on) | Set it for test.gokesari.com, check signed-in pages and that Neon's pooled host accepts prepared statements, then set it for gokesari.com. | Owner | Pending
38 | Decision | Translate the body of inner pages into Hindi / Marathi? | Boards, header, menus, tabs and error screens are translated; forms, tables and policy pages are English. Thousands of strings; needs a native-speaker review. | Owner | Pending
39 | Security | Delete the downloaded copy-shops SQL files | copy-shops-1-PREVIEW.sql / copy-shops-2-APPLY.sql hold the 5 owners' contact details - delete every downloaded copy. | Owner | Open
40 | Owner inputs | Copied shops: sign-in, legal documents, two shops without location | The 5 copied owners sign in on gokesari.com and upload their legal documents; add map locations for the 2 original production shops (Asmy super market x2) so Nearby can list them. | Owner | Pending
43 | QA | Record browser runs for Seller Central and the saffron wordmark | Seller Central (#142) has only local checks; no staging / production run after #153. Run both on test and gokesari.com and record results. Update 15 Oct: Seller Central was used on test in the order-lifecycle run (TR-23, shop switcher checked); a full Seller Central pass and the saffron wordmark run are still to record. | QA / dev | Open
44 | Owner inputs | Production order-lifecycle run (real payment) | For QA-009: a production shop with delivery on and its owner's sign-in email; an approved rider (or permission to register one for approval); confirmation that the Cashfree live keys are set; the owner pays the small real top-up. No test data or sandbox keys on gokesari.com. Listed again in Owner inputs §14 (18 Oct). | Owner | Pending
50 | Go-live blocker | Bulk upload: mobile store builds | EAS / Expo account and Apple Developer account for the AAB and the iPhone build | Owner | Open
51 | Owner action | Inventory & Accounting: INTEGRATION_ENCRYPTION_KEY value | The variable is set on test and production but is not base64 of 32 bytes (test reports encryption not configured; GST link answers 500). Set `openssl rand -base64 32` (a different value per site) in Hostinger and redeploy. | Owner | Open
52 | Decision / vendor | Inventory & Accounting: licensed GSP for GST returns | Choose and contract a GSP (Masters India, ClearTax, IRIS, Tally GSP, Vayana) for live GSTR-2B/2A/1 pull; until then owners upload the file from gst.gov.in (works on production). | Owner | Open
53 | Decision | Inventory & Accounting: AI reading of supplier bills | Allow bills to be read by Claude (ANTHROPIC_API_KEY + INVOICE_EXTRACTION_PROVIDER=claude): needed for photos, handwriting, Hindi and Marathi. Without it: e-invoice, Excel, PDF text and typing. | Owner | Open
54 | Owner action | Inventory & Accounting: crons | Schedule POST /api/cron/gst-reminders daily and /api/cron/bill-captures every 10 min (Bearer CRON_SECRET) on both sites. | Owner | Open
55 | Vendor | Inventory & Accounting: bill forwarding by email and S3 bucket | Inbound mail provider (INBOUND_EMAIL_SECRET / _DOMAIN) for forwarding; S3-compatible bucket credentials (ACCOUNTS_S3_*) - bills stay in the database until then. | Owner | Open
57 | Owner inputs | Payment gateway live keys and webhook secrets | PAYMENT_GATEWAY + Cashfree (or Razorpay / PhonePe) live keys; payment and payout webhook secrets | Owner | Pending
58 | Owner inputs | Payout account and keys | RazorpayX / Cashfree payout account and keys for the 5-day shop payouts | Owner | Pending
59 | Owner inputs | GoKesari GSTIN, legal details and invoice prefix | For GoKesari fee invoices (F10.2.5) | Owner | Pending
60 | Legal / CA | CA confirmation of TCS / TDS / SAC rates | Rates looked up 18 Oct; CA must confirm before production use | Owner / CA | Pending
61 | Owner inputs | Grievance Officer details | Name, contact and address to publish on the grievance portal (consumer protection rules) | Owner | Pending
62 | Owner inputs | Deep links: Android signing fingerprint and Apple Team ID | MOBILE_* values so gokesari.com links open the app | Owner | Pending
63 | Owner inputs | Mobile push keys | EAS project + FCM / APNs keys for real push notifications (app 1.2.0) | Owner | Pending
64 | Owner choice | Switch on the new batch features in production | Every batch feature is OFF on gokesari.com: online payments, broadcast offers, pickup QR (needs PICKUP_QR_SECRET), rider navigation, payouts, fee invoices, push | Owner | Pending
65 | Owner inputs | Batch cron jobs on both sites | payments-reconcile (5 min), auth-housekeeping, timeout-sweep, payouts and the other entries in crontab.txt | Owner | Pending
67 | Owner inputs | iPhone app builds from GitHub | Repository secret EXPO_TOKEN and the Expo project id in mobile/app.config.ts; the 'iPhone app' workflow failed on 18 Oct without them | Owner | Open
69 | Legal / CA | Enter GST rates and HSN codes for the live catalogue | No product has a GST rate or HSN code, so tax invoices use the 0% default. Enter them at /admin/product-gst once the CA confirms (see #15). | Owner / CA | Pending
71 | Platform | Hostinger PR preview builds migrate the target site's database | A preview build of a PR into main runs MIGRATE_ON_BUILD against production before the PR merges (how 0089-0091 reached production early, and the D-99 journal skip on test). Decide whether previews should migrate. | Owner / dev | Open
new | Hosting | gokesari.com outage after the 25 Oct release (E-03) | Check the Hostinger account's CPU / memory / process use and the six other Node apps on it; ask Hostinger why the app kept restarting; add uptime monitoring with an alert | Owner | Open
new | Release step | Next production release | One release PR staging -> main for #250, #251, #254, #257, #259, #260 (+ docs), in an agreed window, one deploy at a time, with the site checked after the deploy | Owner / dev | Pending

## Incidents
Incidents
Production incidents on 25 Oct.
ID | When | What | Recovery | Prevention | Status
E-02 | 25 Oct 01:56-02:10 UTC (about 14 min) | Two overlapping production builds (#248 and #249 merged 75 s apart) | API restart of the Node app | Release process changed (#260, on staging only) | Open (owner decision)
E-03 | 25 Oct 09:59-14:15 UTC (about 4 h 15 min) | After the #261 release the app kept restarting with no error; test.gokesari.com unaffected. Not proven: most likely hosting limits | Restart (12:38) and rollback #262 (13:02) did not bring it back; it answered again at 14:15 without a further change from our side | None yet: hosting check, Hostinger support, uptime monitoring | Open