## Summary
GoKesari: detailed gap analysis - sessions, defects, PRs (local, staging, main) - 25 Oct 2026, 05:00 UTC (10:30 IST)
Where | Branch | Commit | Latest migration | CI | Note
gokesari.com (production) | main | 4a32386 | 0091 | green | Release #249, 25 Oct 01:48 UTC
test.gokesari.com (staging) | staging | 82c6fd9 | 0094 | #254 merge green; #251 merge running | 5 PRs ahead of main; migrations 0092-0094 run on the next build
Local: this cloud session | staging (82c6fd9) | 82c6fd9 | 0094 | - | Clean, nothing unpushed
Local: owner's Mac | - | - | - | - | Not visible from the cloud; one known item (permissions allowlist) yet to commit
Defects (107 in the log) | Count
Fixed, re-test passed | 74
Fixed, re-test pending | 29
Closed, no change (not a defect / by design) | 2
Open | 2
Where the fix is | Count
In both | 95
Release to main | 8
By design | 1
Open | 1
Not a defect | 1
Hosting / release process | 1
Not yet re-tested or open, by severity | Count
Low | 14
Medium | 13
High | 5
Info | 1
Next steps
1. Wait for staging CI on #251's merge (running), then check test.gokesari.com rebuilt and ran migrations 0092-0094.
2. Re-test on test.gokesari.com: the 8 defects fixed only in staging (D-23, D-25, D-57, D-69, D-91, D-96, D-103, D-105), GAP-011/012/014/016/017/018/019, and TC-CART-001.
3. Re-test on gokesari.com the 21 defects already live there but marked 're-test pending' (D-07 ... D-104).
4. Open one release PR staging -> main (#250-#254). Production migrations 0092-0094 in an owner-approved window; one deploy at a time (E-02).
5. Bring main's 21 Oct status report (#223) back into staging.
6. Decide PR #255 (Driving Simulator page): it targets main directly and is outside the staging -> test -> main flow.
7. Owner decisions still open: E-02 (release process), D-95 (follow-up PR coming), GAP-008/009/010/013/015; Phase 2: GAP-003.
8. On the Mac: commit the .claude/settings.json allowlist; decide on the GoKesari spreadsheets (1 Oct session).
9. Delete the 5 stale branches; archive finished sessions.
Notes
Scope: GoKesari only. Sessions for Ladwani, Education, ATIP and Bkesari are left out (CLAUDE.md).
Defect source: docs/testing/qa-defects.json on staging (107 entries) and on main (105). Fixes and their log entries ride in the same PRs, so a fix is on main when main's copy marks it fixed.
GAP items: Feature Register of GOKESARI_FEATURE_STATUS_REPORT_2026-10-21.xlsx, updated with #250 and #251.
Which build each site actually serves is not checked: no version endpoint, and the Hostinger connector needs authorising in claude.ai connector settings.

## Defects (all)
ID | Severity | Title | Test cases | Status (staging log) | Status (main log) | Fix in staging (test) | Fix in main (prod) | Gap | Next step | Found | Last re-test
D-01 | Low | Write APIs read the request before checking the session | TC-SEC-001, TC-RBAC-002 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local + test.gokesari.com (guest tier) | 2026-10-24 gokesari.com guest tier after release #242 (df923a2): TC-SEC-001, TC-RBAC-002 pass (docs/testing/qa-runs/2026-10-24-production-release-3.json)
D-02 | Low | A malformed id in the URL answers 500 | TC-SEC-002, TC-DISC-007 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local + test.gokesari.com | 2026-10-24 gokesari.com guest tier after release #242 (df923a2): TC-SEC-002, TC-DISC-007 pass (docs/testing/qa-runs/2026-10-24-production-release-3.json)
D-03 | Low | Responses advertise the framework (X-Powered-By: Next.js) | TC-SEC-010, TC-SEC-005 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local + test.gokesari.com | 2026-10-24 gokesari.com guest tier after release #242 (df923a2): TC-SEC-010, TC-SEC-005 pass (docs/testing/qa-runs/2026-10-24-production-release-3.json)
D-04 | Medium | PIN codes starting with 0 (and 000000) are accepted | TC-LOC-002, TC-FLD-020, TC-FLD-016 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local + test.gokesari.com | 2026-10-24 gokesari.com guest tier after release #242 (df923a2): TC-LOC-002, TC-FLD-020, TC-FLD-016 pass (docs/testing/qa-runs/2026-10-24-production-release-3.json)
D-05 | Low | No robots.txt on the test site | TC-SEC-008 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 test.gokesari.com | 2026-10-24: TC-SEC-008 pass in local round 3 (one database); local round 3 (split); production release 3
D-06 | Medium | Shop search by PIN code finds nothing | TC-DISC-004 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 gokesari.com (guest tier) | 2026-10-24 gokesari.com guest tier after release #242 (df923a2): TC-DISC-004 pass (docs/testing/qa-runs/2026-10-24-production-release-3.json)
D-07 | Medium | A deleted address can still be used at checkout | TC-FLD-025 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-08 | Medium | The rider never sees address line 2 (flat, floor) | TC-FLD-013 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-09 | Medium | '+91' typed in a mobile field becomes a different number | TC-LOC-009, TC-FLD-012 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-LOC-009, TC-FLD-012 pass in local round 3 (one database); local round 3 (split)
D-10 | Medium | Shops whose hours run past midnight always show Closed | TC-LOC-026, TC-FLD-052 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-LOC-026, TC-FLD-052 pass in local round 3 (one database); local round 3 (split)
D-11 | Low | Order notes never reach the shop | TC-CART-017, TC-FLD-028 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-12 | Low | Deleting the default address leaves no default | TC-FLD-018 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-018 pass in local round 3 (one database); local round 3 (split)
D-13 | Low | 'Show all shops' drops the type and other filters | TC-DISC-003 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-DISC-003 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-14 | Low | '%' and '_' in a search match everything | TC-DISC-007, TC-FLD-022 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24 gokesari.com guest tier after release #242 (df923a2): TC-DISC-007, TC-FLD-022 pass (docs/testing/qa-runs/2026-10-24-production-release-3.json)
D-15 | Low | The shop page does not show the minimum order | TC-DISC-013 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-16 | Low | A broken product photo stays broken (no placeholder) | TC-DISC-018 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-17 | High | A session cookie keeps working after sign-out | TC-AUTH-034 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-AUTH-034 pass in local round 3 (one database); local round 3 (split)
D-18 | Medium | An account can be created without accepting the Terms | TC-FLD-004, TC-MKT-002 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-004, TC-MKT-002 pass in local round 3 (one database); local round 3 (split); production release 3
D-19 | Medium | A suspended account's sign-in link shows an error page | TC-AUTH-027 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-AUTH-027 pass in local round 3 (one database); local round 3 (split)
D-20 | Medium | A rider who signs out stays online and gets offers | TC-AUTH-040 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-21 | Low | The previous user's delivery location survives sign-out | TC-AUTH-038 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-AUTH-038 pass in local round 3 (one database); local round 3 (split)
D-22 | Low | Sign-out is not audited | TC-AUTH-045 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-AUTH-045 pass in local round 3 (one database); local round 3 (split)
D-23 | Low | After a session expires, sign-in does not return to the page asked for | TC-AUTH-044, SC-27 | Fixed - awaiting retest | Open (deferred) | Yes (#254) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-24 local (signed and local tiers)
D-24 | Medium | No risk flag for repeated referral abuse | TC-MKT-015, SC-35 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-MKT-015, SC-35 pass in local round 3 (one database); local round 3 (split)
D-25 | Medium | A rewarded referral found fraudulent cannot be reversed | TC-MKT-017 | Fixed - awaiting retest | Open (owner decision) | Yes (#254) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-24 local (signed and local tiers)
D-26 | Low | Society gate contact '123456' is accepted | TC-FLD-105 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-105 pass in local round 3 (one database); local round 3 (split)
D-27 | Low | Society rider mobile is read as its last 10 digits | TC-FLD-106 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-106 pass in local round 3 (one database); local round 3 (split)
D-28 | Low | Text in a segment's number field is silently dropped | TC-FLD-122 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-122 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-29 | High | Reconciliation reports books that agree as UNMATCHED | TC-PAY-032, TC-COD-011, TC-FIN-021, TC-FIN-026, SC-14, SC-29 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-30 | High | A shop cannot remove an unavailable line from an online-paid order | TC-PAY-029 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-31 | High | Subscription orders carry no delivery address | TC-SUB-013 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SUB-013 pass in local round 3 (one database); local round 3 (split)
D-32 | High | Wallet 'Add money' is off-screen on a phone | TC-PAY-002 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-33 | Medium | Admin money trace shows no payment for an online-paid order | TC-PAY-026 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-PAY-026 pass in local round 3 (one database); local round 3 (split)
D-34 | Medium | A cancelled subscription can still be edited | TC-SUB-008 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SUB-008 pass in local round 3 (one database); local round 3 (split)
D-35 | Medium | Bad subscription start dates give 500; past dates accepted | TC-FLD-108 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-108 pass in local round 3 (one database); local round 3 (split)
D-36 | Medium | A negative rider payout is not flagged | TC-COD-010 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-37 | Low | Bad skip / pause / override dates give 500 | TC-FLD-109 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-109 pass in local round 3 (one database); local round 3 (split)
D-38 | Low | Off-step subscription quantities are accepted | TC-FLD-107 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-107 pass in local round 3 (one database); local round 3 (split)
D-39 | Low | Marking another user's notification read is not refused | TC-NTF-012 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-NTF-012 pass in staging round 3; local round 3 (one database); local round 3 (split); production release 3
D-40 | Low | Verifying an unpaid top-up gives 500 when the gateway is unreachable | TC-PAY-004 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-41 | Low | Wallet amount 10.555 is rounded instead of refused | TC-FLD-030 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-030 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-42 | Low | Low-balance threshold has no upper limit | TC-FLD-032 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-032 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-43 | Low | Cart button says 'Pay from wallet' when 'Pay online' is chosen | TC-PAY-001 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-PAY-001 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-44 | High | A suspended rider can still accept the offer in hand | TC-DEL-026 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-DEL-026 pass in local round 3 (one database); local round 3 (split)
D-45 | Medium | Rider reliability and fairness ranking never applies | TC-DSP-020, TC-DSP-021 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-DSP-020, TC-DSP-021 pass in local round 3 (one database); local round 3 (split)
D-46 | Medium | No 'Cancel order' button after pickup | TC-ORD-008 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-47 | Medium | Rider KYC and bank numbers are not format-checked | TC-FLD-092, TC-FLD-093, TC-DEL-030 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-092, TC-FLD-093, TC-DEL-030 pass in local round 3 (one database); local round 3 (split)
D-48 | Medium | 1.5 of a per-piece item can be returned | TC-RET-003, TC-FLD-094 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-49 | Low | A suspended or rejected rider can be approved again with no reason | TC-DEL-027 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-DEL-027 pass in local round 3 (one database); local round 3 (split)
D-50 | Low | No notice to the rider on reactivate or deactivate | TC-DEL-015 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-DEL-015 pass in local round 3 (one database); local round 3 (split)
D-51 | Low | Vehicle numbers are not normalised or checked | TC-FLD-091, TC-DEL-030 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-091, TC-DEL-030 pass in local round 3 (one database); local round 3 (split)
D-52 | Low | Cancelling during the rider search leaves the search running | TC-DSP-011 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-DSP-011 pass in local round 3 (one database); local round 3 (split)
D-53 | Low | The remove-line reason accepts anything | TC-FLD-083 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-54 | Low | The failed-delivery reason accepts anything | TC-FLD-087 | Not changed (by design) | Not changed (by design) | - | - | By design | None | 2026-10-24 local (signed and local tiers)
D-55 | Low | Grievance phone unchecked; ticket lookup reveals which tickets exist | TC-FLD-101 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-101 pass in local round 3 (one database); local round 3 (split)
D-56 | Low | Admin refund form rounds 10.555 instead of refusing it | TC-FLD-099 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-57 | Medium | Riders can be approved with no identity documents | TC-DEL-025 | Fixed - awaiting retest | Open (owner decision) | Yes (#254) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-24 local (signed and local tiers)
D-58 | High | A product can be put on sale at ₹0 | TC-CAT-004 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-CAT-004 pass in local round 3 (one database); local round 3 (split)
D-59 | High | The shop page shows only the first 100 products | TC-CAT-050 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-CAT-050 pass in local round 3 (one database); local round 3 (split)
D-60 | Medium | Excel price list: 0 is valid, blank is an error | TC-CAT-033 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-CAT-033 pass in local round 3 (one database); local round 3 (split)
D-61 | Medium | Referral performance report gives 500 | TC-ONB-025 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-ONB-025 pass in local round 3 (one database); local round 3 (split)
D-62 | Medium | A suspended or approved (trading) shop can be rejected | TC-ONB-038, TC-FLD-121 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-ONB-038, TC-FLD-121 pass in local round 3 (one database); local round 3 (split)
D-63 | Medium | Invalid GSTINs are accepted | TC-FLD-043 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-043 pass in local round 3 (one database); local round 3 (split)
D-64 | Medium | A GST certificate valid 'To: Not Applicable' is blocked as expired | TC-FLD-047 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-047 pass in local round 3 (one database); local round 3 (split)
D-65 | Medium | Impossible opening times are accepted | TC-FLD-052 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-052 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-66 | Medium | Product master: GST '-5' read as 5 %, 7 % accepted | TC-FLD-078 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-078 pass in local round 3 (one database); local round 3 (split)
D-67 | Medium | MRP of ₹0 or ₹10 crore accepted | TC-FLD-079, TC-CAT-062 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-079, TC-CAT-062 pass in local round 3 (one database); local round 3 (split)
D-68 | Medium | A product removed from a shop cannot be listed again | TC-CAT-034 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-CAT-034 pass in local round 3 (one database); local round 3 (split)
D-69 | Medium | An owner cannot close their shop | TC-ONB-042 | Fixed - awaiting retest | Open (owner decision) | Yes (#254) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-24 local (signed and local tiers)
D-70 | Low | Product card shows no MRP strike-through or discount | TC-CAT-008, SC-22 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-71 | Low | Inventory form rounds 10.555 instead of refusing it | TC-CAT-032 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-CAT-032 pass in local round 3 (one database); local round 3 (split)
D-72 | Low | A closed (deleted) shop can be approved | TC-ONB-043 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-ONB-043 pass in local round 3 (one database); local round 3 (split)
D-73 | Low | Shop address of spaces accepted; text not trimmed | TC-FLD-037 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-037 pass in local round 3 (one database); local round 3 (split)
D-74 | Low | Stored FSSAI number accepts anything | TC-FLD-044 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-044 pass in local round 3 (one database); local round 3 (split)
D-75 | Low | No upper limit on minimum order, delivery fee or free-delivery threshold | TC-FLD-051, TC-FLD-053 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-76 | Low | No preparation-time setting for the shop | TC-FLD-054 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-054 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-77 | Low | Line breaks in the shop description are dropped | TC-FLD-055 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-055 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-78 | Low | A 'javascript:' logo URL is accepted; no logo upload | TC-FLD-056 | Fixed in part (re-test pending) | Fixed in part (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-79 | Low | Product master: '-1 kg' read as 1 kg; any unit accepted | TC-FLD-074 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-074 pass in local round 3 (one database); local round 3 (split)
D-80 | Medium | Order monitoring's date filter uses UTC days, not IST | TC-ADM-004 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-ADM-004 pass in local round 3 (one database); local round 3 (split)
D-81 | Low | Some staff and shop routes answer 422 (field names) instead of 403 | TC-RBAC-003, TC-RBAC-005 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-RBAC-003, TC-RBAC-005 pass in staging round 3; local round 3 (one database); local round 3 (split)
D-82 | Low | Address form: a server refusal highlights no field | TC-FLD-125 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-125 pass in local round 3 (one database); local round 3 (split)
D-83 | Low | Vouchers with a ₹0 budget, past dates or a budget below one bonus are accepted | TC-FLD-114 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-114 pass in local round 3 (one database); local round 3 (split)
D-84 | Low | Reject and classification reasons are stored with outer spaces | TC-FLD-121 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-121 pass in local round 3 (one database); local round 3 (split)
D-85 | High | A return on an online-paid order is never refunded | SC-29 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: SC-29 pass in local round 3 (one database); local round 3 (split)
D-86 | Medium | A physical stock count makes the product unavailable online | SC-23 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: SC-23 pass in local round 3 (one database); local round 3 (split)
D-87 | Medium | A returned unopened unit is not put back in stock | TC-SPI-020, SC-26 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SPI-020, SC-26 pass in local round 3 (one database); local round 3 (split)
D-88 | Medium | A substitution does not give the original item's stock back | TC-SPI-010, SC-26 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SPI-010, SC-26 pass in local round 3 (one database); local round 3 (split)
D-89 | Medium | A stale stock save overwrites a sale made meanwhile | TC-SPI-022 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SPI-022 pass in local round 3 (one database); local round 3 (split)
D-90 | Medium | The public storefront API shows exact stock | TC-SPI-027 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SPI-027 pass in local round 3 (one database); local round 3 (split); production release 3
D-91 | Medium | Order lines record no MRP | TC-SPI-005, SC-25 | Fixed - awaiting retest | Open (deferred) | Yes (#254) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-24 local (signed and local tiers)
D-92 | Low | Order pages lack unit price and payment method | TC-SPI-006, TC-SPI-008 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local (signed and local tiers)
D-93 | Low | The order e-mail has no lines or totals | TC-SPI-004 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SPI-004 pass in local round 3 (one database); local round 3 (split)
D-94 | Low | Out-of-stock products are not listed after buyable ones | TC-SPI-023 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-SPI-023 pass in local round 3 (one database); local round 3 (split)
D-95 | Medium | Loose stock cannot hold decimals | TC-SPI-025 | Open (owner decided - in a follow-up change) | Open (deferred) | No | No | Open | Follow-up PR (decimal loose stock), owner decided | 2026-10-24 local (signed and local tiers)
D-96 | Low | Inventory page has no filters or sort | TC-SPI-026 | Fixed - awaiting retest | Open (deferred) | Yes (#254) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-24 local (signed and local tiers)
D-97 | Low | Stock and price fields have no upper bounds; forms round decimals | TC-FLD-058, TC-FLD-059, TC-FLD-061, TC-FLD-062, TC-FLD-063, TC-FLD-065, TC-FLD-068 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-058, TC-FLD-059, TC-FLD-061, TC-FLD-062, TC-FLD-063, TC-FLD-065, TC-FLD-068 pass in local round 3 (one database); local round 3 (split)
D-98 | Low | Finance entries have no upper bounds; an unfinished week can be settled | TC-FLD-112, TC-FLD-113, TC-FLD-116, TC-FLD-117, TC-FLD-118 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 local (signed and local tiers) | 2026-10-24: TC-FLD-112, TC-FLD-113, TC-FLD-116, TC-FLD-117, TC-FLD-118 pass in local round 3 (one database); local round 3 (split)
D-99 | Blocker | After the round-2 release, test.gokesari.com refused every session (sign-in did not stick) | TC-AUTH-001, TC-AUTH-034 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 test.gokesari.com, right after the round-2 fixes (PR #232) were deployed | 24 Oct 2026 15:05 and 16:00 UTC on test.gokesari.com (purchase-lists QA run, build 2853b3d): customer and customer2 signed in with emailed codes and stayed signed in — /api/auth/session returns the us
D-100 | High | On two databases, promoting a product-master record into the catalogue fails (duplicate product code) | TC-PMD-004, TC-FLD-075 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 local, two-database (split) layout, build 7e4e920
D-101 | Medium | Vouchers took 'today' in UTC: from midnight to 05:30 IST a past end date was accepted | TC-FLD-114 | Fixed - retest passed | Fixed - retest passed | Yes | Yes | In both | None | 2026-10-24 CI (both layouts) at 02:09 IST on 25 Oct | 2026-10-24: TC-FLD-114 pass in local round 3 (one database); local round 3 (split)
D-102 | Medium | Two simultaneous 'add to cart' of the same product: one answers 500 (new line) or one add is lost (existing line) | TC-CART-001, TC-LIST-021 | Fixed - retest passed | Fixed (re-test pending) | Yes | Yes | In both | None | 2026-10-24 test.gokesari.com (signed tier, purchase-lists run; build 487f11b) | 24 Oct 2026 22:11 UTC on test.gokesari.com, build e44252b (#241): the staging customer sent two POST /api/cart of Burger Bun at the same moment. Empty cart, 2 + 2: [200, 200] and one line of 4, 5 of 5
E-01 | Info | The host's firewall answers some requests itself (SQL-like search text, bursts) | TC-DISC-004, TC-DISC-007, TC-FLD-022, TC-RBAC-002 | Not a defect | Not a defect | - | - | Not a defect | None | 2026-10-24 test.gokesari.com
D-103 | Medium | Signed-in desktop header: the search box collapses to 0 px and 'Search by voice' covers the Shops link |  | Fixed - awaiting retest | Open | Yes (#254) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-24 test.gokesari.com (purchase-lists screenshots, staging customer; build 487f11b)
D-104 | Low | Shop owner menu links to the public page of a shop that is not approved yet | TC-UX-001 | Fixed (re-test pending) | Fixed (re-test pending) | Yes | Yes | In both | Re-test (fix is live on both sites) | 2026-10-24 test.gokesari.com round 3 (signed tier, shop owner whose newest shop is pending approval)
E-02 | High | gokesari.com stopped answering for about 14 minutes after two overlapping deploys | TC-PRE-001 | Open (owner decision) | (not in main's log) | - | - | Hosting / release process | Owner: one deploy at a time + site check after each release | 2026-10-25 01:56 UTC, while waiting for the release #248 deploy | 2026-10-25 02:10-02:35 UTC: guest tier 96 pass, 0 fail after the restart (docs/testing/qa-runs/2026-10-25-production-release-4.json)
D-105 | Medium | Voucher Excel upload accepted an end date that has already passed (also yesterday, from 00:00 to 05:30 IST) | TC-FLD-114 | Fixed (re-test pending) | (not in main's log) | Yes (#251) | No | Release to main | Re-test on test.gokesari.com, then release to main | 2026-10-25 code check of TC-FLD-114 with the clock pinned to 00:30 IST (tests/integration/vouchers.test.ts)

## Known gaps GAP-001-019
ID | Area | Item | 21 Oct status | 25 Oct status | In staging | In main | Fixed / built in | Next step
GAP-001 | Delivery | Pickup QR code | Completed, off | Completed, off | Yes | Yes | #190, #194 | Owner: set PICKUP_QR_SECRET and switch on
GAP-002 | Delivery | In-app turn-by-turn navigation | Completed, off | Completed, off | Yes | Yes | #190, #194 | Owner: routing provider, switch on
GAP-003 | Delivery | Signature capture at delivery | Yet to start | Deferred to Phase 2 | No | No | - | Phase 2 (owner decision)
GAP-004 | Delivery | Broadcast job offers / radius widening | Completed, off | Completed, off | Yes | Yes | #190, #194 | Owner: switch on (needs timeout-sweep cron)
GAP-005 | Finance | Automated bank transfer (settlements, payouts) | Completed, off | Completed, off | Yes | Yes | #190, #194 | Owner: payout keys (RazorpayX / Cashfree)
GAP-006 | Finance | Platform tax invoice for GoKesari's own fees | Completed, off | Completed, off | Yes | Yes | #190, #194 | Owner: GSTIN, legal details, prefix; CA rates
GAP-007 | Orders | Customer Cancel button on My Orders | Completed, live | Completed, live | Yes | Yes | #122, #123 | None
GAP-008 | Location | Map 'Confirm location' 500 on test | Blocked | Blocked | - | - | - | Owner: Maps server key restriction (IP, not referrer)
GAP-009 | Notifications | Email sending capacity | Yet to start | Open (owner) | - | - | - | Owner: email provider / higher limit
GAP-010 | Performance | Slow signed-in pages, cold first visits | Blocked | Blocked | - | - | - | Owner: hosting / database region
GAP-011 | Search | Search shows '0 shops' for products nearby shops sell | Yet to start | Fixed, re-test pending | Yes | No | #250 | Re-test on test, release
GAP-012 | Disputes | Admin dispute resolution: no confirmation | Yet to start | Fixed, re-test pending | Yes | No | #250 | Re-test on test, release
GAP-013 | Returns | Staff cannot complete a return waiting for a rider | Yet to start | Open (owner) | No | No | - | Owner: business rule
GAP-014 | Orders | /orders?tab=returns shows the Active list | Yet to start | Fixed, re-test pending | Yes | No | #250 | Re-test on test, release
GAP-015 | Navigation / UX | Hindi / Marathi for inner page bodies | Yet to start | Open (owner) | No | No | - | Owner: translate? (needs native review)
GAP-016 | Platform | Drizzle bare-id subquery bug (integrations 'listed') | Yet to start | Fixed, re-test pending | Yes | No | #250 | Re-test on test, release
GAP-017 | Platform | React #418 hydration (and UTC times on server pages) | Yet to start | Fixed, re-test pending | Yes | No | #250 (2 pages), #251 (every date) | Re-test on test, release
GAP-018 | Orders | My Orders wording after switch to pickup | Yet to start | Fixed, re-test pending | Yes | No | #250 | Re-test on test, release
GAP-019 | Checkout | Wallet checkout 30-38 s on test | Yet to start | Fixed in part, re-test pending | Yes | No | #250 (54 -> 46 queries) | Re-time on test; rest depends on GAP-010

## PR gaps
PR | Title | From -> to | State | In staging | In main | Migrations | Gap / action
#250 | Fix the seven open bugs (GAP-011 to GAP-019) | peaceful-pascal -> staging | Merged 25 Oct 02:09 UTC | Yes | No | - | Release to main
#251 | Dates in India time everywhere + voucher upload past end date (D-105) | laughing-brown -> staging | Merged 25 Oct 04:27 UTC | Yes | No | - | Release to main (staging CI on the merge still running)
#252 | QA: staging re-tests of cart and checkout races passed (D-102) | serene-curie -> staging | Merged 25 Oct 02:18 UTC | Yes | No | - | Release to main (docs)
#253 | QA 25 Oct: production retest after #248; incident note E-02 | hopeful-cerf -> staging | Merged 25 Oct 03:27 UTC | Yes | No | - | Release to main (docs)
#254 | Owner decisions: D-103, D-57, D-91, D-25, D-96, D-23, D-69 | peaceful-pascal -> staging | Merged 25 Oct 03:58 UTC | Yes | No | 0092, 0093 (core), 0094 (seller) | Migrations on test with the deploy; on production in an approved window
#223 | Feature status report 21 Oct (merged straight into main) | peaceful-pascal -> main | Merged 24 Oct 22:02 UTC | No | Yes | - | Bring main back into staging (docs)
#255 | Add Driving Simulator placeholder page (+ Android app link) | festive-ride -> main | Open, draft | No | No | - | Goes to main directly, skipping staging and test.gokesari.com. Owner: confirm it belongs on GoKesari; if so, retarget to staging
(none) | Release staging -> main | staging -> main | Not opened | - | - | 0092-0094 | Open one release PR after the test-site re-tests

## Branches
Branch | Commits not in staging | Last commit | PR | Verdict
claude/festive-ride-udspyl | 2 (+2 from main) | 25 Oct | #255 open (to main) | Active - see PR #255
claude/trusting-allen-97xhex | 1 | 19 Oct | #212 closed | Superseded by #211. Safe to delete
claude/serene-gates-7cymxj | 2 | 9 Oct | #121 squash-merged | Already in staging. Safe to delete
claude/tile-board-ui | 1 (WIP) | 9 Oct | none | Superseded by the shipped Tile Board. Safe to delete
claude/awesome-dijkstra-fmccpl | 18 | 3 Oct | #26 closed | Abandoned MySQL port. Delete or keep as archive
claude/amazing-cannon-5n3fro | 1 | 2 Oct | #27 closed | Old docs fix. Check, then delete
(owner's Mac) claude/permissions-allowlist | ? | 25 Oct | none | Still not on GitHub: .claude/settings.json allowlist yet to commit

## Sessions
Session | Status | Last update (UTC) | Branch / PR | Waiting on | Suggested action
Pin India time in all client-side date formatting (this session) | Running | 25 Oct 05:00 | #251 merged | - | This report
Feature status review and update #PR250+ | Idle | 25 Oct 03:22 | #250, #254 merged | - | D-95 follow-up PR is next there
Fix cart add race (D-99) | Idle - review ready | 25 Oct 04:22 | #252 merged | Its scheduled TC-FLD-114 re-test (19:00 UTC today) | Let it run once #251 is on test.gokesari.com
Gokesari.com test automation | Idle - done | 25 Oct 03:27 | #253 merged | - | Archive, or use it for the staging re-test run
Seamless deployment approvals (several projects; GoKesari part = PR #255) | Idle - needs input | 25 Oct 04:51 | #255 open (to main) | You: decide on PR #255 | Decide; retarget to staging if kept
Frequent "allow once" prompts | Archived | 25 Oct 03:40 | Mac: claude/permissions-allowlist | You: run the commit on the Mac | Still not on GitHub
PostgreSQL frequent downtime | Idle - needs input | 24 Oct 21:30 | no code | You: which site, what 'down' looks like | Answer it
Hostinger plugin installation (20 Oct) | Idle - needs input | 20 Oct 19:08 | no code | settings.json approval | Superseded; archive
Inventory & Accounting module for shop owners | Idle - needs input | 15 Oct 18:27 | released (#179) | An open question | Read and answer, or archive
GitHub billing messages issue | Idle - needs input | 11 Oct 02:39 | - | PROD_DATABASE_URL / prod DB password | Confirm done, archive
Older GoKesari sessions 28 Sep - 14 Oct with open questions (crons, Maps key, domain access, db:migrate, mobile, Turbopack, Mac spreadsheets) | Idle | 28 Sep - 14 Oct | merged or no code | Old questions | Very likely overtaken; check, then archive. Decide on the Mac spreadsheets
About 30 other GoKesari sessions 6-24 Oct | Idle - done | 6-24 Oct | PRs merged | - | Nothing pending; archive